## CWI Summary
Summary For Ichalkarnji, Kolhapur
Address | HDFC Bank Ltd. Upper Ground Floor & first floor ,12/215,Bungalow Road, Ichalkarnji,Tal- Hatkanagale,Dist -Kolhapur - 416115.
Contractor | M/s. Teamswift Projects Pvt Ltd
Area | 2,280 Sqft
LOC, Code | 0736
PO No | CPC/014849/25-26
FINAL BILL SUMMARY
Sr. No | Particulars | AS per WO | As per CWI | Excess | Saving | Total
I | Civil & related works | 1504620 | 1444213.22 | 102419.15 | -162825.93 | -60406.78
II | POP and false ceiling work | 324120 | 295074.12 | 21427.64 | -50473.52 | -29045.88
III | Carpentry and Interior work | 2147140 | 1999427.59 | 364478.61 | -512191.02 | -147712.41
IV | Painting works | 69930 | 79262 | 31362.25 | -22030.25 | 9332
V | Rolling Shutter and MS Work | 28800 | 0 | 0 | -28800 | -28800
VI | Electrification and Allied Work | 1106859 | 793654.56 | 105439 | -418643.44 | -313204.44
VII | Additional Work | 0 | 162810.6 | 162810.6 | 0 | 162810.6
A | TOTAL | 5181469 | 4774442.09 | 787937.25 | -1194964.16 | -407026.91
TAXES | TAXES:
Taxes as applicable (pl indicate applicable taxes)
a) | CGST @ 9% | 466332.21 | 429699.7881 | 70914.3525 | -107546.7744 | -36632.4219
b) | SGST @ 9% | 466332.21 | 429699.7881 | 70914.3525 | -107546.7744 | -36632.4219
c)
B | Total | 932664.42 | 859399.5762 | 141828.705 | -215093.5488 | -73264.8438
(A + B) | Grand Total (incl. taxes) | 6114133.42 | 5633841.6662 | 283657.41 | -430187.0976 | -146529.6876

## Extracted Data
U. Code | Sub Category | Nature of Works | Particulars | Rate | As per CWI (Qty) | As per CWI (Amount) | Rate per sq.feet | Unit
Sr. No | Others | Others/Uncategorized | Particulars | 0 | 0 | 0 | 0 | Unit
I | Others | Others/Uncategorized | CIVIL & RELATED WORKS | 0 | 0 | 0 | 0
1 | Others | Others/Uncategorized | Demolition / Clearing Works | 0 | 0 | 0 | 0
a | Others | Others/Uncategorized | Dismantling/Demolishing the following and carting away the debris from the site and unloading at a approved location as per statutory rules and regulations. | 0 | 0 | 0 | 0
i | Others | Others/Uncategorized | Dismantling of existing brickwork | 12 | 0 | 0 | 0 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Dismantling of existing dado tiles without plaster | 11 | 932.39 | 10256.29 | 4.5 | Sq.ft
iii | Partition | CARPENTRY AND INTERIOR WORKS | Dismantling of existing plaster | 11 | 459.73 | 5057.03 | 2.22 | Sq.ft
iv | PAINTING WORKS | PAINTING WORKS | Existing flooring including bedding material & PCC/IPS. | 16 | 540.83 | 8653.28 | 3.8 | Sq.ft
v | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Existing Doors / Windows | 381 | 16 | 6096 | 2.67 | Nos.
vi | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Dismantling of existing Sanitary wares & Plumbing Fittings | 1199 | 0 | 0 | 0 | Nos.
vii | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Existing Rolling Shutter , Safety door, collapsible door etc. | 11 | 0 | 0 | 0 | Sq.ft
viii | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Existing Electrical fittings and fixtures | 3 | 0 | 0 | 0 | Sq.ft
ix | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Dismantling of existing wooden & aluminum partitions | 10 | 0 | 0 | 0 | Sq.ft
x | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Miscellaneous items such as false ceilings. | 11 | 0 | 0 | 0 | Sq.ft
xi | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Shifting /Dismantling existing furniture items (For renovation projects only) | 487 | 0 | 0 | 0 | Nos.
xii | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Dismantling of existing RCC 6 "/ 9" thk wall. | 84 | 2 | 168 | 0.07 | Sq.ft
2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Construction of Masonry Walls | 0 | 0 | 0 | 0
a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and erecting 115 mm thk , Half brick wall (first class bricks) in cement and sand mortar 1:3 with flush joint complete with material, labour, scaffolding, curing etc. The rate to include Appling chicken mesh at RCC to brickwork joints wherever required and RCC stiffener at every 1 meter intervals in 1:2:4 concrete. (Excluding plastering). The work to include cost for lintels / sills in RCC required for Doors , windows, openings etc. | 114 | 0 | 0 | 0 | Sq.ft
b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Same as 2(a) but 230mm thk ( Single brick wall) | 150 | 0 | 0 | 0 | Sq.ft
c | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Do-do as 2(a) above but 100mm thk siporex / AAC / Aerocon / light weight block wall (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,aerocon blocks) | 124 | 0 | 0 | 0 | Sq.ft
d | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Do-do as 2(a) above but 150mm thk siporex / AAC / Aerocon / light weight block wall (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,aerocon blocks) | 129 | 851.4 | 109830.6 | 48.17 | Sq.ft
3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | R.C.C Works | 0 | 0 | 0 | 0
a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | R.C.C work :Providing & casting in-situ reinforced cement concrete 225 mm thick for wall/columns/ as per details/ drawings/ design( The rate to include cost of re-baring/Hilti/drilling and joining with existing beam or lintel including shuttering, steel , concrete, inserts, cutout for ventilator, hacking, curing, bonding chemical / slurry all complete, design and certification from structural consultant. Grade of concrete to be considered shall be M25 & steel to be considered as 12mm dia tor steel @150mm c/c both way in two layers staggered by 75mm in both directions. The thickness of walls to be 225 mm without plaster. 300mm x300mm RCC column to be provided near the strong room door for mounting strong room door. | 444 | 0 | 0 | 0 | Sq.ft
b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Do-do as 3(a) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) | 699 | 0 | 0 | 0 | Sq.ft
c | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Similar to above but for Floor slab with single layer of steel comprising 12mm dia @150 mm c/c and concrete jointing compound to be provided in case the premises is located on first floor and floor below does not belong to the bank. | 198 | 0 | 0 | 0 | Sq.ft
d | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Do-do as 3(c) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) | 330 | 0 | 0 | 0 | Sq.ft
e | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Similar to above but for Floor slab with double layer of steel comprising of 12 mm dia @ 150 mm c/c Mesh on both ways staggered by 75mm and concrete jointing compound to be provided in case the premises is located on first floor and floor below does not belong to the bank. | 336 | 0 | 0 | 0 | Sq.ft
f | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Do-do as 3(f) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) | 453 | 0 | 0 | 0 | Sq.ft
g | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Similar to above but without concrete (ceiling reinforcement Mesh to be provided in case upper floor does not belong to the bank) | 129 | 0 | 0 | 0 | Sq.ft
i | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Do-do as 3(g) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) | 389 | 0 | 0 | 0 | Sq.ft
j | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Similar to item 3(c) i.e. 6mm MS plate instead of reinforcement mesh for wall cladding. Including necessary MS framework. Complete as directed. | 468 | 0 | 0 | 0 | Sq.ft
k | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Fixing in place of Strong Room Door by providing necessary grouting in the floor and proper support. The vendor should ensure that the door is fixed in plumb. | 8559 | 0 | 0 | 0 | Job
l | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Fixing in place of Ventilator by providing necessary grouting in the floor and proper support. The vendor should ensure that the door is fixed in plumb. | 5720 | 0 | 0 | 0 | Job
4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Plaster | 0 | 0 | 0 | 0
a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | P/A 1:4 cement plaster(Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement) with waterproofing compound to brick/RCC work including scaffolding in single coat of minimum 12 mm thick finished to receive Plaster of Paris levelling coat. | 46 | 2317.13 | 106587.98 | 46.75 | Sq.ft
b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | External Plaster in 1:3 with waterproofing compound to brick/RCC work up to 25mm thk including cost of scaffolding up to 20'.( Prior approval of Bank required) (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement) | 62 | 0 | 0 | 0 | Sq.ft
5 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Waterproofing treatment | 0 | 0 | 0 | 0
a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing & appling water proofing treatement by Mixing and applying two coats of ready-to-use acrylic polymer based waterproofing component on modified cement base of approved make to a thickness of 2 mm over the bottom and sides of toilet and pantry slabs, including preparation of surface, finishing, curing etc. all complete at all levels as per manufacturer's specifications and as directed. | 45 | 285.08 | 12828.6 | 5.63 | Sq.ft
6 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Brick Bat Coba | 0 | 0 | 0 | 0
a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Proving and Laying brick bat coba up to 150mm thk in 1:4 cement mortar incl. of necessary slope towards nahni trap, over waterproofing course including finishing the top surface with water proofing compound to receive the floor tiles as per India Waterproofing Co. Measurements of floor area shall only be considered for said works.(Toilet area) | 88 | 109.28 | 9616.64 | 4.22 | Sq.ft
7 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Plain Cement Concrete | 0 | 0 | 0 | 0
a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | P/E Plain cement concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) of grade M -10 ( 1:3:6 ) including shuttering for levelling course for flooring within the Bank Premise. The thickness may vary from 75mm to 125 mm as per requirement. (As per site condition - Prior approval of Bank required) | 50 | 534.5 | 26725 | 11.72 | Sq.ft
b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Same as 7(A) but for depth upto 250 mm | 105 | 0 | 0 | 0 | Sq.ft
c | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Do-do as 7(a) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) | 72 | 0 | 0 | 0 | Sq.ft
d | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Do-do as 7(b) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) | 139 | 0 | 0 | 0 | Sq.ft
e | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Similar to above but for exterior works (As per site condition - Prior approval of Bank required) | 64 | 0 | 0 | 0 | Sq.ft
f | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Do-do as 7(e) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) | 80 | 0 | 0 | 0 | Sq.ft
g | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and laying cement concrete flooring 40 - 50 mm thick , C.M. 1:3 laid to proper level and slope cost should including compaction as directed and curing complete in all respect. (As per site condition - Prior approval of Bank required)(Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) | 38 | 0 | 0 | 0 | Sq.ft
8 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Drywall Panel | 0 | 0 | 0 | 0
a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and fixing of Solid Dry Wall Panel 75mm thick of size 2400/2700/3000mm in length and 600mm width certified by Green Building council having a unique tongue and groove jointing system. The panels are made of two fibre reinforced cement sheets enclosing a light weight aerated concrete core composed of cement, fly ash and other binders. Density is 720~780kg/cum, panel has Axial load carrying capacity min 83 KN/m with 2.5 times factor safety as per test method of ASTM -E-72:98 . These panels need to meet Uniformly distributed load (Bending load 80 -95kg/sqm & modulus of rupture 40-58kg/sqcm) as per test method ASTM-E-72:98 & IS 2380 Part 4. Thermal Conductivity typical K value - 0.17 ~0.21 W/m K, having a fire rating of 120 minutes as per BS 476 part 20-22 and sound transmission coefficient 36~40 as per IS 9901 (part 1) 1981 The wall panels to be installed with G.I Floor Channel : 14 x 75 x 25 mm size of 1 mm thick at bottom and 38 X75X 38 mm size with 1mm thickness at top. Tongue and Groove joints will be joined with elastomeric cementitious highly polymerized jointing compound as per manufacturer’s recommendation. Non-woven Self-adhesive glass fiber / fiber mesh tape in sufficient width to be applied to reinforce the exposed skin of jointing system. Jointing compound to be applied on joint finally to make good . Rate by the vendor to include scaffolding, lifting charges and jointing material, wastages etc. as a complete item of work excluding finishing etc. The installation will be done as per specification, drawing and as directed by EIC/consultant. All work to be done by certified installer with proper supervision following WMS and as per instruction of Engineering in charge. (Ideal for Server room , Solid Partition, Store rooms ) Approved Brands : HIL Limited , Visaka (Vnext) , Everest Panel) (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Aerocon Panel) | 160 | 0 | 0 | 0 | Sq.ft
b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Do-do as 8(a) above but 100mm thk (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Aerocon Panel) | 254 | 0 | 0 | 0 | Sq.ft
9 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Flooring | 0 | 0 | 0 | 0
a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Vitrified Tile Flooring | 0 | 0 | 0 | 0
i | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Vitrified Tile Flooring - Proving and Laying 1000mm x 1000mm / 800mm X 800 mm Vitrified floor tiles (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,vitrified floor tiles) over a 75 mm thk cement mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) bedding (1: 4) as per the design. The joints shall be kept up to 4 mm and filled with epoxy grouting of approved shade. (Basic cost of tile up to up to Rs. 110/-Sq. ft). | 152 | 2009.78 | 305486.56 | 133.99 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Similar to above but for providing and fixing 75mm high skirting/border. | 66 | 86.45 | 5705.7 | 2.5 | R.ft
iii | Partition | CARPENTRY AND INTERIOR WORKS | Proving and Laying 600mm x 600mm anti-skid and Anti-dust Vitrified floor tiles for Toilet floors with a 75 mm thk cement mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) bedding (1: 4) as per the design including colour cement in joint to matching shade. The joints shall be kept as thin as possible should not exceeding 1 mm. (Basic cost of tile upto Rs. 60 /-Sq. ft). ( For server room, store, pantry, toilets ) (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, vitrified floor tiles) Somany : Delmon Beige - (600 x 600) | 102 | 1359.32 | 138650.64 | 60.81 | Sq.ft
iv | PAINTING WORKS | PAINTING WORKS | Similar as 9_a_iii but for providing and fixing 75mm high skirting/border. | 57 | 129.89 | 7403.73 | 3.25 | R.ft
b | PAINTING WORKS | PAINTING WORKS | Ceramic Tile Flooring | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Proving and Laying of 300 mm x 300mm Ceramic floor tiles (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,ceramic tiles) (1st quality) of approved make over a 75 mm thk cement mortar (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) bedding (1: 4) as per the pattern given including colour cement joints in matching shade. Rate to include curing, acid wash, etc. complete. The joints shall be kept as thin as possible not exceeding 1 mm. (Basic cost of tile Rs. 35/- Sq. ft) | 76 | 0 | 0 | 0 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Similar to above but for providing and fixing 3" high skirting/border. | 38 | 0 | 0 | 0 | R.ft
c | POP Punning | POP & FALSE CEILING WORKS | Granite Flooring | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Supplying and laying 12 mm thk machine cut & machine polished Granite flooring , on a prefinished surface with 1:3 cement sand mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) .(Basic cost of granite Rs 180 /sq.ft). Rate shall be inclusive of machine polishing edges in case of protruding edges & groove if ordered. . Measurement for payment shall be as per laid area . | 317 | 0 | 0 | 0 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Similar to above but 75mm high skirting/border. | 128 | 0 | 0 | 0 | R.ft
d | POP Punning | POP & FALSE CEILING WORKS | Vitrified Tiles in wooden finish (in HNW areas with prior approval) | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Same as item 9.a-(i) but vitrified tiles in wooden finish. (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,vitrified floor tiles) (Basic cost of tile Rs.85/- per sq ft.) | 122 | 0 | 0 | 0 | Sq.ft
e | POP Punning | POP & FALSE CEILING WORKS | Carpet Flooring (in HNW areas with prior approval) | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and laying carpet of 20 ounce loop pile in polypropylene in carpet tile (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,vitrified floor tiles)form without underlay. Cost also included surface preparation required for laying of it and carpet protection. ( Basic cost of tile Rs.160 /- per sq ft.) | 152 | 0 | 0 | 0 | Sq.ft
f | POP Punning | POP & FALSE CEILING WORKS | Vinyl Flooring | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing fixing Vinyl Anti-Static flooring 5 mm thick Armstrong/LG/Tusker installed on smooth, hard & absolutely levelled sub-floor. Brushed SS edges shall be used at the seams. Conductive adhesives shall be used for fixing . | 105 | 418.52 | 43944.6 | 19.27 | Sq.ft
g | POP Punning | POP & FALSE CEILING WORKS | False Flooring | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | P/F Raised access floor (false floor app. 150 mm to 230 mm high) .The panel shall be finished with antistatic 600x600x1.5mm laminate laid on base panels with solvent free epoxy, edge shall have 0.6mm PVC lipping & floor shall have UDL of 10 KN/Sq.m point load of 2.5 | 339 | 73.32 | 24855.48 | 10.9 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | P/F Raised access floor (false floor app. 300 mm high) .The panel shall be finished with antistatic 600x600x1.5mm laminate laid on base panels with solvent free epoxy, edge shall have 0.6mm PVC lipping & floor shall have UDL of 10 KN/Sq.m point load of 2.5 | 350 | 0 | 0 | 0 | Sq.ft
h | POP Punning | POP & FALSE CEILING WORKS | POP covering on Flooring | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and applying POP covering on flooring for floor protection with plastic sheet between the flooring and POP. The rate should include the cleaning of POP and plastic on completion before handing over completed site. | 12 | 0 | 0 | 0 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Providing and applying covering on flooring for floor protection with Heavy duty bubble sheet on newly placed flooring. The rate should include the cleaning of plastic on completion before handing over completed site. | 12 | 2049.09 | 24589.08 | 10.78 | Sq.ft
i | POP Punning | POP & FALSE CEILING WORKS | Wall Dado Tiles | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Proving and Laying Ceramic glaze Wall Tiles (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) ( Colour : White ) of size 450mm x 300mm (1st quality) of somany make or approved make over a cement mortar bedding (1:4) (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) as per the pattern given including filling joint with colour cement in matching shade. (Basic cost of tiles Rs. 50/- Sq.ft). | 76 | 0 | 0 | 0 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Proving and Laying wall dado Vitrified glaze tiles of size 600 mm X 600 mm (1st quality) of approved make over a cement mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) bedding (1:4) as per the pattern given including filling joint with colour cement in matching shade. (Basic cost of tiles upto Rs. 65/- Sq.ft). (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, wall tiles) Somany : Delmon Beige - (600 x 600) | 99 | 0 | 0 | 0 | Sq.ft
10 | POP Punning | POP & FALSE CEILING WORKS | Pantry / Dining / Toilet Counter & Thresholds | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing & fixing 600mm deep pantry counter made out of 12mm thk black granite supported by 25mm thk Kadappa to be fixed horizontally and vertically. The cost to be included of the platform to have 75mm wide granite fascia horizontally with molded edges as per design. 100mm high granite band over dado level to be provided. 75mm thk platform at floor level inside the counter should be provided finished with 75mm high granite skirting from outside The cost to include of making hole in the counter for fixing sink, End verticals to be fixed made of Kadappa and covered with granite to be provided as per the design. (Basic Cost of Granite 180/- sq.ft). Cost of Storage, CP fittings, SS sink are not included. | 2796 | 20 | 55920 | 24.53 | R.ft
b | POP Punning | POP & FALSE CEILING WORKS | Providing & Fixing Dining Counter with S.S Angle Bracket in approved Black Granite finish at ht. 750 mm from Finished Floor Level.(Depth of Counter 600 mm) (Basic Cost of Granite 180/- sq.ft) | 1483 | 0 | 0 | 0 | R.ft
c | POP Punning | POP & FALSE CEILING WORKS | Providing & fixing wash basin counter in Toilets of 600 mm Deep made of 12 mm thk black granite supported on 25thk Kadappa base. 75 mm wide granite facia to be provided at the edge of the counter. The cost to include of making hole in the counter for fixing wash basin, Cost of CP fittings, Wash basin are not included. (Basic Cost of Granite 180/- sq.ft) | 1815 | 0 | 0 | 0 | R.ft
d | POP Punning | POP & FALSE CEILING WORKS | Providing & Fixing of size 450mm X 900mm both sides polished divider for Urinal made of 12mm thk Black Granite embedded in the wall. The edges of the granite to be machine polished. | 1716 | 1 | 1716 | 0.75 | Nos.
e | POP Punning | POP & FALSE CEILING WORKS | Providing & Laying 150mm wide Black Granite Threshold at ATM and Main Entrance. (Basic Cost of Granite 180/- sq.ft) | 211 | 29.41 | 6205.51 | 2.72 | R.ft
f | POP Punning | POP & FALSE CEILING WORKS | Providing & Laying 75 mm wide Black Granite Threshold for Toilets & Pantry. (Basic Cost of Granite 180/- sq.ft) | 177 | 11.5 | 2035.5 | 0.89 | R.ft
11 | POP Punning | POP & FALSE CEILING WORKS | External Paving/Flooring/Window sill | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Supplying and laying 20 mm thk glossy chequered tiles heavy duty external grade for paving on a prefinished surface with 1:3 cement (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) sand mortar over a 50 mm thk cement mortar bedding (1: 4) / PCC as per the design including colour cement float joints in matching shade. (Basic cost of tiles Rs.35 /- per sq. ft.) | 91 | 0 | 0 | 0 | Sq.ft
b | POP Punning | POP & FALSE CEILING WORKS | Providing and laying inter locking Paver blocks (heavy duty) in two or more shades by excavating the existing surface by @ 150mm to 230mm and providing layer for gravel over the entire area and covering the same with a layer of graded sand limestone, screeding / sinner to the required slope and providing primer locking pave blocks. The rate is inclusive of PCC (1:2:4) bed at the edges of the pattern as per site conditions. (Basic cost of tiles Rs.40 /- per sq. ft.) | 98 | 0 | 0 | 0 | Sq.ft
c | POP Punning | POP & FALSE CEILING WORKS | Providing and laying Kotah stone, flooring 25mm-30mm thk. Having sizes not less than 55cms x 55 cms in plain/ diamond pattern and bed of 1:6 cm including cement float filling joints with neat cement slurry, curing, polishing and clearing complete in all respect. (for strong room flooring) | 110 | 0 | 0 | 0 | Sq.ft
d | POP Punning | POP & FALSE CEILING WORKS | Treads & risers of steps. Providing and laying in required position polished granite slab 18mm thk with machine cut and machine polish in CM 1:3 for treads/ risers of steps. The rate is inclusive of full rounded nosing for treads and 3 no's groove on treads complete in all respect. ' The granite to be fixed with adhesive (approved Low VOC/No VOC Adhesives to be used by Bank or CPC team as exception / Refer Make and Model sheet, Adhesives) in case the same is to be fixed on a plywood surface. (Basic cost of Jet black granite Rs. 180/- sq.ft.) | 314 | 0 | 0 | 0 | Sq.ft
e | POP Punning | POP & FALSE CEILING WORKS | Sill & jambs to windows / Doors. Providing and laying in required positions granite, slab 12 mm thk (Single piece), of approved make & colour with machine, cut and machine polish up to 145mm wide ; in cement mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) of 1:3 for sills and jambs of windows .The rate is inclusive of full rounded molding at the edges from inside. (Basic cost of granite Rs. 180/- sq.ft.) | 194 | 85.04 | 16497.76 | 7.24 | R.ft
f | POP Punning | POP & FALSE CEILING WORKS | Providing and laying jambs to door at required positions granite slab 12mm thk. Up to 2100mm in length (Double piece) and machine polish up to 145mm wide ; in cement mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) of 1:3 for jambs of door .The rate is inclusive of fillet rounded molding at the edges from inside. (Basic cost of granite Rs. 180/- sq.ft.) | 385 | 84 | 32340 | 14.18 | R.ft
g | POP Punning | POP & FALSE CEILING WORKS | Treads & risers of steps. Providing and laying in required position granite slab 12mm thk with machine cut and machine polish in 19 mm BWP Plywood (BWP Plywood which are "Free of Added Urea Formaldehyde" (required) approved by Bank or CPC team as exception / Refer Make and Model sheet, BWP Plywood) for treads/ risers of steps of internal staircase of branch. The rate is inclusive of full rounded nosing for treads and 3 no's groove on treads complete in all respect. ' The granite to be fixed with adhesive (approved Low VOC/No VOC Adhesives to be used by Bank or CPC team as exception / Refer Make and Model sheet, Adhesives) in case the same is to be fixed on a plywood surface. (Basic cost of granite Rs. 180/- sq.ft.) | 396 | 0 | 0 | 0 | Sq.ft
12 | POP Punning | POP & FALSE CEILING WORKS | Façade Treatment | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | P/F 12mm thk Black Granite to be fixed with approved adhesive (approved Low VOC/No VOC Adhesives to be used by Bank or CPC team as exception / Refer Make and Model sheet, Adhesives) and curing on plywood base (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) paneling on the façade. (Cost of plywood paneling not included). (Basic cost of granite Rs. 180/- sq.ft.) | 474 | 0 | 0 | 0 | Sq.ft
13 | POP Punning | POP & FALSE CEILING WORKS | Handicapped Access Ramp | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing and constructing handicapped ramp at a slope of 1:12 or as per site conditions with raised floor to be made by filling dubber stone soling and compacted by sand dust & 1:4 cement mortar ( Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, cement) to match the required level. The width of ramp should be minimum upto 1200mm | 1114 | 0 | 0 | 0 | R.ft
b | POP Punning | POP & FALSE CEILING WORKS | Providing and constructing raised floor for staircase and midlanding by filling dubber stone soling and compacted by sand dust ,1:4 cement mortar (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) to match the required level. | 271 | 0 | 0 | 0 | Sq.ft
14 | POP Punning | POP & FALSE CEILING WORKS | Ramp Finishes | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing & fixing 100mm wide polished Black Granite Patti of 18mm thk on ramp for maintaining level difference in order to form anti-skid surface. | 305 | 0 | 0 | 0 | Sq.ft
b | POP Punning | POP & FALSE CEILING WORKS | Providing & fixing 12mm thk prepolished Black Granite flooring on staircase midlanding at Main Entrance as per approved quality laid to required pattern with cement mortar of required thickness. Joints shall be finished with epoxy based grouting compound. Rate shall be inclusive of Cutting of slab, wastage etc. basic rate of granite delivered at site ( Basic cost of granite Rs.145/- per sq.ft. ) | 345 | 0 | 0 | 0 | Sq.ft
15 | POP Punning | POP & FALSE CEILING WORKS | Plumbing | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Internal concealed plumbing works for water supply, drainage and related works per toilet comprising of wash basin, WC, urinals etc. all complete. Gents Toilet (1 no Urinal + 1 nos. wash basin + 1 no EWC) | 11441 | 1.25 | 14301.25 | 6.27 | Lumpsum per toilet
b | POP Punning | POP & FALSE CEILING WORKS | Internal concealed plumbing works for water supply, drainage and related works per toilet comprising of wash basin, WC etc. all complete. Ladies Toilet (1 Wash Basin + 1 EWC) | 11017 | 1 | 11017 | 4.83 | Lumpsum per toilet
c | POP Punning | POP & FALSE CEILING WORKS | Supply fixing and installation of heavy duty 20/15 mm Concealed stop cocks ( Make Jaguar Continental Series ) to be provided only at the entry point of plumbing lines within the toilets / pantry | 2012 | 1 | 2012 | 0.88 | Nos.
d | POP Punning | POP & FALSE CEILING WORKS | Internal Plumbing work for Pantry. Water supply and drainage points for sink, water supply point to water purifier and proper drain point. | 6073 | 1 | 6073 | 2.66 | Lumpsum
e | POP Punning | POP & FALSE CEILING WORKS | Supply & fixing of Nahani trap ( Make : Nathani , Seko ) with Stainless Steel Chili trap mesh on it. | 1207 | 4 | 4828 | 2.12 | Nos.
f | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing machanical driven industrial grade water meter made up of solid brass and should have multi jet, anti corrosion and sedimentation free features for horizontal flow of approved make (Make : Kranti , Everest and approved by CPC as expectional basis) | 3919 | 1 | 3919 | 1.72 | Nos.
16 | POP Punning | POP & FALSE CEILING WORKS | Sanitary wares (Pure white colour) | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing first quality European Water closet with attached cisten of Dual Flush Cistern of flow rates of 4/2 LPF approved by bank or CPC team as exception/ Refer make and model sheet, water closet cost is including flush tank, seat cover, connection pipe, chair bracket and All complete as per design and specifications. | 14831 | 2 | 29662 | 13.01 | Nos.
b | POP Punning | POP & FALSE CEILING WORKS | Same as above 16(a) wall hung EWC but with dual Flush Valves for Flow of 25 mm with flush valve of flow rates of 4/2 LPF approved by bank or CPC team as exception/ Refer make and model sheet. | 15305 | 0 | 0 | 0 | Nos.
c | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing of single Urinal with electronic Flushing system (large flat back type) (flow rates of max upto 1.5 LPF approved by bank or CPC team as exception/ Refer make and model sheet, urinal) including all connection pipe , necessary brackets, urinal spreader, dome grating All complete as per design and specifications. | 11059 | 0 | 0 | 0 | Nos.
d | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing of single Urinal pressmatic Flushing system (large flat back type) (flow rates of max upto 1.5 LPF approved by bank or CPC team as exception/ Refer make and model sheet, urinal) including all urinal valve with auto closing system (Pressmatic taps), connection pipe , necessary brackets, urinal spreader, dome grating All complete as per design and specifications. | 7627 | 2 | 15254 | 6.69 | Nos.
e | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing under/ Over counter Wash Basin of approved shape (make model as approved by bank or CPC team as exception ). including waste coupling, brackets & connection pipe etc. all required to complete the work and make it functional. All complete as per design and specifications. | 7203 | 4 | 28812 | 12.64 | Nos.
f | POP Punning | POP & FALSE CEILING WORKS | Same as above 15(c) but half Pedestal Wash Basin | 7398 | 0 | 0 | 0 | Nos.
g | POP Punning | POP & FALSE CEILING WORKS | Similar to above but in divider plate (make model as approved by bank or CPC team as exception ) | 2118 | 0 | 0 | 0 | Nos.
h | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing Pantry staintless steel sink of size 18" x 16" (make and model as approved by bank or CPC team as exception). cost including waste coupling & connection pipe etc. all required to complete the work and make it functional. All complete as per design and specifications. | 7013 | 0 | 0 | 0 | Nos.
17 | POP Punning | POP & FALSE CEILING WORKS | Plumbing Fittings | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing heavy duty pillar cock for pantry manufactured by (Pillar Cock with water flow rate or Aerators (flow Restrictors) restricting flow rate upto 3 LPM @ 3 Bar Pressure, approved by bank or CPC team as exception/ Refer make and model sheet, Pillar cock, Aerators) all complete as per standard specifications and as directed by the CPC. | 1716 | 0 | 0 | 0 | Nos.
b | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing angular stopcock manufactured by (make & model as approved by bank or CPC team as exception) 15 mm dia. all complete as per standard specifications and as directed by CPC | 1222 | 6 | 7332 | 3.22 | Nos.
c | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing heavy duty 15 mm dia C.P. brass short body bibcock (two in one) of approved manufacturer (Bib Cock with water flow rate or Aerators (flow Restrictors) restricting flow rate upto 3 LPM @ 3 Bar Pressure, approved by bank or CPC team as exception/ Refer make and model sheet,two way bib cock) all complete as per standard specifications and as directed by the in - Charge. | 2008 | 2 | 4016 | 1.76 | Nos.
d | POP Punning | POP & FALSE CEILING WORKS | providing and fixing of heavy duty bottle trap. (Make & model as approved by bank or CPC team as exception). | 1716 | 4 | 6864 | 3.01 | Nos.
e | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing heavy duty pillar cock auto closing system (Pressmatic taps) for washbasins manufactured by (Pillar Cock with water flow rate or Aerators (flow Restrictors) restricting flow rate upto 3 LPM @ 3 Bar Pressure, approved by bank or CPC team as exception/ Refer make and model sheet, Pillar cock) all complete as per standard specifications and as directed by the CPC | 2309 | 4 | 9236 | 4.05 | Nos.
f | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing heavy duty sensor pillar cock (Automatic taps) for washbasins manufactured by (Pillar Cock with water flow rate or Aerators (flow Restrictors) restricting flow rate upto 3 LPM @ 3 Bar Pressure, approved by bank or CPC team as exception/ Refer make and model sheet, Pillar cock) all complete as per standard specifications and as directed by the CPC | 10000 | 0 | 0 | 0 | Nos.
g | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing aerators Shower Flow Aerator (Spray) to lavatory faucets and kitchen faucets with 21mm dia (For Lavatory Faucets - Flow rate restricted to 3 LPM @ 3 Bar Pressure and for Kitchen Faucet - Flow rate restricted to 3.8 LPM @ 3 Bar Pressure. Make & model as approved by bank or CPC team as exception/ refer make and model sheet, Aerators) | 228 | 0 | 0 | 0 | Nos.
h | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing hand type Jet Spray with adjustable nozzle and push type valve and inlet flexible water connection in the toilet manufactured by M/s. Jaguar continental series or as approved by bank or CPC team | 1716 | 2 | 3432 | 1.51 | Nos.
18 | POP Punning | POP & FALSE CEILING WORKS | Toilet Accessories | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Supplying of disposable Soap Dispenser of make as approved by bank or CPC team | 1207 | 4 | 4828 | 2.12 | Nos.
b | POP Punning | POP & FALSE CEILING WORKS | Supply & fixing of Toilet paper holder of make as approved by bank or CPC team | 762 | 2 | 1524 | 0.67 | Nos.
c | POP Punning | POP & FALSE CEILING WORKS | Supply & fixing of SS finish Robe Hooks of make as approved by bank or CPC team | 495 | 2 | 990 | 0.43 | Nos.
d | POP Punning | POP & FALSE CEILING WORKS | CP brass towel ring make as approved by bank or CPC team | 805 | 4 | 3220 | 1.41 | Nos.
19 | POP Punning | POP & FALSE CEILING WORKS | External plumbing works. | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing & laying CPVC pipes with screwed sockets, joints, and necessary pvc fittings such as socket, elbows, bends, tees etc., including making/ drilling holes in walls/ slabs and remaking good the damages in original conditions. The rate is inclusive of necessary scaffolding ( Make : Astral / Precision ) | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | 15mm dia | 94 | 0 | 0 | 0 | R.ft
ii | POP Punning | POP & FALSE CEILING WORKS | 20mm dia | 106 | 0 | 0 | 0 | R.ft
iii | Partition | CARPENTRY AND INTERIOR WORKS | 25mmdia | 131 | 5 | 655 | 0.29 | R.ft
iv | PAINTING WORKS | PAINTING WORKS | 40mmdia | 150 | 0 | 0 | 0 | R.ft
b | PAINTING WORKS | PAINTING WORKS | Supplying and fixing of PVC Pipe of SWR Grade of approved company including all necessary fitting fixed with GI Clamp making necessary holes in valets, refilling the same with concrete making good the damaged portions with matching plaster complete in all respects. The rate is inclusive of scaffolding. ( Make : Astral / Precision ) | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | 2" dia | 93 | 0 | 0 | 0 | R.ft
ii | POP Punning | POP & FALSE CEILING WORKS | 4" dia | 156 | 30 | 4680 | 2.05 | R.ft
iii | Partition | CARPENTRY AND INTERIOR WORKS | 6" dia | 159 | 0 | 0 | 0 | R.ft
c | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing CI pipe (heavy duty ) for soil, waste, vent, of approved company with required fittings such as junctions, bends, bowl fixed with GI clamps filling the joints of pipe in cement including making necessary holes in walls, refilling the same with concrete making good the damaged portion with matching plaster, complete with 3 coats of oil paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade. The rate is inclusive of necessary scaffolding. | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | 4 " dia | 805 | 0 | 0 | 0 | R.ft
d | Partition | CARPENTRY AND INTERIOR WORKS | Providing and laying 150mm dia salt glazed stoneware pipes in proper gradient on cement concrete bedding or bricks over compacted soil & including fittings such as bends, single or double junctions, laying, jointing in CM (1:1) including excavation and filling the trench | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | 4 " dia | 141 | 0 | 0 | 0 | R.ft
ii | POP Punning | POP & FALSE CEILING WORKS | 6" dia | 152 | 0 | 0 | 0 | R.ft
e | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing 23cm x 23cm salt glazed stone ware gutty trap in cm (1:4:8) outside the building including connecting salt glazed stone ware pipes and mount out of brick masonry finished with cement plaster from inside & out side covered with CI/RCC cover. Complete in all respect. | 2966 | 0 | 0 | 0 | Nos.
f | POP Punning | POP & FALSE CEILING WORKS | Providing & constructing brick masonry chamber of size: 2'-0" x 1'-0" & 1-0" to 1'-6" in depth including 6" thk CC (1:4:8) foundation, CC (1:2:4) channels, brick masonry and in CM (1:6) & 20mm thk. plastering from inside and out side in CM (1:3) , providing CI / RCC cover (heavy duty ) with necessary arrangement for lifting. | 6356 | 0 | 0 | 0 | Nos.
20 | POP Punning | POP & FALSE CEILING WORKS | Anti Termite Treatment | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Carrying out Eco - Friendly Pest control and ant-termite treatment by appointing specialized agency ( Agency : PCI / Hi-care)* for the premises with one year guarantee. Mode of measurement shall be on carpet area. A certificate of guarantee to be submitted by the vendor along with hand over document. ( * In case PCI / Hi-care do not have reach to particular location vendor to share credentials of pest control vendor with CPC for approvals ) | 18 | 2280 | 41040 | 18 | Sq.ft
21 | POP Punning | POP & FALSE CEILING WORKS | Miscellaneous civil work | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Chasing work in the existing brick/siporex up to 200mm wide and max to 75mm deep, for installation of A.C. copper pipes/drain pipes as required and Making finished surfaces with 1:4 cement mortar (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section), for portions of wall where chasing is done after laying drainage pipes and refrigerant pipes all complete including making good, closing and finishing of holes/openings in walls. | 72 | 0 | 0 | 0 | R.ft
b | POP Punning | POP & FALSE CEILING WORKS | Trenching work as per width and depth required. Making finished surfaces with 1:4 cement mortar (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) , portions of floor where trenching is done for laying Raceways for Electrical, Data and Voice cables all complete.(Chasing should be avoided in floors, it should be done only if no alternative is availaible). | 132 | 190 | 25080 | 11 | R.ft
c | POP Punning | POP & FALSE CEILING WORKS | Making punctures in existing brick/siporex block up to 200mm diameter, for passing A.C. copper pipes/drain pipes as required and making good the same with cement plaster/POP. | 320 | 1 | 320 | 0.14 | Nos.
d | POP Punning | POP & FALSE CEILING WORKS | Vendor should provide D.G. set during execution of site while power cut issues remote location. Opex cost, Diesel is included with hireing charges. | 5525 | 0 | 0 | 0 | Per Day
e | POP Punning | POP & FALSE CEILING WORKS | Filling charges of Diesel in installed D.G. set by Bank (Vendor should submit diesel bill during final billing) | 17161 | 0 | 0 | 0 | Lumpsum
f | POP Punning | POP & FALSE CEILING WORKS | Civil & interior vendor will be responsible for securing the premises till the site is ready for IT hand-over with proper locking mechanism or till project is handed over to Project manager. (Daily 12 hour shift ) | 19068 | 0 | 0 | 0 | Per month Basis
g | POP Punning | POP & FALSE CEILING WORKS | TOILET CUBICLES - Provide and fix Toilet cubicles bottom mounted made of high pressure compressed color boards with all necessary mount fittings for fixed panels. Panels to be 300mm above finished floor with door size of 650 x 1750mm Rate to include all necessary hardware's and fittings including door locks with vacant/occupied signage locks. mode of measurement L x H Approved brand Greenlam. Shop drawings to be approved by Architect. | 823 | 34.5 | 28393.5 | 12.45 | Sq.ft
h | POP Punning | POP & FALSE CEILING WORKS | Providing and making Core cut of in RCC slab / Beam of thickness up to 300mm, with core cutting machine inclusive of filling of core with fire retardant sealant of HILTI make as per the manufacturer's specification, cleaning etc complete. Note: The contractor should determine the location of beams/post tensioned tendons before carrying out the operation, getting prior approval from the builder/structural consultant and cutting all reinforcement by gas cutting machine or as directed etc. complete. (wherever required) | 104 | 0 | 0 | 0 | Nos.
i | POP Punning | POP & FALSE CEILING WORKS | Upto 75mm dia | 1695 | 0 | 0 | 0 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | Upto 100mm dia | 2067 | 0 | 0 | 0 | Nos.
iii | Partition | CARPENTRY AND INTERIOR WORKS | Upto 150mm dia | 2584 | 1 | 2584 | 1.13 | Nos.
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing, fixing and Removing MS H type frame scaffolding for branch interior and exterior work. Scafolding should have flat working platform. | 76 | 350 | 26600 | 11.67 | Sq.ft
j | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing a 1000 Lits over head watertank at branchs cost is including with necessary ball cock operated inlet connection and NRC valve output connection, internal connection and entire conncection should have emergency stop cock on inlet and outlet line. | 15255 | 0 | 0 | 0 | Nos.
k | Partition | CARPENTRY AND INTERIOR WORKS | Prepare and maintain document list, Technical cut sheet, All type of layout, Electrical based calculations, Invoice, Purchase order of purchased goods and Materials for enrollment of the Green building certification.Cost is included with charges towards professional video recording & photo shoot of entire facility available in the premises. | 15560 | 1 | 15560 | 6.82 | Lumpsum
l | Partition | CARPENTRY AND INTERIOR WORKS | Charges towards the preparation of multiple options of proposed or dropped location/s recommended by regional project team (Jobs can not be more than 3 ) | 10212 | 1 | 10212 | 4.48 | Job
m | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing a desktop model of CO2 Monitoring Unit having CO2 Detection Range: 400-5000PPM , Sensitivity: 1PPM , AC / DC operated. | 11441 | 3 | 34323 | 15.05 | Nos.
n | Partition | CARPENTRY AND INTERIOR WORKS | Providing and placing medium size self watering ceramic planters (12 Inch)with plant of given list of Botanical (Areca palm / Mother in law’s tongue/ Lady Palm/ Janet Craig / Dragon Tree / Warneckii or Dracanaenai / Spider Plant / Money plant) Cost including plantation , soil and fertilizers. ( Max 15 Planters to be place in branch). | 1296 | 30 | 38880 | 17.05 | Nos.
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing & fixing Vinly Graphic Film of approved make, with recommended adhesive(Low VOC/No VOC Adhesives as suggested by Bank or CPC team as exception / Refer Make and Model sheet,adhesives) of approved make & sample as per manufacturer's specifications. Rate of Wall Graphics film shall be inclusive of Image cost. | 211 | 461.59 | 97395.49 | 42.72 | Sq.ft.
II | POP Punning | POP & FALSE CEILING WORKS | POP & FALSE CEILING WORKS | 0 | 0 | 0 | 0
1 | POP Punning | POP & FALSE CEILING WORKS | POP Punning | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing and applying Plaster of Paris punning to wall of average thickness 12mm to18mm thk to existing wall surfaces to achieve smooth surface in true level and plumb complete as directed. The rate to include cost for making grooves up to 12mm thick if required in horizontal or vertical direction near doors, windows, skirting (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Gypsum Plaster) | 28 | 1047.19 | 29321.32 | 12.86 | Sq.ft
2 | POP Punning | POP & FALSE CEILING WORKS | False Ceiling | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Gypsum board Ceiling - 12.5mm thk. single layer gypsum board fixed on suspended G.I. tubular channels as per manufacturers' specifications, including jointing, finishing with gypsum compound, jointing tape and top coat. The surface shall up be duly sanded and finished. Rate shall include cost of marking as/ reflected ceiling plan and making all the necessary cutouts for lights, grills, diffusers etc. The rate shall also include providing perimeter channel for grills, lights, diffusers as called for in HVAC and Electrical Drawings. The rate shall also include providing for edge/ angle bits at all corners, necessary taping, filling with jointing compound as per manufacturers specifications. The rate shall be exclusive of trap door which shall be paid for separately. (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Gypsum Ceiling) | 76 | 528.89 | 40195.64 | 17.63 | Sq.ft
b | POP Punning | POP & FALSE CEILING WORKS | 600mm x 600mm Modular Grid Ceiling (providing and fixing modular ceiling systems (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Modular Ceiling) with mineral fibre board ceiling tiles as per following specifications, rate to include all fastening accessories with approved finishes. Fire retardant tiles of size 600mm x 600mm x 15mm thick of approved colour and type with acoustical property of 0.7 NRC. (Armstrong / USG Boral) Suspension shall be as per manufacturer specific stitched, sillhouette reveal profile grid system with 15mm wide flanges incorporating 6mm central recess colour (all black reveal). Sillhouette main runners and cross tees to have metered ends (bird's mouth or manufacturer specific) and profiled notches to provide cruciform junctions. The perimeter runners should have the shadow edge detail forming a uniform groove (minimum 6mm) between the vertical partition / panelling / wall and the modular false ceiling grid as per detail drawing. | 114 | 1917.94 | 218645.16 | 95.9 | Sq.ft
c | POP Punning | POP & FALSE CEILING WORKS | Providing rectangular Coves made up of Gypsum board (Green Pro certified Gypsum Board and make approved by Bank or CPC team as exception / Refer Make and Model sheet, gypsum board) upto a size of 450 mm height and 100 mm facia and including the cost of additional frameworks and overlap , verticals and other necessary requirement (Prior approval of Bank required) | 96 | 72 | 6912 | 3.03 | R.ft
3 | POP Punning | POP & FALSE CEILING WORKS | Trap Doors | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing trap doors for access to the areas above false ceiling. The trap door shall have an external frame made of 50mm x 50 mm in good quality seasoned wood scantling on which the shutter is hinged. Shutter shall be made of 19mm thk ply and finished with 1.0mm thick laminate externally and enamel paint (using paints with Low VOC/ No VOC approved by bank or CPC team as exception/ Refer make and model sheet, Paints - Applicable only if painted at site) internally. Concealed heavy duty hinges shall be used to mount the shutters and locking shall be provided with panel locks. The shutter shall be molded in level with the false ceiling forming a groove all around. Sufficient number of hinges and locks shall be provided to avoid sagging of the shutter. Key also shall be supplied for opening the shutter. No extra rate shall be provided for suspenders or frame works around for linking the trap door to gypsum board false ceiling. (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Gypsum Ceiling) | 398 | 0 | 0 | 0 | Sq.ft
b | POP Punning | POP & FALSE CEILING WORKS | Same as item above but trap door shutters to be of Lay - in type. | 411 | 0 | 0 | 0 | Sq.ft
c | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing modular trap doors for access to the areas above false ceiling having size 1200 mm x 600 mm ( Make Knauf ) | 6780 | 0 | 0 | 0 | Nos.
III | Partition | CARPENTRY AND INTERIOR WORKS | CARPENTRY AND INTERIOR WORKS | 0 | 0 | 0 | 0
1 | Partition | CARPENTRY AND INTERIOR WORKS | Partition | 0 | 0 | 0 | 0
a | Partition | CARPENTRY AND INTERIOR WORKS | Solid Partitions | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing of full height solid partition made with Aluminum framework of 20 gauge of size 50 mm x 50mm fixed @600mm c/c both ways and covered with 9mm thk BWR plywood (Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished with 1.0mm thk laminate of approved shade. 75 mm wide aluminium skirting is to be provided. Cost to include wooden inserts of sal-wood at the door opening for fixing of floor spring pivot etc. (The measurements will be taken from flooring to bottom of false ceiling) ( Basic cost of laminate up to Rs. 45/- Per sq.ft) | 462 | 325.36 | 150316.32 | 65.93 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Portion of the partition above the ceiling level to be made of Aluminum framework of 20 gauge of size 50 mm x 50mm. And covered from one side with 12.5 mm thick gypsum board of ( Green Pro certified Gypsum Board and make approved by Bank or CPC team as exception / Refer Make and Model sheet, gypsum board) specified Make.(The measurements will be taken from bottom of false ceiling up to slab bottom) | 131 | 0 | 0 | 0 | Sq.ft
iii | Partition | CARPENTRY AND INTERIOR WORKS | Same as item 1.a-(i) above but partition framework to be covered with one side BRW plywood (Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) of 9mm thickness finished with 1.0mm thick laminate and other side with gypsum of 12.5mm thickness finished with 3 coats of luster paint (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, paints) of approved shade. 75 mm wide aluminium skirting is to be provided. (The measurements will be taken from flooring to bottom of false ceiling) ( Basic cost of laminate up to Rs. 45/- Per sq.ft) | 380 | 0 | 0 | 0 | Sq.ft
iv | PAINTING WORKS | PAINTING WORKS | Same as item 1.a-(i) but partition framework to be covered with both side gypsum board (Green Pro certified Gypsum Board and make approved by Bank or CPC team as exception / Refer Make and Model sheet, gypsum board) of 12.5mm thickness with 3 coats of luster paint (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, paints) of approved shade | 340 | 0 | 0 | 0 | Sq.ft
v | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and fixing of full height solid partition made with Aluminum framework of 20 gauge of size 50 mm x 38mm fixed @600mm c/c both ways and covered with 12 mm thk Fire rated plywood (Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Fire rated Plywood) and finished with 1.0mm thk laminate of approved shade. 75 mm wide aluminium skirting is to be provided. Cost to include inserts of stainless steel at the door opening for fixing of floor spring pivot etc. Rate shall be inclusive of Glass Wool Rate shall include filling all cutouts using Acrylic Firestop Sealant Hilti CP 606. | 543 | 0 | 0 | 0 | Sq.ft
b | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Glazed Partitions | 0 | 0 | 0 | 0
i | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Glazing profile (size: 26mm x 32mm) single glazed fixed partition for 12 mm toughened glass Complete systems (Entrance Partition & BM Cabin) Sap Code : EAPS- 1032 - WCP With Cover - 12mm - Non safety Profile for 12mm Glass Aluminum S.S Finish 3MTR W.C.P End Cap H Profile 12mm glass to glass 180 deg Stock Length 3000mm with 3M Adhesive (approved Low VOC/No VOC Adhesives to be used by Bank or CPC team as exception / Refer Make and Model sheet, Adhesives) Finish EV 101 Glass 12 mm Tuff Clear Crystal Edge Polished with cut out and Holes Silicon Seal Clear - Dow / Wacker S.S Screw for Fixing Metal / Wooden 38mm x 6mm CSK Philip Head with Plastic Anchor Grip | 434 | 517.42 | 224560.28 | 98.49 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Providing & fixing of Semi glazed partitions solid upto 4'0" ht The solid portion of the partitions is made by using the Al. frame work of size 50mm x 50mm fixed @600mm c/c bothways covered with 9mm thick BWR plywood (Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (optional) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished with 1.0mm thick laminate of approved shade. Glazing profile (size: 26mm x 32mm) single glazed fixed partition for 12 mm toughened glass Complete systems (Entrance Partition & BM Cabin) Sap Code : EAPS- 1032 - WCP With Cover - 12mm - Non safety Profile for 12mm Glass Aluminum S.S Finish 3MTR W.C.P End Cap H Profile 12mm glass to glass 180 deg Stock Length 3000mm with 3M Adhesive (approved Low VOC/No VOC Adhesives to be used by Bank or CPC team as exception / Refer Make and Model sheet, Adhesives) Finish EV 101 Glass 12 mm Tuff Clear Crystal Edge Polished with cut out and Holes Silicon Seal Clear - Dow / Wacker S.S Screw for Fixing Metal / Wooden 38mm x 6mm CSK Philip Head with Plastic Anchor Grip | 442 | 0 | 0 | 0 | Sq.ft
c | POP Punning | POP & FALSE CEILING WORKS | Low Height Solid Partition | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Same as item 1.a-(i) but low height solid partition up to 1200 mm height. The partition framework to be covered with 12mm thick BWR plywood ( Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished with 1.0mm thick laminate. Wooden trim of size 75mm x 12mm made of Teak wood to be provided at the edge of the partition finished with approved shade of laminate and 75 mm wide aluminium skirting is to be provided. | 408 | 0 | 0 | 0 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing of 55 mm thick Low ht Modular partition up to 1200 mm height. The partition framework to be covered with 12mm thick partical board and finished with 1.0mm thick laminate. Powder coated trim of size 75mm x 12mm made of aluminium profile to be provided at the edge of the partition finished with approved shade of coating and 75 mm wide aluminium skirting is to be provided. | 434 | 0 | 0 | 0 | Sq.ft
d | POP Punning | POP & FALSE CEILING WORKS | Low Height Semi Solid Partition | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Same as item 1.c-(i) above but low height solid partition to have 12mm thick clear float glass (Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) of 300mm high fixed by way of ss brackets . The glass edges to be machine Polished and rounded at the corner. | 427 | 0 | 0 | 0 | Sq.ft
2 | POP Punning | POP & FALSE CEILING WORKS | Paneling Work | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Column / Wall Paneling | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | P/f paneling of 12mm thick BWP plywood (BWP Plywood which are "Free of Added Urea Formaldehyde" (required) make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWP Plywood) fixed on leveled wall and finished with 1.00mm thk. laminate of approved Make and shade , on all exposed surfaces on all exposed surfaces as per details, cost should also include molding made out of 25 mm x 12 mm teak wood of at the top and side edge of the paneling finished with 2 mm thk PVC edge banding tap and 75 mm wide aluminium skirting is to be provided. | 275 | 0 | 0 | 0 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | P/F paneling with Aluminium frame work of 20 gauge of size 50 mm x 38mm with 600mm c/c covered by 12mm thick BWP plywood (BWP Plywood which are "Free of Added Urea Formaldehyde" (required) make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWP Plywood) fixed on frame and finished with 1.00mm thk laminate having 25 mm x 12 mm teak wood of at the top and side edge of the paneling finished with 2 mm thk PVC edge banding tap and 75 mm wide aluminium skirting is to be provided. | 351 | 989.03 | 347149.53 | 152.26 | Sq.ft
iii | Partition | CARPENTRY AND INTERIOR WORKS | same as item 2.a-(ii) above covered with 12.5mm gypsum board (Green Pro certified Gypsum Board and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Gypsum Board) and finished with 3 coats of approved shade of luster paint. (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) | 177 | 0 | 0 | 0 | Sq.ft
iv | PAINTING WORKS | PAINTING WORKS | Same as above 2.a-(i) but with 12 mm thick bison board and finished with 1 mm thk laminate of approved shade. | 211 | 0 | 0 | 0 | Sq.ft
v | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Same as above 2.a-(ii) but with 12 mm thick bison board and finished with 1 mm thk laminate of approved shade. | 275 | 0 | 0 | 0 | Sq.ft
vi | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | same as item 2.a-(i) above but with 12mm thick bison board finished with 3 coats of approved shade of luster paint. (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) | 182 | 0 | 0 | 0 | Sq.ft
vii | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | same as item 2.a-(ii) above but with 12mm thick bison board finished with 3 coats of approved shade of luster paint.(Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) | 261 | 0 | 0 | 0 | Sq.ft
viii | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and fixing 6mm thk back painted glass (extra clear glass) (Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) as per approved shade on 6mm thk MDF (exterior grade only) backing for partitions/walls as per design and detail drawing. The glass should be glued to the MDF backing using 3M double tape. cost is including 8mm width aluminium hat section in to the grooves between ply paneling / back painted glass | 442 | 513.06 | 226772.52 | 99.46 | Sq.ft
3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Plywood Boxing | 0 | 0 | 0 | 0
a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | P/f BOXING FOR ROLLING SHUTTER up to 600mm wide x 600mm high with open able panels for accessing rolling shutter made of Salwood internal framework and 19mm thk plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) finished with 1.0mm thk laminate of approved shade on all exposed surfaces including boxing top. Openable panel for accessing the rolling shutter to be provided .Rate to include cutouts for lights, necessary hardware, etc., all complete. (surface area will be measured for the purpose of billing) | 288 | 0 | 0 | 0 | Sq.ft
b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | P/f wooden boxing for covering AC Piping, windows with Aluminium frame work of 20 gauge of size 25 mm x 25 mm with 600mm c/c internal framework and covered with by 12mm thick BWP plywood (use BWP Plywood which are "Free of Added Urea Formaldehyde" (required) make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWP Plywood) finished with 1.0mm thk laminate of approved shade on all exposed surfaces including boxing top.(surface area will be measured for the purpose of billing) | 244 | 0 | 0 | 0 | Sq.ft
c | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | P/f wooden boxing for covering AC Piping, windows with Aluminium frame work of 20 gauge of size 25 mm x 25 mm with 600mm c/c internal framework and covered with by 12mm thick BWP plywood (use BWP Plywood which are "Free of Added Urea Formaldehyde" (required) make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWP Plywood) finished with 3 coats of paints (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade on all exposed surfaces including boxing top.(surface area will be measured for the purpose of billing) | 244 | 0 | 0 | 0 | Sq.ft
4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Doors | 0 | 0 | 0 | 0
a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Main Entrance and ATM door | 0 | 0 | 0 | 0
i | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and fixing in place main entrance single leaf toughen glass ( Make : Sain Globain , Modi and Asashi )door for branch and ATM of overall size of 1050mm x 2100 mm. Rate is Tobe include cost of heavy duty floor spring of approved Make and model, ss handle of size 450 mm, mortise lock), necessary patches and all required hardware complete as directed. | 22035 | 0 | 0 | 0 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing in place main entrance single leaf toughen glass ( Make : Saint Gobin, Asashi)door for branch and ATM of overall size of 1050mm x 2400 mm. Rate is Tobe include cost of heavy duty floor spring (Make : Enox/Ozone), ss handle of size 450 mm, mortise lock), necessary patches ( Make : Enox/Ozone)and all required hardware complete as directed. | 24789 | 2 | 49578 | 21.74 | Nos.
iii | Partition | CARPENTRY AND INTERIOR WORKS | Extra for providing and fixing Enox/Ozone Make floor spring of 120 kg capacity ( only in the case of existing doors ) | 6568 | 0 | 0 | 0 | Nos.
b | Partition | CARPENTRY AND INTERIOR WORKS | Cabin and Meeting Room Doors | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Same as item no.4.a-(i) above but size of the door shall be 900mm x 2100mm | 20975 | 2 | 41950 | 18.4 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | Same as item no.4.a-(ii) above but size of the door shall be 900mm x 2400mm | 21505 | 0 | 0 | 0 | Nos.
c | POP Punning | POP & FALSE CEILING WORKS | Doors for Server Room, Store Room, Pantry and Toilet. | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing & fixing Solid Flush Door of 38mm thickness in laminate finish on both sides With Vision Panel of size 300mm x 300mm made of 6mm thk glass (Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) for Server, Teller, store and Pantry. Door to be mounted on hinges and heavy duty door closer to be provided including Handles & necessary hardware fittings ( All hardware Make : Enox/Ozone ). the sizes of the doors to be considered as under: | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | i. server room door : 975mm x 2100mm | 14259 | 0 | 0 | 0 | Nos.
b | POP Punning | POP & FALSE CEILING WORKS | i. server room door : 975mm x 2400mm | 15664 | 0 | 0 | 0 | Nos.
c | POP Punning | POP & FALSE CEILING WORKS | ii. Teller and store room door : 900mm x 2100mm | 13884 | 0 | 0 | 0 | Nos.
d | POP Punning | POP & FALSE CEILING WORKS | ii. Teller and store room door : 900mm x 2400mm | 15664 | 0 | 0 | 0 | Nos.
e | POP Punning | POP & FALSE CEILING WORKS | iii. Pantry door : 825mm x 2100mm | 13136 | 3 | 39408 | 17.28 | Nos.
f | POP Punning | POP & FALSE CEILING WORKS | iii. Pantry door : 825mm x 2400mm | 15255 | 0 | 0 | 0 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | same as item 4.c-(i) but with out vision panel for toilets and wash rooms. The size of the door to be 825mm x 2100mm | 12994 | 2 | 25988 | 11.4 | Nos.
iii | Partition | CARPENTRY AND INTERIOR WORKS | P/f. solid wicket gate door of size 675mm x 900mm made of 38mm thick flush door and mounted on heavy duty soft closing hinges and with locking arrangement for Welcome Desk. | 5169 | 0 | 0 | 0 | Nos.
d | Partition | CARPENTRY AND INTERIOR WORKS | Door Frames | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing including necessary civil work door frames made out of salwood section of size 100mm x 75mm including providing 3 nos. anchor hold fasts, applying black jaipan paint (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, paints) on the surface of the frame touching the edge of the wall. The frames to be finished with 1.0 mm thick laminate or paint (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade. | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | i. Server room frame: as per door size mentioned in item no.4.c-(a) above | 3432 | 1 | 3432 | 1.51 | Nos.
b | Partition | CARPENTRY AND INTERIOR WORKS | ii. Server room frame: as per door size mentioned in item no.4.c-(b) above | 3432 | 0 | 0 | 0 | Nos.
c | Partition | CARPENTRY AND INTERIOR WORKS | iii. Teller room door/ Store room door : as per door size mentioned in item no. 4.c-(c) above | 3432 | 0 | 0 | 0 | Nos.
d | Partition | CARPENTRY AND INTERIOR WORKS | iv. Teller room door/ Store room door : as per door size mentioned in item no. 4.c-(d) above | 3432 | 0 | 0 | 0 | Nos.
e | Partition | CARPENTRY AND INTERIOR WORKS | iv. Pantry door : as per door size mentioned in item no. 4.c-(e) above | 3432 | 0 | 0 | 0 | Nos.
f | Partition | CARPENTRY AND INTERIOR WORKS | iv. Pantry door : as per door size mentioned in item no. 4.c-(f) above | 3432 | 0 | 0 | 0 | Nos.
e | Partition | CARPENTRY AND INTERIOR WORKS | Server Room Door | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Wooden Fire Rated Door - Supply and Installation of 2hrs Fire Rated Wooden Doors 45 mm thk. (Single shutter) along with door frame with approved SS ball bearing hinges (CE Marked). Fire Rated doors to be manufactured with internal stiles and rails of tropical hardwoods, kiln seasoned and chemically treated under vacuum pressure with suitable wood preservatives having antiseptic and Fire Retardant properties in a pressure vessel. The construction is sandwich type infill material of Cera Wool Blanket and Calcium Silicate boards of required thickness for 2hour Fire Rated Door). The sandwich construction is further bonded with LEED Rated LEED Rated Ply wood on both sides which is waterproof and bonded with Phenol Formaldehyde Synthetic Resin. The doors are further given an external timber lipping of 6.5mm thickness in which intumescent strips are affixed which impart expansion properties to the door to seal them against fire / smoke escaping to the adjoining areas. Concealed door closer ITS 96 shall be used. The Fire Rated doors should achieve the criteria of STABILITY, INTEGRITY & THERMAL INSULATION PROPERTIES as per the standards laid down in BS 476”. The door frame and shutter shall be finished as per detail drgs. Skinning of the door (both side) Fire rated laminate make shall be considered. Fire and Smoke Seal Strips of size 10mm x 4mm mounted in the grooves in the shutter on all sides except bottom. Intumescent sealant is used to seal the gaps of approved make. All Test reports and warranties/guarantee to be taken from manufacturer and submitted to engineer in charge before installation. Approved Make: Kenwood / Promat Rate to be inclusive of all hardwares and vision panels in fire rated glass of size as per drgs. approx size upto 1050 mm x 2100 mm (server room) | 47602 | 1 | 47602 | 20.88 | Nos.
5 | Partition | CARPENTRY AND INTERIOR WORKS | Tables | 0 | 0 | 0 | 0
|  |  | NOTE : First drawer at each workstation must have shelves for segregating currency notes pens/staplers / stamps etc.)Drawer at each workstation to divided in 2 equal parts by a horizontal partition and the front partition among these to be divided into 3 equal partitions by vertical partitions.(As per 5S requirement) Modular furniture makes should have BIFMA / Green Guard / Green Pro Certification and approved by bank or CPC team as exception (Refer make and model sheet) | 0 | 0 | 0 | 0
a | Partition | CARPENTRY AND INTERIOR WORKS | Branch Manager's Table | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing in place, branch manager's table of size 1575mm x 675mm(worktop size)comprising of 25mm thick table top made of medium density particle board with side credenza of size 400mm deep and 900mm long having sliding shutters with locks ( Make : Ebco ) and a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high Density particle board. The table top to have post form edge. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware .( Make : Ebco) all the external surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with 0.8 mm thick laminate of approved shade. all complete as directed.( All furniture hardware should be Ebco Make ) | 28249 | 1 | 28249 | 12.39 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | same as item 5.a - i but table of size 1425 x 675mm.(worktop size). | 25340 | 0 | 0 | 0 | Nos.
b | POP Punning | POP & FALSE CEILING WORKS | P.B./RM worktables | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing in place, Personal manager's table of size 1350 x 675mm.(worktop size)comprising of 25mm thick table top made of medium density particle board with side credenza of size 400mm deep and 900mm long having sliding shutters with locks ( Make : Ebco )and a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board.. The table top to have post form edge. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware. all the external surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with 0.8 mm thick laminate of approved shade. all complete as directed.( All furniture hardware should be Ebco Make ) | 25213 | 0 | 0 | 0 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | same as item 5(a) above but size of the worktable to be 1200mm x 675mm with side credenza having two nos. top drawers and openable shutters below and without drawer pedestal. | 20128 | 0 | 0 | 0 | Nos.
iii | Partition | CARPENTRY AND INTERIOR WORKS | same as item 5(a) above but size of the worktable to be 1200mm x 675mm with drawer pedestal and without side credenza. | 20488 | 0 | 0 | 0 | Nos.
c | Partition | CARPENTRY AND INTERIOR WORKS | RM's worktables in HNW area (cockpit type) | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing cockpit type workstation of average size of 1500mm x 1500mm comprising of 25mm thick table top having post form edge. 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware. All the exposed surfaces to be finished with 1.0mm thick laminate and internal surfaces with 0.8mm thick laminate. ( All furniture hardware should be Ebco Make ) | 22458 | 0 | 0 | 0 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | Same as item 5.c-(i) above but of size 1425mm x 1425mm. | 20340 | 0 | 0 | 0 | Nos.
d | POP Punning | POP & FALSE CEILING WORKS | Running Counter, Linear Desks (WBO and back office) and Pantry Counter | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing in place 600mm deep running counter made of medium density particle board with post form edge profile for 25mm thick table top, Consisting of a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware.All the exposed surfaces to be finished with 1.0mm thick laminate.( All furniture hardware should be Ebco Make ) | 16568 | 21 | 347928 | 152.6 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | Back Office Tables -1200mm width x 600 mm x750mm deep Free Standing Table top made of 25mm thk prelaminated particle board of approved color laminate with front longer edge having post form dome type head with alumminium access flap with soft closing mechanism. Understructure shall have Square looped legs with min size of section 46mm x45mmx 1.2 mm thk made of MS Extrusion duly powder coated . It is fitted with M8x 25mm Dome shape leveller to have better look & it's size should be matching to leg pipe size. Front Apron wooden Modesty of 18mm prelaminated twin laminated shall be fixed with minfix with metal leg .The ht. of modesty is 700mm All wiring mecahnism /swith plates are to be mounted on below access flap with vertical/horizontal post to carry wires from junction post heavy duty keyboard Tray made of MS duly powder coated with wrist pad 3 Drawer wooden fixed pedestal of size 700mm ht x 380mm w x 450mm D. Pedestal should be opened with single Key & all drawers & doors shall have no handles Entire body except back is made of 18mm prelaminated board of approved color, & back is in 9mm white All Facia vetical edges shall have reverse waterfall edge in such a way for easy finger grip to user & shall have no external handle. Cost of soft Pin board cum writing board dividor inclusive with cost . | 17043 | 0 | 0 | 0 | Nos.
iii | Partition | CARPENTRY AND INTERIOR WORKS | same as item 5.d-(i) above but made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) All the External & internal surfaces to be laminated Polished. | 0 | 0 | 0 | 0 | Nos.
iv | PAINTING WORKS | PAINTING WORKS | Providing and fixing lunch counter with top made up of 19 mm ply, fascia and brackets in 12 mm thick ply and finished with 1 mm thick laminate on top, bottom and facia Complete as directed. | 1268 | 0 | 0 | 0 | R.ft
e | PAINTING WORKS | PAINTING WORKS | Welcome Desk | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Providing and fixing welcome desk consisting of two worktops (laminate and glass/granite) with a cabinet to house FRFC made of 19mm thick BWR plywood top, sides finished in 1.0mm thick laminate of approved shade. The table shall have a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board. with key boards and CPU stand complete with all hardware etc. all the exposed edges to have wooden lipping stained to match the laminate and Melaminee finished. all the internal surfaces to be hand Melamine Polished. ( All furniture hardware should be Ebco Make ) | 24336 | 0 | 0 | 0 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing double set welcome desk consisting of two worktops (laminate and Glass (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass)) with a common cabinet to house FRFC made of 19mm thick BWR plywood top, sides finished in 1.0mm thick laminate of approved shade. The table shall have a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board, with key boards and CPU stand complete with all hardware etc. all the exposed edges to have wooden lipping stained to match the laminate and Melaminee finished. all the internal surfaces to be hand Melamine Polished. ( All furniture hardware should be Ebco Make ) | 37247 | 0 | 0 | 0 | Nos.
f | POP Punning | POP & FALSE CEILING WORKS | Teller Counter | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | P/f Double level teller counter made out of 19mm thick plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished in laminate one at 750mm and other at 1200mm level. Top level counter to be finished in jet black granite with double molding. The upper most worktop to have vertical barriers in form of 8 mm thick toughen glass mounted on ss finish fabricated brackets for cash transactions. Teller to be provided with 4 nos. equal sized drawers, one key board at every 1200mm length. There should be a vertical barrier separating the adjacent counter at every 1200mm length. All the exposed surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with hand Melamine Polish. all 5 S compliances as per bank's requirements to be followed. ( All furniture hardware should be Ebco Make ) | 3813 | 0 | 0 | 0 | R.ft
g | POP Punning | POP & FALSE CEILING WORKS | Demat Counter | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Same as item 5.f-(i) above but without glass partition. | 3203 | 0 | 0 | 0 | R.ft
h | POP Punning | POP & FALSE CEILING WORKS | Meeting table | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing meeting room table made out of 12mm thick glass (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) table top of size up to 900mm dia. Glass edges to have machine cut. The base of the table to be made of Powder coated MS base finished with approved shade of PU paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) and finished . Glass to be fixed to the base with PVC vacuum holders. | 12757 | 0 | 0 | 0 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing in place conference room table for 10 persons made out of 19mm thick plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) finished with 1.0mm thick laminate externally and hand Melamine Polish internally. Provision to be 8 module POP Up box of Ebco made for wire management on the table top as per design. (All furniture hardware should be Ebco Make ) | 32035 | 0 | 0 | 0 | Nos.
iii | Partition | CARPENTRY AND INTERIOR WORKS | Same as 5.h.ii but for 8 persons | 21738 | 0 | 0 | 0 | Nos.
iv | PAINTING WORKS | PAINTING WORKS | Same as 5.h.ii but for 12 persons | 32035 | 0 | 0 | 0 | Nos.
v | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Same as 5.h.ii but for 16 persons | 43476 | 0 | 0 | 0 | Nos.
i | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Reprography Counter (Requirement to be rechecked with Project Manager at site before providing) | 0 | 0 | 0 | 0
i | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and fixing low height storage cabinet for Reprography Counter of height 600mm and depth 750mm made of 19mm plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) with drawers on top and shutters below. All the exposed surfaces to be finished with 1.0mm thick laminate and internal surfaces to be hand Melamine Polished. | 889 | 10 | 8890 | 3.9 | Sq.ft
J | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Gold loan desk / Table | 0 | 0 | 0 | 0
|  |  | Gold Loan Desk - 1985 mm width x 675 mm deep (with Flap door & Front Toughened Glass with SS Stud) Providing and fixing in place, Gold loan manager's table of 1985 mm width x 675 mm deep (worktop size)comprising of 25mm thick table top made of medium density particle board with side credenza of size 400mm deep and 900mm long having sliding shutters with locks ( Make : Ebco ) and a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board. The table top to have post form edge. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware .( Make : Ebco) all the external surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with 0.8 mm thick laminate of approved shade. all complete as directed.( All furniture hardware should be Ebco Make ) All Facia vetical edges shall have postformed reverse waterfall edge in such a way for easy finger grip to user & shall have no external handle. (Above Table 12mm toughned Glass Fix with SS Stud 40x40x450/600 mm ) SS stud can be locally fabricated( as per attached image) or equivalent of model- Kich DT32-1-G12 which will require holes in toughened glass | 26696 | 0 | 0 | 0 | Nos.
6 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Storages | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Full height storage units (use of BIFMA/Green Guard/ GPSC certified Storage Units) | 0 | 0 | 0 | 0
i | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and fixing 450mm deep full height storage unit made of 19mm thick plywood/HD particle board and finished with 1.0mm thick laminate externally and internally. Shutter made of 19mm thick plywood/ Particle board to be provided finished with 1.0mm thick laminate internally and externally. Intermediate shelves made of 19mm thick plywood (Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) to provided at every 400mm (as per size of box file/office file) finished with white 0.8 mm laminate. The exposed edges of the shelves should have post form edges All complete including necessary hardware, heavy duty hinges, handles, locks etc. ( All furniture hardware should be Ebco Make ) | 779 | 38.5 | 29991.5 | 13.15 | Sq.ft
b | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Low height storage units (BIFMA/Green Guard/ GPSC certified Storage Units) | 0 | 0 | 0 | 0
i | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and fixing 450mm deep Low height storage unit (Upto 1050 mm high) made of 19mm thick plywood/Particle board and finished with 1.0mm thick laminate externally and internally. Openable shutter made of 19mm thick plywood to be provided finished with 1.0mm thick laminate internally and externally. Intermediate shelves made of 19mm thick plywood to provided (as per size of box file/office file) finished with 1 mm laminate. The exposed edges of the shelves should have post form edges All complete including necessary hardware, heavy duty hinges, handles, locks etc. ( All furniture hardware should be Ebco Make )(use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) | 610 | 103.84 | 63342.4 | 27.78 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | same as item 6.b-(i) above but shutters of the storage to be made sliding with locking arrangement. (Specifically for BM Cabin) | 610 | 0 | 0 | 0 | Sq.ft
iii | Partition | CARPENTRY AND INTERIOR WORKS | Same as item 6.b-(i) above but overhead storage of approx. height 750mm. | 678 | 0 | 0 | 0 | Sq.ft
iv | PAINTING WORKS | PAINTING WORKS | Providing and fixing wall mounted storage rack for DVR having front side opened and all the sides closed with 19mm thick BWR plywood. All the external surfaces to be finished with 1.0mm thick laminate and internal surfaces Tobe finished with hand Melamine Polish. Aluminium ventilation grille to be provided on either sides of the storage rack. size of the rack W 600mm x H 530mm x D 400mm (Requirement to be confirmed by Bank before providing) (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood | 3856 | 0 | 0 | 0 | Nos.
v | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | A 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood/high density particle board. (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) | 2669 | 0 | 0 | 0 | Nos.
c | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Slotted Angle Racks | 0 | 0 | 0 | 0
i | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Steel Slotted Angle Racks Open Type of size 1829 H x 915 W x 260 D mm of 14 gauge thick with 6 panels of 18 gauge thick making 5 compartments with 3 sides covered by cladding sheet of 22 gauge thick with required bolts and nuts and other hardware complete as directed. | 205 | 117 | 23985 | 10.52 | Sq.ft
d | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Pigeon hole storage | 0 | 0 | 0 | 0
i | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and fixing in place pigeon hole storages made of 19mm thick BWR Plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) or HD Partical Board and finished with 1.0mm thick laminate externally. The shelves and internal verticals for the pigeon hole to be made of 12mm thick plywood and finished in hand Melamine Polish. All complete as per the 5 S requirements of the Bank. | 966 | 0 | 0 | 0 | Sq.ft
7 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Shutters | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and fixing shutters below pantry counter made of 19mm thick plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished with 1.0mm thick laminate internally and externally. The cost to include wooden frame of size 50 mm x 38mm for fixing of the shutters. All complete including necessary hardware like hinges, handles etc. aluminum perforated grilles for ventilation. | 466 | 51.52 | 24008.32 | 10.53 | Sq.ft
b | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Same as item 7(a) but shutters without ventilation grille for built in niches . | 466 | 0 | 0 | 0 | Sq.ft
c | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and fixing DB shutters/ Electrical cabinate in 19 mm thick FR Grade Plywood (use FR Plywood which are "Free of Added Urea Formaldehyde" (required) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, FR Plywood) of approved make only to be finished with 1.0mm thick laminate externally & Internally should have of aluminum perforated grille at bottom and all hardware, tower bolts, locks etc. to be included. | 457 | 31.5 | 14395.5 | 6.31 | Sq.ft
8 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Façade Treatment | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Aluminium Composite Panel | 0 | 0 | 0 | 0
i | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and fixing tricolour (Silver - Red - Grey) Aluminium Composite Panels (ACP) of A2 FR Grade exterior grade for cladding near entrance of approved make for external wall / column / canopy cladding in combination of solid / Metallic colours, including all necessary frame work and complete weather sealing. The composite panel should consist of 3mm thermoplastic core of LDPE sandwiched between 2 skins of 0.5mm thick aluminium sheet (alloy designation 310S) making a total panel thickness of 4mm. The surface will be furnished with Lumiflon based flourcarbon coating on top sides and service coating on reverse side. Coatings shall conform to specifications of specifications of ECCA / AAMA and conforming to the mechanical properties of panel as per detailed technical specifications. the system shall be fixed using GI brackets and stainless steel bolts and nuts complete with spring washers and cap nuts and all other necessary accessories. The bracket support shall be designed as per manufactures specification and shall withstand a wind pressure of 150 kg / sqm. all hardware shall corrosion resistant frame out of anodised aluminium member. | 286 | 111.8 | 31974.8 | 14.02 | Sq.ft
9 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Railing | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | SS Railing | 0 | 0 | 0 | 0
i | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and fixing SS railing of 304 quality as per design for staircase/ramps etc. | 1167 | 0 | 0 | 0 | R.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Same as item 9.a-(i) above but providing only ss pipe of dia 50 mm on one side of the wall with necessary brackets at required intervals. | 808 | 0 | 0 | 0 | R.ft
b | POP Punning | POP & FALSE CEILING WORKS | MS Railing | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing MS railing with powder coated finish of approved shade | 712 | 0 | 0 | 0 | R.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Same as item 9.b-(i) but providing only MS pipe of dia 50mm on one side of the wall with necessary brackets at required intervals. | 570 | 0 | 0 | 0 | R.ft
10 | POP Punning | POP & FALSE CEILING WORKS | Loose Furniture (use of BIFMA/Green Guard/ GPSC certified Sofa Units) | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Single Seater Sofa in composite leather as per design. ( Make: Amardeep Design or approved by CPC ) | 10627 | 0 | 0 | 0 | Nos.
b | POP Punning | POP & FALSE CEILING WORKS | Two Seater Sofa in composite leather as per design.( Make: Amardeep Design or approved by CPC ) | 17628 | 0 | 0 | 0 | Nos.
c | POP Punning | POP & FALSE CEILING WORKS | Three Seater Sofa in composite leather as per design.( Make: Amardeep Design or approved by CPC ) | 21687 | 0 | 0 | 0 | Nos.
d | POP Punning | POP & FALSE CEILING WORKS | Corner Tables of size 450 mm x450mm made of glass top (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) and Powder coated MS base finished with approved shade of paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) and finished . ( Make: Amardeep Design or approved by CPC ) | 10610 | 0 | 0 | 0 | Nos.
e | POP Punning | POP & FALSE CEILING WORKS | Centre Table of size 600mm x 1200mm made of glass top (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) and Powder coated MS base finished with approved shade of paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) and finished . ( Make: Amardeep Design or approved by CPC ) | 11017 | 0 | 0 | 0 | Nos.
11 | POP Punning | POP & FALSE CEILING WORKS | Windows | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Supplying & fixing in position Aluminium extruder sections of 16 gauge of approved Makes two track sliding windows with outer frame made from section overall size 62mm x 45mm, with shutters of sections made of 19mm x 40mm with 6mm plain sheet glass (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) of approved Make with new neoprene gasket, shutters to be provided with nylon encased S.S. rollers, necesarry locks, and handles etc. The A1 section should be, treated with powder coating of approved colour/ shade. Complete in all respect. | 300 | 133.84 | 40152 | 17.61 | Sq.ft
b | POP Punning | POP & FALSE CEILING WORKS | Same as item 11(a) above but for 3 tracks | 296 | 0 | 0 | 0 | Sq.ft
c | POP Punning | POP & FALSE CEILING WORKS | Same as item 11(a) as above but openable type with friction hinges of approved co. | 319 | 0 | 0 | 0 | Sq.ft
d | POP Punning | POP & FALSE CEILING WORKS | Louvered windows for toilet and pantry windows | 794 | 8.62 | 6852.22 | 3.01 | Sq.ft
12 | POP Punning | POP & FALSE CEILING WORKS | Miscellaneous | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Soft / Pinup Board | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing 12thk. Soft board comprising of 12mm thk. back Ply (use FR Plywood which are "Free of Added Urea Formaldehyde" (required) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, FR Plywood) fixed on wall with 12mm thk pinup board (Soft board) covered with fabric of approved shade (Basic cost Rest. 110/- per running meter.) | 177 | 72 | 12744 | 5.59 | Sq.ft
b | POP Punning | POP & FALSE CEILING WORKS | White Board | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing of magnetic white board of 3'-0" X 4'-0" size for Branch Manager & Meeting Room including accessories like markers, dusters , tray etc. | 3203 | 0 | 0 | 0 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | Similar to above but 6'-0" x4'-0" size | 6576 | 0 | 0 | 0 | Nos.
iii | Partition | CARPENTRY AND INTERIOR WORKS | Same as b (i) but toughened glass writing board of size 3' x 4' on S.S. studs | 5367 | 0 | 0 | 0 | Nos.
c | Partition | CARPENTRY AND INTERIOR WORKS | Window Blinds | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Supplying and fixing 4" wide vertical fabric blinds of approved made and colour and texture including all fittings of approved quality complete. Blinds made using 100% polyester with acrylic polymer coating. | 66 | 0 | 0 | 0 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Supplying and fixing roller fabric blinds of approved made and colour and texture including all fittings of approved quality complete. Blinds made using 100% polyester with acrylic polymer coating. | 106 | 201.92 | 21403.52 | 9.39 | Sq.ft
d | POP Punning | POP & FALSE CEILING WORKS | Frosted Film | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing of frosted film on glass as per design - Make Garware. | 67 | 0 | 0 | 0 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing of frosted film on glass as per design - Make 3M | 105 | 489.5 | 51397.5 | 22.54 | Sq.ft
iii | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing Sun control film on the main glazing - Make 3M | 50 | 0 | 0 | 0 | Sq.ft
e | Partition | CARPENTRY AND INTERIOR WORKS | Mirror for Toilets & Strong Room | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing flawless 6 mm thk. mirror of approved quality . The mirror shall be fixed on 12mm thk marine plywood (use FR Plywood which are "Free of Added Urea Formaldehyde" (required) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Plywood) backing with stainless steel mirror screws. | 226 | 12 | 2712 | 1.19 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | same as above but with pedestal unit of total 600 mm x 450 mm to be provided wherever it is not possible to fix the mirror on the strong room walls | 6419 | 0 | 0 | 0 | Nos.
f | POP Punning | POP & FALSE CEILING WORKS | Curtain with SS Rod | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing of curtain with SS rod in Strong Room ( size upto 1500 mm x 2100mm) | 1966 | 0 | 0 | 0 | Job
g | POP Punning | POP & FALSE CEILING WORKS | Aluminium Skirting | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | providing and fixing 75 mm ht approved aluminium extruded profile skirting (readymade section) made out of 18 gauge aluminium, powder coated with shade as approved by architect with a thickness of 50 microns. Skirting to include all nesessary fixing details all complete as per detail drawing. Rate to include 12mm thk marine plywood backing (use FR Plywood which are "Free of Added Urea Formaldehyde" (required) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Plywood) for solid partition/ wall. Rate to be inclusive of providing 12mm groove between the skirting and the partition skinning. | 97 | 0 | 0 | 0 | R.ft
h | POP Punning | POP & FALSE CEILING WORKS | Glass Shelves | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing 300 mm wide and 10 mm thick glass (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) shelves for momentos in Br. manager's cabin fixed with ss brackets. Size of each shelve. | 661 | 0 | 0 | 0 | Sq.ft
i | POP Punning | POP & FALSE CEILING WORKS | Wooden Shelf | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing 19mm thk ply shelf for DVR in Server Room. Size (1'-6" X 9") | 518 | 0 | 0 | 0 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | Similar to above but shelf of size(2'-0" X 9") for Strong Room below vanity mirror | 847 | 0 | 0 | 0 | Nos.
j | POP Punning | POP & FALSE CEILING WORKS | Plastic Board Signages | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing plastic board signage and numbers | 423 | 12 | 5076 | 2.23 | Nos.
k | POP Punning | POP & FALSE CEILING WORKS | Writing Ledge (Requirement to be checked with the Project Manager before provision) | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing of writing ledge as per design. | 4025 | 0 | 0 | 0 | Nos.
l | POP Punning | POP & FALSE CEILING WORKS | Notice Board | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing Notice board made up of soft board comprising of 12mm thk. back Ply (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) fixed on wall with 12 mm thk pinup board (Soft board) covered with fabric of approved shade Board to be covered with four way frame of 75 mm thik 12 mm plywood and to be finished with approved laminated shade | 220 | 0 | 0 | 0 | Sq.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing modular Notice board made up of soft board comprising of 18 Gauge thik back aluminium foil on wall with 10 mm thk pinup board (Soft board) covered with fabric of approved shade and Board to be covered with four way frame of 35 mm thik aluminium extruded profile. | 211 | 0 | 0 | 0 | Sq.ft
m | POP Punning | POP & FALSE CEILING WORKS | Pelmet (as per site conditions and window / ceiling intersection) | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing in place 150mm deep pelmet made out of 19mm thick plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished internally with enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) . The pelmet to be provided at the junction of window and false ceiling only as per site conditions. The pelmet to be concealed inside the false ceiling such as to receive the vertical blinds. | 243 | 0 | 0 | 0 | R.ft
ii | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing in place 150mm deep pelmet made out of 12.5 mm thick gypsum board (use Green Pro certified Gypsum Board and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Gypsum Board) and finished with luster paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) . The pelmet to be provided at the junction of window and false ceiling only as per site conditions. The pelmet to be concealed inside the false ceiling such as to receive the vertical blinds. | 262 | 0 | 0 | 0 | R.ft
n | POP Punning | POP & FALSE CEILING WORKS | Key Hanging Box | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing in place key hanging box of size 600mm x 675mm made out of 19mm thick plywood and finished with 1.0 mm thick laminate of approved shade. The shutter of the key box to be made of 19mm thick plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) with 60mm wide frame on all sides with 6mm thick glass embedded in it. The key box to be provided with key hooks. | 3326 | 1 | 3326 | 1.46 | Nos.
o | POP Punning | POP & FALSE CEILING WORKS | Aluminium Folding Step Ladder (A` type Self-supporting plate form ladder | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Ladder of height 8 feet (C section and steps on both sides) | 6186 | 1 | 6186 | 2.71 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | Ladder of height 10 feet (C section and steps on both sides) | 7909 | 0 | 0 | 0 | Nos.
iii | Partition | CARPENTRY AND INTERIOR WORKS | Ladder of height 12 feet (C section and steps on both sides) | 9513 | 0 | 0 | 0 | Nos.
p | Partition | CARPENTRY AND INTERIOR WORKS | Miscellaneous work | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Fixing of internal marketing poster frames supplied by the bank. | 95 | 0 | 0 | 0 | Nos.
ii | POP Punning | POP & FALSE CEILING WORKS | Fixing of modular ATM drop box cum writing ledge supplied by the bank | 137 | 0 | 0 | 0 | Nos.
iii | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing weather shed made of GI sheet of 16/18 gauge. All complete with waterproofing, vata, drip mould etc. | 286 | 0 | 0 | 0 | Sq.ft
iv | PAINTING WORKS | PAINTING WORKS | Providing and fixing folding/retractable mechanical operation canopy awning made of high quality tensile plastic sheet. Cost is inclusive of all necessary accessaries, gears etc. | 548 | 0 | 0 | 0 | Sq.ft
v | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Supply of carpenter on monthly basis (8 hour shift per day) after handing over of the site for branch pre-launch activity. | 15466 | 1 | 15466 | 6.78 | per month basis
vi | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Removing and re-applying laminate on existing furniture. | 129 | 0 | 0 | 0 | Sq.ft
vii | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and fixing in place, media & offer zone made out of 12mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) with 230 mm deep niche of size 710mm X 750 mm 2 nos for net banking and phone banking and 1 no of size 710mm X 1050mm for offer zone finished with 1.0mm thick laminate of approved shade as per design. All niches to have a 18mm thick granite top of size 710mm X 350 mm with grommet hole of 75 mm dia with wire manager complete with round Melamine Polish on all exposed edges. Center niche to have cabinet with hinged shutter for housing CPU unit as per detail drawing. All the external surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with 0.8 mm thick laminate of approved shade. All complete including necessary hardware. | 805 | 0 | 0 | 0 | Sq.ft
viii | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and fixing 12 mm Chair / Corner Guard of approved aluminium extruded profile (readymade section) as approved by architect. Rate to include all nesessary fixing details all complete as per detail drawing. | 101 | 617.18 | 62335.18 | 27.34 | R.ft
ix | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing Heavy Traffic Entrance Mattin 3M Nomad Terra 8150 Floor Mat size upto 8'0" x 3'0" | 3356 | 2 | 6712 | 2.94 | Nos.
x | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and placing foot operated Dry and Wet Dust made up of 100 % food grade and BPA Free plastice having 19 Liters capacity . Bin should have individual bin slot with removable buckets and covered with outer frame. ( Make : Nayasa or RAGA) (For Desk) | 1695 | 18 | 30510 | 13.38 | Nos.
xi | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and placing foot operated Dry and Wet Dust made up of 100 % food grade and BPA Free plastice having 33 Liters capacity . Bin should have individual bin slot with removable buckets and covered with outer frame. ( Make : Nayasa or RAGA) ( For Pantry ) | 1678 | 3 | 5034 | 2.21 | Nos.
xii | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and fixing folding/retractable mechanical operation canopy awning made of high quality tensile plastic sheet. Cost is inclusive of all necessary accessaries, gears etc. | 529 | 0 | 0 | 0 | Sq.ft
xii | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and fixing 12 mm froster glass partion to be placed in between interconnected workstation. Rate to include all nesessary fixing details all complete as per detail drawing. | 381 | 0 | 0 | 0 | Sq.ft
xiii | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and placing 6 mm transparant acrylic glass for table top to avoid lnk / stamp marking on white laminated tops. (Basis rate of acrylic is 300 Rs./ Sq.ft) | 343 | 0 | 0 | 0 | Sq.ft
q | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Fire Exit Door | 0 | 0 | 0 | 0
a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Supply & Fixing single leaf Metal Fire Doors of Size : 1200mm X 2400mm with a vision panel 310mm X 310mm & without panic bar of 60 minutes Rated Insulated Fire Door Tested in accordance to BS: 476 Part – 20 and IS: 3809: 1979, CNP – 2150 Door Frame: Providing of Door Frame of section 120mm X 70mm with fire intumescent seal strip of size 10mm X 4mm for fire and smoke sealing mounted in the grooves of the frame and coated with fire retardant intumescent Primer coating. Hinges: Providing of ball bearing hinges with S.S. Screws - 4 nos per shutter. Handle: Fire rated handles in SS finish to be included in cost. | 33391 | 0 | 0 | 0 | Nos.
b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Same as 12_p_xiii_a but included Supply and installation of Panic Bar with Hooter | 36442 | 0 | 0 | 0 | Nos.
IV | PAINTING WORKS | PAINTING WORKS | PAINTING WORKS | 0 | 0 | 0 | 0
a | PAINTING WORKS | PAINTING WORKS | Paint on Walls | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Providing and applying desired paint luster finish to walls, of approved shade.. The surface of wall to be painted shall be prepared and applied with two coats of primer, two coats of putty and touch up putty if required to achieve smooth finish. The surface shall be painted with three coats of luster paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of Dulux - akzonobel / Asian. | 25 | 1047.19 | 26179.75 | 11.48 | Sq.ft
b | PAINTING WORKS | PAINTING WORKS | Acrylic Emulsion Paint on Ceiling | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Same as item (a) but applying acrylic emulsion paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) on the ceiling | 20 | 478.58 | 9571.6 | 4.2 | Sq.ft
c | PAINTING WORKS | PAINTING WORKS | Synthetic Enamel Paint (over existing MS grilles, gates, shutters etc.) | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Same as item (a) above but applying synthetic enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) to MS grilles, collapsible gates, rolling shutters etc. | 21 | 858.45 | 18027.45 | 7.91 | Sq.ft
d | PAINTING WORKS | PAINTING WORKS | Apex Paint | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | The surface of wall or ceiling to be painted shall be prepared as per the manufacturers specification. Cracks if any visible on the surface to be treated by opening up the cracks, filling the same using polymer based waterproofing compound. The surface shall be applied with a priming coat of white cement or approved primer. The primed surface shall be painted with the desired paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) with two or more coats as per specifications of the manufacturer. | 16 | 1592.7 | 25483.2 | 11.18 | Sq.ft
e | PAINTING WORKS | PAINTING WORKS | Texture Paint | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Textured superfine paint shall be applied after preparing the surface to get the antique finish. The paint shall be applied using texture roller to give a uniform roller texture finish with two coats different colours of acrylic emulsion paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) . The texture paint used shall be of spectrum make. | 63 | 0 | 0 | 0 | Sq.ft
f | PAINTING WORKS | PAINTING WORKS | Duco Paint ( over existing Locker room door only ) | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Same as item (a) above but applying duco paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) to existing locker room only etc. | 102 | 0 | 0 | 0 | Sq.ft
g | PAINTING WORKS | PAINTING WORKS | Fire rated paint on wall | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Providing and applying three coats of fire rated paint of approved make, with low voc - leed certified, wherever required to internal walls/ceiling surfaces after thoroughly sand papering surfaces to remove dust, dirt etc. and repairing dents, cracks, holes with pop to achieve level surface and finishing with two coats of primer, putty and three coats of paint including cost of material, labour etc. all complete as directed by the engineer in charge. Rate to include application at all heights and levels, surfaces and textures. approval required of engineer in charge after each coat. | 61 | 0 | 0 | 0 | Sq.ft
V | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | 0 | 0 | 0 | 0
1 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | MS Window grill | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and fixing of MS Box type window grille made out of 10mm X 10 mm MS square section with the depth fof 300 mm in standard pattern as per design. The grille to be finished with red oxide and 2 coats of enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade (Black) | 144 | 0 | 0 | 0 | Sq.ft
2 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | M.S. Fabrication work. | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing, Fixing and fabrication of MS structure for staircase, under/overdeck strengthing of slab, columns, and MS Brackets. Cost includes cost of all types of MS members requires to build structure, Additional supports, fabrication, bolting, grouting and other neccesary structure elements. MS structure should treated with anti corrotion treament before final finishing. Cost is inclusive of anti corrontion and 2 coats of enamal paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) , Structure certificate etc. ( This item is applicable for MS Brackets of signages, MS Staircase, MS Strengthing work) | 139 | 0 | 0 | 0 | KG.
3 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Rolling Shutter / Collapsible Gate | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | P/f. ROLLING SHUTTER in 18 gauge GI 2" wide flat interlocking slats, with bottom lock rail, necessary handles and locking arrangement, guides on sides including providing vision panel of size 450mm x length at 1500mm from the floor finish level. Shutters to be coated with 2 coats of anti-rust paint and 3 coats of 1st quality enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) in Blue colour as per HDFC logo. Rate to include top cover box . | 247 | 0 | 0 | 0 | Sq.ft
b | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Add extra for providing mechanical gear for rolling shutter wherever required as per site condition. | 7517 | 0 | 0 | 0 | Job
c | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | All type of modification at Existing Rolling Shutter for introducing grill at Eye Level / making two or more other parts from single Shutter. | 129 | 0 | 0 | 0 | Sq.ft
d | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | servicing/greasing of existing rolling shutters to make it workable. | 7627 | 0 | 0 | 0 | Job
4 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Collapsible Gate | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and erecting in position MS Collapsible grill gate with heavy duty standard sections, channel, flats, top and bottom guides, pivots, rollers, stoppers, handles with proper locking arrangement & necessary accessories. The gate shall be finished with 1 coat of red oxide and two coats of enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade. | 239 | 0 | 0 | 0 | Sq.ft
5 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Collapsible MS Shutter | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Similar to above 4(a) but for Collapsible MS Shutter | 466 | 0 | 0 | 0 | Sq.ft
6 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | VSAT Monkey cage / MS enclosure | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Provide and installation of Mild steel Vsat monkey cage of size 8 ft x 8 ft x 8 ft and fixed at bottom with MS angle frame of size 40/40/5 and also having intermediate supports MS flats of size 25/25/5 and frame covered with MS mesh size of 10 Gauge 4'' x 4'' the cage having access gate Size 6 ft x 3 ft strength by angle with proper locking arrangement, Cage shall be finished with 1 coat of anti-rusting paint and two coats of enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade. | 245 | 0 | 0 | 0 | Sq.ft
VI | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 : POWER DISTRIBUTION PANEL | 0 | 0 | 0 | 0
|  |  | Supply, Installation, Testing & commissioning of the following panels/DBs fabricated with 16 gauge CRCA steel & 14 gauge CRCA sheet for the frame sheet painted in 7 tank process with 2 coats of red oxide & 2 coats of Smokey grey colour similar to RAL7032 Siemens grey colour. Interconnecting wires of panel should be Cu flexible / PVC wires as per following details : - PT control circuit for voltmeter - 1.5mm2, CT control circuit for ammeter - 2.5mm2, 20A circuit - 4mm2, 30A circuit - 6mm2, 40A circuit - 10mm2, 50/60A circuit - 16mm2, | 0 | 0 | 0 | 0
1.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | TYPE I PANEL - Main LT Panel (For upto 1000 sq. ft) | 83902 | 0 | 0 | 0 | Nos.
|  |  | This Panel includes MCB for Power and AC distributions hence there is no separate LDB, PDB and ACDB required. | 0 | 0 | 0 | 0
|  |  | Metering:- | 0 | 0 | 0 | 0
|  |  | 2 nos of Separate KWH sub-meter to be installed, 1 no. for critical load and other for remaining load. It should be complient with the RS485 port. | 0 | 0 | 0 | 0
|  |  | Digital VAF meter to show voltage, current and frequency parameters of the entire load | 0 | 0 | 0 | 0
|  |  | Phase Indication Lamps - 3 Nos. | 0 | 0 | 0 | 0
|  |  | I/c- 63A.25KA 4P TPN MCCB:- 1 no. (Changeover can be consider seperately as per line item in BoQ below) | 0 | 0 | 0 | 0
|  |  | O/g:- 40 A, TPN MCB:- 4 nos. | 0 | 0 | 0 | 0
|  |  | 32/40 A,DP MCB:- 2 Nos. | 0 | 0 | 0 | 0
|  |  | 40 A,100mA, DP ELCB:-1 nos | 0 | 0 | 0 | 0
|  |  | 10,16,20 A,SP MCB:-6 nos | 0 | 0 | 0 | 0
|  |  | 25 A,30mA, DP ELCB:-2 nos | 0 | 0 | 0 | 0
|  |  | 40 A,DP ISOLATOR:-2 NOS | 0 | 0 | 0 | 0
1.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | TYPE I PANEL - Main LT Panel (For 1000-1500 sq. ft) | 127675 | 0 | 0 | 0 | Nos.
|  |  | This panel includes MCB's for AC hence separate ACBD is not required | 0 | 0 | 0 | 0
|  |  | Metering:- | 0 | 0 | 0 | 0
|  |  | 2 nos of Separate KWH sub-meter to be installed, 1 no. for critical load and other for remaining load. It should be complient with the RS485 port. | 0 | 0 | 0 | 0
|  |  | Digital VAF meter to show voltage, current and frequency parameters | 0 | 0 | 0 | 0
|  |  | Phase Indication Lamps - 3 Nos. | 0 | 0 | 0 | 0
|  |  | Incomer 1 - 100 A. 25KA 4P MCCB:- 1 nos. (Changeover can be consider seperately as per line item in BoQ below) | 0 | 0 | 0 | 0
|  |  | 100A TP Power Contactor with 2NO and 2NC contacts | 0 | 0 | 0 | 0
|  |  | Normal Bus (during bank hours) | 0 | 0 | 0 | 0
|  |  | O/g:- 63 A, TPN MCB:- 3 nos. | 0 | 0 | 0 | 0
|  |  | 32/40 A,DP MCB:- 4Nos. | 0 | 0 | 0 | 0
|  |  | 32 A,TPN MCB:-1 nos | 0 | 0 | 0 | 0
|  |  | Critical Bus (24/7) | 0 | 0 | 0 | 0
|  |  | Incomer 1 - 63A TP MCCB | 0 | 0 | 0 | 0
|  |  | O/g:- 40 A, TPN MCB:- 1 nos. | 0 | 0 | 0 | 0
|  |  | 32A DP MCB - 4 nos. | 0 | 0 | 0 | 0
1.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | TYPE I PANEL - Main LT Panel (For 1500-2500 sq. ft) | 155313 | 1 | 155313 | 68.12 | Nos.
|  |  | This panel includes MCB's for AC hence separate ACBD is not required | 0 | 0 | 0 | 0
|  |  | Metering:- | 0 | 0 | 0 | 0
|  |  | 2 nos of Separate KWH sub-meter to be installed, 1 no. for critical load and other for remaining load. It should be complient with the RS485 port. | 0 | 0 | 0 | 0
|  |  | Digital VAF meter to show voltage, current and frequency parameters | 0 | 0 | 0 | 0
|  |  | Phase Indication Lamps - 3 Nos. | 0 | 0 | 0 | 0
|  |  | Incomer 1 - 125 A. 25KA 4P MCCB:- 1 nos. (Changeover can be consider seperately as per line item in BoQ below) | 0 | 0 | 0 | 0
|  |  | 125A TP Power Contactor with 2NO and 2NC contacts | 0 | 0 | 0 | 0
|  |  | Normal Bus (during bank hours) | 0 | 0 | 0 | 0
|  |  | O/g:- 63 A, TPN MCB:- 7 nos. | 0 | 0 | 0 | 0
|  |  | 32/40 A,DP MCB:- 2 Nos. | 0 | 0 | 0 | 0 | Not on site
|  |  | 80/100 A TPN MCCB:- 1 nos. | 0 | 0 | 0 | 0 | Not on site
|  |  | 32 A,TPN MCB:-1 nos | 0 | 0 | 0 | 0 | Not on site
|  |  | Critical Bus (24/7) | 0 | 0 | 0 | 0
|  |  | Incomer 1 - 80A TP MCCB | 0 | 0 | 0 | 0
|  |  | O/g:- 63 A, TPN MCB:- 1 nos. | 0 | 0 | 0 | 0 | Not on site
|  |  | 40A TPN MCB - 1 no | 0 | 0 | 0 | 0 | Not on site
|  |  | 32A DP MCB - 3 nos. | 0 | 0 | 0 | 0 | Not on site
1.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | TYPE II PANEL - Main LT Panel (For 2500-4500 sq. ft) | 161759 | 0 | 0 | 0 | Nos.
|  |  | This panel includes MCB's for AC hence separate ACBD is not required | 0 | 0 | 0 | 0
|  |  | Metering:- | 0 | 0 | 0 | 0
|  |  | 2 nos of Separate KWH sub-meter to be installed, 1 no. for critical load and other for remaining load. It should be complient with the RS485 port. | 0 | 0 | 0 | 0
|  |  | Digital VAF meter to show voltage, current and frequency parameters | 0 | 0 | 0 | 0
|  |  | Phase Indication Lamps - 3 Nos. | 0 | 0 | 0 | 0
|  |  | Incomer 1 - 160 A. 25KA 4P MCCB:- 1 nos. (Changeover can be consider seperately as per line item in BoQ below) | 0 | 0 | 0 | 0
|  |  | 160A TP Power Contactor with 2NO and 2NC contacts | 0 | 0 | 0 | 0
|  |  | Normal Bus (during bank hours) | 0 | 0 | 0 | 0
|  |  | O/g:- 63 A, TPN MCB:- 7 nos. | 0 | 0 | 0 | 0
|  |  | 32/40 A,DP MCB:- 3 Nos. | 0 | 0 | 0 | 0
|  |  | 80/100 A TPN MCCB:- 1 nos. | 0 | 0 | 0 | 0
|  |  | 32 A,TPN MCB:-1 nos | 0 | 0 | 0 | 0
|  |  | Critical Bus (24/7) | 0 | 0 | 0 | 0
|  |  | Incomer 1 - 80A TP MCCB | 0 | 0 | 0 | 0
|  |  | O/g:- 63 A, TPN MCB:- 1 nos. | 0 | 0 | 0 | 0
|  |  | 40A TPN MCB - 1 no | 0 | 0 | 0 | 0
|  |  | 32A DP MCB - 3 nos. | 0 | 0 | 0 | 0
1.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Supply & Installation of Master Switch with Key comprising of Start and Stop Push Button with key control for Start and Stop complete in powder coated MS box near the entrance of the bank. By Switching off this master switch the entire electrical equipment (Except Critical Bus) in the branch will get switched off. This switch can be operated while closing the branch. We have excluded following load from Master switch : entire UPS Load, Signage, Server room and ATM room AC's, CCTV, emergency lights and any other critical loads if any as per the seperate critical bus mentioned in panels specification as above. | 28612 | 2 | 57224 | 25.1 | Nos.
1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Supply, installation, testing and commissioning of the following rating of MCCBs in Sheet Steel enclosure duly housed in CRCA Sheet Enclosure , front operated Powder coated. | 0 | 0 | 0 | 0
1.2.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 63 Amps TP&N (16 Ka) MCCB- 1. No. | 9175 | 0 | 0 | 0 | Nos.
1.2.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 80 Amps TP&N (16 Ka) MCCB- 1. No. | 10137 | 0 | 0 | 0 | Nos.
1.2.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 100 Amps TP&N (16 Ka) MCCB- 1. No. | 11624 | 0 | 0 | 0 | Nos.
1.2.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 125 Amps TP&N (25 Ka) MCCB- 1. No. | 12602 | 0 | 0 | 0 | Nos.
1.2.5 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 160 Amps TP&N (25 Ka) MCCB- 1. No. | 15784 | 0 | 0 | 0 | Nos.
1.2.6 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 63 Amps FP MCB 10 ka in Powder Coated Steel Sheet Enclosure- 1 no. | 3457 | 0 | 0 | 0 | Nos.
1.2.7 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 80 Amps FP MCB 10 ka in Powder Coated Steel Sheet Enclosure- 1 no. | 4237 | 0 | 0 | 0 | Nos.
|  |  | PART ‘1’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 212537 | 93.22
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 : CAPACITOR PANEL | 0 | 0 | 0 | 0
2.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | APFCR PANEL - 10 kVAR | 35086 | 0 | 0 | 0 | Nos.
|  |  | This Panel is for area 1000 till 1500 sq. ft. | 0 | 0 | 0 | 0
|  |  | Incomer section | 0 | 0 | 0 | 0
|  |  | 63A TP MCCB 25kA, O/C+S/C with rotary handle - 1no | 0 | 0 | 0 | 0
|  |  | 0-500V, Voltmeter with selector switch and 3 nos. 2A MCBs - 1set | 0 | 0 | 0 | 0
|  |  | R Y B Phase Indicating lamps - 3 nos | 0 | 0 | 0 | 0
|  |  | APFC RELAY - 4 STEP - 1no | 0 | 0 | 0 | 0
|  |  | Control wiring with Fuses - 1 set | 0 | 0 | 0 | 0
|  |  | Outgoing Section | 0 | 0 | 0 | 0
|  |  | 2 nos 5kVAR Capacitor banks comprising of the following items: | 0 | 0 | 0 | 0
|  |  | 20A TP MCB "D" Curve - 2 nos | 0 | 0 | 0 | 0
|  |  | 5kVAR Capacitor Duty Contactor with damping resistor - 2nos. | 0 | 0 | 0 | 0
|  |  | ON/OFF Push Button with indicating lamps - 6 nos | 0 | 0 | 0 | 0
|  |  | 5kVAR MPP type 415V capacitor - 2sets | 0 | 0 | 0 | 0
2.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | APFCR PANEL - 15 kVAR | 55333 | 0 | 0 | 0 | Nos.
|  |  | This Panel is for area 1500 till 2500 sq. ft. | 0 | 0 | 0 | 0
|  |  | Incomer section | 0 | 0 | 0 | 0
|  |  | 63A TP MCCB 25kA, O/C+S/C with rotary handle - 1no | 0 | 0 | 0 | 0
|  |  | 0-500V, Voltmeter with selector switch and 3 nos. 2A MCBs - 1set | 0 | 0 | 0 | 0
|  |  | R Y B Phase Indicating lamps - 3 nos | 0 | 0 | 0 | 0
|  |  | APFC RELAY - 4 STEP - 1no | 0 | 0 | 0 | 0
|  |  | Control wiring with Fuses - 1 set | 0 | 0 | 0 | 0
|  |  | Outgoing Section | 0 | 0 | 0 | 0
|  |  | 3 nos 5kVAR Capacitor banks comprising of the following items: | 0 | 0 | 0 | 0
|  |  | 20A TP MCB "D" Curve - 3 nos | 0 | 0 | 0 | 0
|  |  | 5kVAR Capacitor Duty Contactor with damping resistor - 3 nos. | 0 | 0 | 0 | 0
|  |  | ON/OFF Push Button with indicating lamps - 6 nos | 0 | 0 | 0 | 0
|  |  | 5kVAR MPP type 415V capacitor - 3sets | 0 | 0 | 0 | 0
2.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | APFCR PANEL - 30 kVAR | 90152 | 0 | 0 | 0 | Nos.
|  |  | This Panel is for area 2500 till 4500 sq. ft. | 0 | 0 | 0 | 0
|  |  | Incomer section | 0 | 0 | 0 | 0
|  |  | 100A TP MCCB 25kA, O/C+S/C with rotary handle - 1no | 0 | 0 | 0 | 0
|  |  | 0-500V, Voltmeter with selector switch and 3 nos. 2A MCBs - 1set | 0 | 0 | 0 | 0
|  |  | R Y B Phase Indicating lamps - 3 nos | 0 | 0 | 0 | 0
|  |  | APFC RELAY - 4 STEP - 1no | 0 | 0 | 0 | 0
|  |  | Control wiring with Fuses - 1 set | 0 | 0 | 0 | 0
|  |  | Outgoing Section | 0 | 0 | 0 | 0
|  |  | 2 nos 5kVAR Capacitor banks comprising of the following items: | 0 | 0 | 0 | 0
|  |  | 20A TP MCB "D" Curve - 2 nos | 0 | 0 | 0 | 0
|  |  | 5kVAR Capacitor Duty Contactor with damping resistor - 2 nos. | 0 | 0 | 0 | 0
|  |  | ON/OFF Push Button with indicating lamps - 4 nos | 0 | 0 | 0 | 0
|  |  | 5kVAR MPP type 415V capacitor - 2 sets | 0 | 0 | 0 | 0
|  |  | 2 nos 10kVAR Capacitor banks comprising of the following items: | 0 | 0 | 0 | 0
|  |  | 32A TP MCB "D" Curve - 2 nos | 0 | 0 | 0 | 0
|  |  | 10kVAR Capacitor Duty Contactor with damping resistor - 2 nos. | 0 | 0 | 0 | 0
|  |  | ON/OFF Push Button with indicating lamps - 4 nos | 0 | 0 | 0 | 0
|  |  | 10kVAR MPP type 415V capacitor - 2 sets | 0 | 0 | 0 | 0
|  |  | PART ‘2’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 : PHASE CORRECTION CIRCUIT | 0 | 0 | 0 | 0
|  |  | PHASE CORRECTION DB SHOULD BE INSTALLED BEFORE STABILISER AND AFTER ELECTRICITY METER | 0 | 0 | 0 | 0
|  |  | TRAINING SHOULD BE PROVIDED TO BRANCH TEAM AND FA'S | 0 | 0 | 0 | 0
3.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | MANUAL PHASE CORRECTION CIRCUIT | 0 | 0 | 0 | 0
|  |  | Providing Phase Correction Distribution Boards (Double Door) suitable for 415V, 50 Hz system. Dust and vermin proof having floor / wall mounting cubicle pattern with removable gland plates, with 1 set of 100 amps Copper Bus Bar, Earth and Neutral Link etc as required. | 0 | 0 | 0 | 0
3.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 20-30KVA Phase correction DB (For upto 1000 sq. ft) | 22119 | 0 | 0 | 0 | Nos.
|  |  | 63A 4P Onload Changeover | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 63 A - 1 no. | 0 | 0 | 0 | 0
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
3.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 30-40 KVA Phase correction DB (For 1000-1500 sq. ft) | 0 | 0 | 0 | 0
|  |  | 100A 4P Onload Changeover | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 100 A - 1 no. | 31188 | 0 | 0 | 0 | Nos.
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
3.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 40-50 KVA Phase correction DB (For 1500-2500 sq. ft) | 36612 | 0 | 0 | 0 | Nos.
|  |  | 125A 4P Onload Changeover | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 63 A - 1 no. | 0 | 0 | 0 | 0
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
3.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 50-60 KVA Phase correction DB (For 2500-4500 sq. ft) | 41951 | 0 | 0 | 0 | Nos.
|  |  | 160A 4P Onload Changeover | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 100 A - 1 no. | 0 | 0 | 0 | 0
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
3.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | AUTO PHASE CORRECTION CIRCUIT (with Auto-Manual provision) - CONTACTOR LOGIC | 0 | 0 | 0 | 0
|  |  | Providing Phase Correction Distribution Boards (Double Door) suitable for 415V, 50 Hz system. Dust and vermin proof having floor / wall mounting cubicle pattern with removable gland plates, with 1 set of 100 amps Copper Bus Bar, Earth and Neutral Link etc as required. | 0 | 0 | 0 | 0
3.2.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 20 KVA Phase correction DB | 23263 | 0 | 0 | 0 | Nos.
|  |  | TPN MCCB - 63 A - 1 no. | 0 | 0 | 0 | 0
|  |  | TP Contactor - 63 A - 2 Nos. | 0 | 0 | 0 | 0
|  |  | Auto Manual Selector switch - 10 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Stop-Start P.B (Red, Green) - 10A - 4 nos. | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 63 A - 1 no. | 0 | 0 | 0 | 0
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | On-delay timer - 0-30 Sec - 1 no. | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
3.2.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 30 KVA Phase correction DB | 30510 | 0 | 0 | 0 | Nos.
|  |  | TPN MCCB - 100 A - 1 no. | 0 | 0 | 0 | 0
|  |  | TP Contactor - 100 A - 2 Nos. | 0 | 0 | 0 | 0
|  |  | Auto Manual Selector switch - 10 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Stop-Start P.B (Red, Green) - 10A - 4 nos. | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 100 A - 1 no. | 0 | 0 | 0 | 0
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | On-delay timer - 0-30 Sec - 1 no. | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
3.2.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 40-50 KVA Phase correction DB (For 1500-2500 sq. ft) | 38137 | 0 | 0 | 0 | Nos.
|  |  | TPN MCCB - 125 A - 1 no. | 0 | 0 | 0 | 0
|  |  | TP Contactor - 125 A - 2 Nos. | 0 | 0 | 0 | 0
|  |  | Auto Manual Selector switch - 10 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Stop-Start P.B (Red, Green) - 10A - 4 nos. | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 125 A - 1 no. | 0 | 0 | 0 | 0
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | On-delay timer - 0-30 Sec - 1 no. | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
3.2.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 50-60 KVA Phase correction DB (For 2500-4500 sq. ft) | 44620 | 0 | 0 | 0 | Nos.
|  |  | TPN MCCB - 160 A - 1 no. | 0 | 0 | 0 | 0
|  |  | TP Contactor - 160 A - 2 Nos. | 0 | 0 | 0 | 0
|  |  | Auto Manual Selector switch - 10 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Stop-Start P.B (Red, Green) - 10A - 4 nos. | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 160A - 1 no. | 0 | 0 | 0 | 0
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | On-delay timer - 0-30 Sec - 1 no. | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
3.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | AUTO PHASE CORRECTION CIRCUIT (with Auto-Manual provision) - ATS LOGIC | 0 | 0 | 0 | 0
|  |  | Providing Phase Correction Distribution Boards (Double Door) suitable for 415V, 50 Hz system. Dust and vermin proof having floor / wall mounting cubicle pattern with removable gland plates, with 1 set of 100 amps Copper Bus Bar, Earth and Neutral Link etc as required. | 0 | 0 | 0 | 0
3.3.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 20 KVA Phase correction DB | 32035 | 0 | 0 | 0 | Nos.
|  |  | TPN MCCB - 63 A - 1 no. | 0 | 0 | 0 | 0
|  |  | FP ATS (Auto C/O) - 63 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Auto Manual Selector switch - 10 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Stop-Start P.B (Red, Green) - 10A - 4 nos. | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 63 A - 1 no. | 0 | 0 | 0 | 0
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | On-delay timer - 0-30 Sec - 1 no. | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
3.3.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 30 KVA Phase correction DB | 35467 | 0 | 0 | 0 | Nos.
|  |  | TPN MCCB - 100 A - 1 no. | 0 | 0 | 0 | 0
|  |  | FP ATS (Auto C/O) - 100 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Auto Manual Selector switch - 10 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Stop-Start P.B (Red, Green) - 10A - 4 nos. | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 100 A - 1 no. | 0 | 0 | 0 | 0
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | On-delay timer - 0-30 Sec - 1 no. | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
3.3.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 40-50 KVA Phase correction DB (For 1500-2500 sq. ft) | 42714 | 0 | 0 | 0 | Nos.
|  |  | TPN MCCB - 125 A - 1 no. | 0 | 0 | 0 | 0
|  |  | FP ATS (Auto C/O) - 125 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Auto Manual Selector switch - 10 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Stop-Start P.B (Red, Green) - 10A - 4 nos. | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 125 A - 1 no. | 0 | 0 | 0 | 0
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | On-delay timer - 0-30 Sec - 1 no. | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
3.3.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 50-60 KVA Phase correction DB (For 2500-4500 sq. ft) | 49578 | 0 | 0 | 0 | Nos.
|  |  | TPN MCCB - 160 A - 1 no. | 0 | 0 | 0 | 0
|  |  | FP ATS (Auto C/O) - 160 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Auto Manual Selector switch - 10 A - 1 No. | 0 | 0 | 0 | 0
|  |  | Stop-Start P.B (Red, Green) - 10A - 4 nos. | 0 | 0 | 0 | 0
|  |  | Phase Sequence Relay (2 C/O) - 160 A - 1 no. | 0 | 0 | 0 | 0
|  |  | Phase sequence indicating lamp (Red) - 2 W - 2 Nos. | 0 | 0 | 0 | 0
|  |  | control Mcb - 6 A - 3 nos | 0 | 0 | 0 | 0
|  |  | On-delay timer - 0-30 Sec - 1 no. | 0 | 0 | 0 | 0
|  |  | R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos | 0 | 0 | 0 | 0
|  |  | PART ‘3’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 : DISTRIBUTION BOARDS | 0 | 0 | 0 | 0
4.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing Lighting / UPS / Power Distribution Boards (Double Door) suitable for 415V, 50 Hz system. Dust and vermin proof having floor / wall mounting cubicle pattern with removable gland plates, with 1 set of 100 amps Copper Bus Bar, Earth and Neutral Link etc as required. | 0 | 0 | 0 | 0
|  |  | ALL MCBS SHALL BE "C" TYPE AND RATED AT 10kA | 0 | 0 | 0 | 0
4.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | UPS DB : | 0 | 0 | 0 | 0
4.1.1.a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | For 3 Phase UPS | 8771 | 1 | 8771 | 3.85 | Nos.
|  |  | TPN, 4 Way | 0 | 0 | 0 | 0
|  |  | I/c:- 63 A TPN MCB. | 0 | 0 | 0 | 0
|  |  | O/g. 10/16/20 A SPMCB:- 12 nos. | 0 | 0 | 0 | 0
|  |  | OR | 0 | 0 | 0 | 0
4.1.1.b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | For 1 Phase UPS | 6483 | 0 | 0 | 0 | Nos.
|  |  | SPN, 16 Way | 0 | 0 | 0 | 0
|  |  | I/c:- 63 A DP MCB. | 0 | 0 | 0 | 0
|  |  | O/g. 10/16/20 A SPMCB:- 12 nos. | 0 | 0 | 0 | 0
4.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Emergency DB (If required/Optional) | 6483 | 0 | 0 | 0 | Nos.
|  |  | SPN, 12 Way | 0 | 0 | 0 | 0
|  |  | I/c:- 40 A DP MCB/ELCB | 0 | 0 | 0 | 0
|  |  | O/g. 10/16 A SPMCB- 6 nos. | 0 | 0 | 0 | 0
4.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Power DB : | 0 | 0 | 0 | 0
4.1.3.a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | TPN, 6 Way (for 1500 to 2500 sq. ft area) | 13638 | 0 | 0 | 0 | Nos.
|  |  | I/c:- 63 A TPN MCB | 0 | 0 | 0 | 0
|  |  | O/g - 3 nos 32A DP RCCB 100mA | 0 | 0 | 0 | 0
|  |  | O/g. 16/20 A SPMCB:- 12 nos. (4 nos per phase) | 0 | 0 | 0 | 0
4.1.3.b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | TPN, 8 Way (above 2500 Sq. ft area) | 14574 | 1 | 14574 | 6.39 | Nos.
|  |  | I/c:- 63 A TPN MCB | 0 | 0 | 0 | 0
|  |  | O/g - 3 nos 40A DP RCCB 100mA | 0 | 0 | 0 | 0
|  |  | O/g. 16/20 A SPMCB:- 18 nos. (6 nos per phase) | 0 | 0 | 0 | 0
4.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Lighting DB : | 0 | 0 | 0 | 0
4.1.4.a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | TPN, 6 Way (for 1500 to 2500 sq. ft area) | 13666 | 0 | 0 | 0 | Nos.
|  |  | I/c:- 63 A TPN MCB | 0 | 0 | 0 | 0
|  |  | O/g - 3 nos 32A DP RCCB 30mA | 0 | 0 | 0 | 0
|  |  | O/g. 10 A SPMCB:- 12 nos. (4 nos per phase) | 0 | 0 | 0 | 0
4.1.4.b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | TPN, 8 Way (above 2500 Sq. ft area) | 15021 | 1 | 15021 | 6.59 | Nos.
|  |  | I/c:- 63 A TPN MCB | 0 | 0 | 0 | 0
|  |  | O/g - 3 nos 32A DP RCCB 30mA | 0 | 0 | 0 | 0
|  |  | O/g. 10 A SPMCB:- 18 nos. (6 nos per phase) | 0 | 0 | 0 | 0
|  |  | PART ‘4’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 38366 | 16.83
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 5 : CABLES & TERMINATIONS | 0 | 0 | 0 | 0
5.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Supply , Installation of 1100V Grade PVC insulated , PVC sheathed GI wire armored Aluminium/ copper standard conductor , Cable of following sizes to be laid in on wall complete with dressing saddling clamping etc. Including civil work and required accessories. | 0 | 0 | 0 | 0
5.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3½ Core 120 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 805 | 0 | 0 | 0 | Mtrs.
5.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3½ Core 95 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 716 | 0 | 0 | 0 | Mtrs.
5.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3½ Core 70 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 553 | 28 | 15484 | 6.79 | Mtrs.
5.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3½ Core 50 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 466 | 0 | 0 | 0 | Mtrs.
5.1.5 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 35 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 387 | 0 | 0 | 0 | Mtrs.
5.1.6 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 25 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 340 | 0 | 0 | 0 | Mtrs.
5.1.7 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 16 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 262 | 0 | 0 | 0 | Mtrs.
5.1.8 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 10 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 250 | 0 | 0 | 0 | Mtrs.
5.1.9 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 10 sq.mm 1.1 KV Grade Copper Ar. Cable | 762 | 0 | 0 | 0 | Mtrs.
5.1.10 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 6 sq.mm 1.1 KV Grade Copper Ar. Cable | 508 | 0 | 0 | 0 | Mtrs.
5.1.11 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 4 sq.mm 1.1 KV Grade Copper Ar. Cable | 409 | 90 | 36810 | 16.14 | Mtrs.
5.1.12 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 Core 6 sq.mm 1.1 KV Grade Copper Ar. Cable | 423 | 0 | 0 | 0 | Mtrs.
5.1.13 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 35 sq. mm. copper flexible cable | 593 | 0 | 0 | 0 | Mtrs.
5.1.14 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 25 sq.mm. copper flexible cable | 411 | 0 | 0 | 0 | Mtrs.
5.1.15 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 16 sq.mm. copper flexible cable | 282 | 50 | 14100 | 6.18 | Mtrs.
5.1.16 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 10 sq.mm. copper flexible cable | 211 | 48 | 10128 | 4.44 | Mtrs.
5.2. | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | End termination of the following sizes of 1100V, Aluminium/copper (as per conductor), PVC insulated and sheathed armoured cables with single compression brass cable glands & crimping type Aluminum / Copper lugs, complete with all hardware etc. One end connection of a cable (with 3/4 core) to be consider as 1 end termination. | 0 | 0 | 0 | 0
5.2.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3½ Core 120 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 953 | 0 | 0 | 0 | Nos.
5.2.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3½ Core 95 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 798 | 0 | 0 | 0 | Nos.
5.2.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3½ Core 70 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 722 | 2 | 1444 | 0.63 | Nos.
5.2.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3½ Core 50 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 632 | 0 | 0 | 0 | Nos.
5.2.5 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 35 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 461 | 0 | 0 | 0 | Mtrs.
5.2.6 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 25 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 416 | 0 | 0 | 0 | Nos.
5.2.7 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 16 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 415 | 0 | 0 | 0 | Nos
5.2.8 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 10 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 381 | 0 | 0 | 0 | Nos
5.2.9 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 10 sq.mm 1.1 KV Grade Copper Ar. Cable | 555 | 0 | 0 | 0 | Nos.
5.2.10 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 6 sq.mm 1.1 KV Grade Copper Ar. Cable | 490 | 0 | 0 | 0 | Nos.
5.2.11 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 4 sq.mm 1.1 KV Grade Copper Ar. Cable | 427 | 5 | 2135 | 0.94 | Nos.
5.2.12 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 Core 6 sq.mm 1.1 KV Grade Copper Ar. Cable | 371 | 0 | 0 | 0 | Nos.
5.2.13 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 35 sq. mm. copper flexible cable | 165 | 0 | 0 | 0 | Nos.
5.2.14 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 25 sq.mm. copper flexible cable | 144 | 0 | 0 | 0 | Nos.
5.2.15 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 16 sq.mm. copper flexible cable | 137 | 8 | 1096 | 0.48 | Nos.
5.2.16 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 10 sq.mm. copper flexible cable | 129 | 10 | 1290 | 0.57 | Nos.
|  |  | PART ‘5’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 82487 | 36.18
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 6 : CABLING FOR CCTV, PAS AND FAS | 0 | 0 | 0 | 0
6.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | CCTV | 0 | 0 | 0 | 0
6.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 Core 1.0 sq.mm. FRLS, tinned copper, armoured cable. For camera power supply. | 113 | 0 | 0 | 0 | Mtrs.
6.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | RG59 FRLS, tinned copper, armoured cable for video transmission / TV connection (if any) | 94 | 0 | 0 | 0 | Mtrs.
|  |  | OR | 0 | 0 | 0 | 0
6.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | RG 59 FRLS tinned copper , flexible cable for video transmission through the conduit (including cost of conduit and its proper installation on ceiling / wall etc.) | 76 | 0 | 0 | 0 | Mtrs.
6.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and laying flexible Category 6 (CAT 6) cable for video transmission through the conduit (including cost of conduit and its proper installation on celling / wall etc.) Make : D-Link | 87 | 0 | 0 | 0 | Mtrs.
6.1.5 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and laying shield Category 6 (CAT 6) cable for video transmission through the conduit (including cost of conduit and its proper installation on celling / wall etc.) Make : D-Link | 92 | 0 | 0 | 0 | Mtrs.
6.1.6 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and laying armoured Category 6 (CAT 6) cable for video transmission and to be fixed on ceilling & wall with MS clamps & clips at every 1 mtr distance. (Cost of clamps and clips included with the rates) Make : D-Link | 97 | 160 | 15520 | 6.81 | Mtrs.
6.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | IAS - Intrusion Alarm System | 0 | 0 | 0 | 0
6.2.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 1 sq.mm. shielded copper cable in 20 mm rigid PVC Conduit with its accessories such as PVC spacers, saddles, screws, bends, couplings etc. | 120 | 75 | 9000 | 3.95 | Mtrs.
6.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | PAS - Panic Alarm System | 0 | 0 | 0 | 0
6.3.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 40/36, SWG flexible wire for Speakers connections | 99 | 0 | 0 | 0 | Mtrs.
6.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | FAS - Fire Alarm System | 0 | 0 | 0 | 0
6.4.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 Core X 1.5 Sqmm solid bare copper conductor, PVC insulated, Laid up, PVC sheathed, GI round wire armoured and overall FRLS RED colour PVS sheathed cable to IS 1554 Part I latest, Cable shall be cleated on ceiling, walls; laid on trays; concealed in timber partitions etc complete as directed and required to complete the installation. (For FAS) | 122 | 122 | 14884 | 6.53 | Mtrs.
6.4.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 Core X 1.5 Sqmm flexible copper conductor wires laid through conduits (including cost of conduit and its proper installation on ceiling / wall etc.) | 106 | 0 | 0 | 0 | Mtrs.
|  |  | PART ‘6’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 39404 | 17.28
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 7 : EARTHING WORK | 0 | 0 | 0 | 0
7.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Supplying and fixing following sizes of copper earth strips/cable complete with connections as required. | 0 | 0 | 0 | 0
7.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 core 6 sq.mm copper flexible cable for UPS earthing laid through the conduit. | 141 | 0 | 0 | 0 | Mtrs.
7.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 core 10 sq.mm copper flexible cable for UPS earthing laid through the conduit. | 194 | 0 | 0 | 0 | Mtrs.
7.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 25 mm x 3 mm copper strip | 724 | 0 | 0 | 0 | Mtrs.
7.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 25 mm x 3 mm G.I. strip | 76 | 0 | 0 | 0 | Mtrs.
7.1.5 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 8 Swg bare copper conductor laid through the conduit | 114 | 0 | 0 | 0 | Mtrs.
7.1.6 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 14 Swg bare copper conductor laid through the conduit | 83 | 0 | 0 | 0 | Mtrs.
7.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Plate Earthing: - Supply, Installation testing and commissioning of permanent earth stations with 600 mm x 600 mm x 3.15 mm copper earth plate & (G.I. pipe for watering) buried in specially prepared, 3 meters. deep earth pits with alternate layers of charcoal & salt, complete with reducer, funnel, wire mesh & test link and brick masonry chamber with hinged type cast iron cover etc. | 13842 | 0 | 0 | 0 | Nos.
7.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Pipe Earthing: - Supply, Installation testing and commissioning GI pipe earthing station including excavation, back filling, 50 mm diameter GI pipe of 3 m long, construction of inspection chamber, chamber cover (C.I), disconnecting link etc. as per specifications. | 11759 | 0 | 0 | 0 | Nos.
7.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Chemical Earthing: - Maintenance free Electrical Grounding system comprising of low carbon high tensile solid electrode of sufficient length (Not less than 2.5 Mtrs) with carbon based, combination of highly conductive material to achieve earth resistance less than 2 ohm. as confirming to IS : 3043-1987, Clause 9.2.8 and 9.3 : The material, selected for Earthing Electrode, and material used should be such that it resists the corrosion complete with CI cover (suitable for vehicular movement) and required masonry work. | 16017 | 0 | 0 | 0 | Nos.
|  |  | PART ‘7' TOTAL CARRIED TO SUMMARY | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 8 : SERVO BYPASS SWITCH | 0 | 0 | 0 | 0
8.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Supplying, installation, testing and commissioning the following type front operated cubicle type front operated panels made out of 14 swg powder coated CRCA Sheet Steel with adequate space for cables (4 Nos) | 0 | 0 | 0 | 0
8.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 80 Amps FP BYPASS - | 13729 | 0 | 0 | 0 | Nos.
8.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 100 Amps FP BYPASS - | 14492 | 0 | 0 | 0 | Nos.
8.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 125 Amps FP BYPASS - | 15954 | 0 | 0 | 0 | Nos.
8.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 160 Amps FP BYPASS - | 18009 | 0 | 0 | 0 | Nos.
8.1.5 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 200 Amps FP BYPASS - | 19675 | 0 | 0 | 0 | Nos.
|  |  | PART ‘8’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 9 : LIGHTING & POWER POINT WIRING | 0 | 0 | 0 | 0
9.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Point Wiring : Wiring for the following points with 3 x 1.5 sq.mm PVC Insulated, Copper Wire in 20mm rigid PVC Conduit pipes with its accessories such as PVC spacers, saddles, screws etc. complete with 1 no. 1.5 sq.mm PVC Insulated copper wire to be used as earthing including the cost of switches / back box, plate etc. | 0 | 0 | 0 | 0
9.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Primary Point : One Light Pt. controlled by one 6 Amps Switch (Point wiring including switches approx. 10 meters. Length) | 1137 | 44 | 50028 | 21.94 | Nos.
9.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Secondary light point: looped from primary light point. ( comprising of 3 nos. 1.5 sq.mm PVC ins. Copper cond. Wire in 20mm. Rigid PVC conduit pipe without switches) | 522 | 46 | 24012 | 10.53 | Nos.
9.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Secondary light point (Two way) looped from 1st light point but inclusive of switch.(3 nos. 1.5 sq.mm PVC ins. Copper cond. Wire in 20mm. Rigid PVC conduit pipe but excluding circuit wiring) | 1483 | 0 | 0 | 0 | Nos.
9.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Power Point Wiring : | 0 | 0 | 0 | 0
9.2.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 6 amps Light Plug Outlets :- | 587 | 20 | 11740 | 5.15 | Nos.
|  |  | Providing of 6 amps Modular type Socket and switch(multicountry type), M.S/ G.I Box for housing the above, Modular sheet, earthing the third pin with 1.00 mm PVC Insulated Copper Conductor as a earth conductor complete in all respects as required. (Cost of wire /pipe/raceways is NOT to be included in this cost) | 0 | 0 | 0 | 0
9.2.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Exhaust Fan Outlet points :- Providing of 6 amps 3Pin socket near the exhaust Fan and switch with the light switch board, G.I / M.S Box for housing the above, complete with earthing with 1.5 sq.mm. PVC insulated copper conductor/wire. | 839 | 0 | 0 | 0 | Nos.
9.2.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 6/16 amps Power Plug Outlets :- Providing of 16 amps Modular type Socket and switch(multicountry type), Box for housing the above, Modular sheet, earthing the third pin with 2.5 sq.mm mm PVC Insulated Copper Conductor Wire, complete in all respects as required (Cost of wire /pipe/raceways is NOT to be included in this cost) | 1283 | 9 | 11547 | 5.06 | Nos.
9.2.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Split A/c outdoor Box :- Providing and fixing of 20 Amps Industrial Socket outlet with top controlled by 20 A 10ka SP MCB all housed in M.S Box duly painted with IP 65, earthing the 3rd Pin with 2.5 sq.mm PVC Insulated copper conductor/wire. (excluding the cost of wires / cables) | 2288 | 0 | 0 | 0 | Nos.
|  |  | PART ‘9’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 97327 | 42.69
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 10 : POWER SOCKET & SWITCHES | 0 | 0 | 0 | 0
10.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Supply, Installation, testing, commissioning of following feeders for Incoming/ outgoing in weatherproof MS sheet box, power sockets etc. | 0 | 0 | 0 | 0
10.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 32 Amps 10ka SPN MCB Housed in M.S Sheet Box. | 758 | 0 | 0 | 0 | Nos.
10.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 63 Amps 10ka FP MCB Housed in M.S Sheet Box. | 1991 | 0 | 0 | 0 | Nos.
10.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 nos. of 5/15 A power sockets controlled by 1 no. of 15 A switch(multicountry sockets) | 1226 | 25 | 30650 | 13.44 | Nos.
10.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 nos. of 5/15A power socket controlled by 1 no. of 15 A switch(multicountry sockets) | 608 | 21 | 12768 | 5.6 | Nos.
10.1.5 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 nos. of 5/15 A power sockets without switch for CCTV power Supply unit(multicountry sockets). | 932 | 1.33 | 1239.56 | 0.54 | Nos.
10.1.6 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | RG -6 T.V Coaxial TV outlet Socket with Modular sheet and M.S Box included with 2 no.s of 5 Amp socket controlled by 1 No. of 15 Amp switch. | 1439 | 0 | 0 | 0 | Nos.
10.1.7 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 nos. of 5/15 A power sockets controlled by 1 no. of 15 A switch (multicountry sockets for Display TV) Separate circuit for 3 nos of front side TV's to be provided. | 1105 | 0 | 0 | 0 | Nos.
|  |  | PART ‘10’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 44657.56 | 19.59
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 11 : SUBMAINS CIRCUIT WIRING | 0 | 0 | 0 | 0
11.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Circuit Wiring (Light & Raw power points): Supply and laying of following sets of wires of PVC insulated , PVC sheathed copper flexible wires in laid PVC conduits Including civil work and required accessories spacers, clamps and hardware etc.(Cost of pipe/raceways is NOT to be included) | 0 | 0 | 0 | 0
11.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 8 meter wires) | 854 | 6 | 5124 | 2.25 | set
11.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 12 meter wires) | 1340 | 4 | 5360 | 2.35 | set
11.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 18 meter wires) | 2045 | 2 | 4090 | 1.79 | set
11.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 24 meter wires) | 2733 | 4 | 10932 | 4.79 | set
11.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | AC Wiring: Supply and laying of following cables with fixed length mentioned cable should be PVC insulated , PVC sheathed copper flexible wires in laid PVC conduits Including civil work and required accessories spacers, clamps and hardware etc.(Cost of pipe/raceways is NOT to be included) | 0 | 0 | 0 | 0
11.2.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 12 meter wires) | 1340 | 7 | 9380 | 4.11 | set
11.2.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 18 meter wires) | 2030 | 0 | 0 | 0 | set
11.2.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 24 meter wires) | 2690 | 6 | 16140 | 7.08 | set
11.2.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 4 sqmm and 1 X 2.5 sqmm (set of 12 meter wires) | 1528 | 0 | 0 | 0 | set
11.2.5 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 4 sqmm and 1 X 2.5 sqmm (set of 18 meter wires) | 2400 | 0 | 0 | 0 | set
11.2.6 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 4 sqmm and 1 X 2.5 sqmm (set of 24 meter wires) | 3034 | 0 | 0 | 0 | set
11.2.7 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 6 sqmm and 1 X 4 sqmm (set of 12 meter wires) | 2284 | 0 | 0 | 0 | set
11.2.8 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 6 sqmm and 1 X 4 sqmm (set of 18 meter wires) | 3279 | 0 | 0 | 0 | set
11.2.9 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 6 sqmm and 1 X 4 sqmm (set of 24 meter wires) | 4979 | 0 | 0 | 0 | set
11.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Computer / RAW Power Point Wiring: Supply & Installation of 3 core 2.5 sq.mm copper flexible PVC insulated sheathed wire 650V grade with ISI mark for connecting power points on work station in laid PVC conduits/raceways. One circuit wire should contains 2-3 UPS / Raw power points as least. (white colour- UPS and black colour:- RAW). (Cost of pipe/raceway is NOT to be included) | 0 | 0 | 0 | 0
11.3.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 core 2.5 sq.mm copper flexible cable ( set of 8 meter Length) | 1093 | 3 | 3279 | 1.44 | set
11.3.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 core 2.5 sq.mm copper flexible cable ( set of 12 meter Length) | 1622 | 2 | 3244 | 1.42 | set
11.3.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 core 2.5 sq.mm copper flexible cable ( set of 18 meter Length) | 2509 | 4 | 10036 | 4.4 | set
11.3.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 core 2.5 sq.mm copper flexible cable ( set of 24 meter Length) | 3276 | 6 | 19656 | 8.62 | set
|  |  | PART 11’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 87241 | 38.26
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 12 : LIGHT FITTINGS,EXHAUST FANS ETC. | 0 | 0 | 0 | 0
12.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | LED Light fittings | 0 | 0 | 0 | 0
|  |  | LED light design should be such that LPD (lighting Power Density) should be below 0.6 W per Sq.ft. at 400 lux level on table top. | 0 | 0 | 0 | 0
12.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 600 x 600mm Recess mounting LED panel CRCA powder coated white housing, Slim, aesthetic CRCA powder coated bottom frame, out frame (If requires) Special translucent high transmissivity, non yellowing polycarbonate diffuser, High power, high efficiency LEDs ,Specially designed constant current driver. Lumen output should be 3000 to 4000. Wattage should be inclusive of LED and Driver losses. (cost is including outer frame if lights need to be placed in gypsum celing) | 0 | 0 | 0 | 0
|  |  | Color Temperature 5000-6000K | 0 | 0 | 0 | 0
i | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 35W - 40W | 2118 | 34 | 72012 | 31.58 | Nos
ii | POP Punning | POP & FALSE CEILING WORKS | 30W - 34W | 2118 | 0 | 0 | 0 | Nos
iii | Partition | CARPENTRY AND INTERIOR WORKS | 25W - 30W | 2118 | 0 | 0 | 0 | Nos
12.1.2 | Partition | CARPENTRY AND INTERIOR WORKS | Circular recess mounted LED Down lighter High power, high efficiency Chip-On-Board LED module, High transitivity, non-yellowing PMMA diffuser, Pressure die cast aluminum housing and special, wave shaped radial heat sink, black powder coated, for superior thermal performance, Aesthetic white rim molded in engineering plastic, Specially designed, easy to install mounting clips. Lumen output should be 1000 to 1300 for 16 -18W, 700 - 1000 for 10 - 12W and 600 to 700 for 6 - 8W. Wattage should be inclusive of LED and Driver losses | 0 | 0 | 0 | 0
|  |  | Color Temperature 5000-6000K | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | 16W - 18W | 922 | 50 | 46100 | 20.22 | Nos
ii | POP Punning | POP & FALSE CEILING WORKS | 10W - 12W | 833 | 0 | 0 | 0 | Nos
iii | Partition | CARPENTRY AND INTERIOR WORKS | 6W - 8W | 715 | 0 | 0 | 0 | Nos
12.1.3 | Partition | CARPENTRY AND INTERIOR WORKS | Rectangular recess mounted LED Down lighter High power, high efficiency Chip-On-Board LED module, High transitivity, non-yellowing PMMA diffuser, Pressure die cast aluminum housing and special, wave shaped radial heat sink, black powder coated, for superior thermal performance, Aesthetic white rim molded in engineering plastic, Specially designed, easy to install mounting clips. Lumen output should be 1000 to 1300 for 16 -18W, 700 - 1000 for 10 - 12W and 600 to 700 for 6 - 8W. Wattage should be inclusive of LED and Driver losses | 0 | 0 | 0 | 0
|  |  | Color Temperature 5000-6000K | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | 16W - 18W | 922 | 0 | 0 | 0 | Nos
ii | POP Punning | POP & FALSE CEILING WORKS | 10W - 12W | 833 | 0 | 0 | 0 | Nos
iii | Partition | CARPENTRY AND INTERIOR WORKS | 6W - 8W | 717 | 0 | 0 | 0 | Nos
12.1.4 | Partition | CARPENTRY AND INTERIOR WORKS | 150mm x 1200mm recess mounting White powder coated finish CRCA housing with extruded Aluminium lip. High efficiency LEDs with long life. Special translucent satin finish virgin PMMA diffuser, Luminaire system wattage. Specially designed driver. Wattage should be inclusive of LED and Driver losses. | 0 | 0 | 0 | 0
|  |  | Color Temperature 5000-6000K | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | 25W - 28W | 3841 | 0 | 0 | 0 | Nos
12.1.5 | Partition | CARPENTRY AND INTERIOR WORKS | 300mm x 1200mm recess mounting White powder coated finish CRCA housing with extruded Aluminium lip. High efficiency LEDs with long life. Special translucent satin finish virgin PMMA diffuser, Luminaire system wattage . Specially designed driver. Wattage should be inclusive of LED and Driver losses. | 0 | 0 | 0 | 0
|  |  | Color Temperature 5000-6000K | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | 25W - 28W | 4258 | 0 | 0 | 0 | Nos
12.1.6 | Partition | CARPENTRY AND INTERIOR WORKS | High power, high efficiency Chip-On-Board LED module LED BAR type fitting for installation in trough lighting (similar to28W T5) for Cove lighting applications | 0 | 0 | 0 | 0
|  |  | Color Temperature 3000-4000K | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | 10W | 466 | 0 | 0 | 0 | Nos
ii | POP Punning | POP & FALSE CEILING WORKS | 20W | 542 | 0 | 0 | 0 | Nos
|  |  | Color Temperature 5000-6000K | 0 | 0 | 0 | 0
iii | Partition | CARPENTRY AND INTERIOR WORKS | 10W | 466 | 0 | 0 | 0 | Nos
iv | PAINTING WORKS | PAINTING WORKS | 20W | 527 | 0 | 0 | 0 | Nos
12.1.7 | PAINTING WORKS | PAINTING WORKS | Circular recess mounted Rechargable LED emergency Down lighter High power, high efficiency Chip-On-Board LED module, High transitivity, non-yellowing PMMA diffuser, Pressure die cast aluminum housing and special, wave shaped radial heat sink, black powder coated, for superior thermal performance, Aesthetic white rim molded in engineering plastic, Specially designed, easy to install mounting clips. Lumen output should be 1000 to 1300 for 16 -18W, 700 - 1000 for 10 - 12W and 600 to 700 for 6 - 8W. Wattage should be inclusive of LED and Driver losses | 0 | 0 | 0 | 0
|  |  | Color Temperature 5000-6000K | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | 16W - 18W | 988 | 0 | 0 | 0 | Nos
ii | POP Punning | POP & FALSE CEILING WORKS | 10W - 12W | 876 | 0 | 0 | 0 | Nos
iii | Partition | CARPENTRY AND INTERIOR WORKS | 6W - 8W | 716 | 0 | 0 | 0 | Nos
12.1.8 | Partition | CARPENTRY AND INTERIOR WORKS | Supply & Installation of 225 mm single phase exhaust fans ( BEE Star rated Fans as suggested by Bank or CPC team as exception / Refer Make and Model sheet,fans) with mounting frame and safety grill etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan. | 2002 | 3 | 6006 | 2.63 | Nos
12.1.9 | Partition | CARPENTRY AND INTERIOR WORKS | Supply & Installation of ceiling fan (BEE Star rated Fans as suggested by Bank or CPC team as exception / Refer Make and Model sheet,fans) 1400 mm sweep with all hanging accessories, electronics regulator, blades etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan. | 2034 | 0 | 0 | 0 | Nos
12.1.10 | Partition | CARPENTRY AND INTERIOR WORKS | Supply & Installation of bracket fan 400 mm sweep, oscillating type with all fixing accessories, blades etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan. | 2449 | 4 | 9796 | 4.3 | Nos
12.1.11 | Partition | CARPENTRY AND INTERIOR WORKS | Supply & Installation of pedestal fan 400 mm sweep, oscillating type with all fixing accessories, blades etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan | 2836 | 2 | 5672 | 2.49 | Nos
|  |  | PART ‘12’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 139586 | 61.22
PART- | Partition | CARPENTRY AND INTERIOR WORKS | 13 : RACEWAYS ,CONDUITS, CASSING-CAPPING | 0 | 0 | 0 | 0
13.1 | Partition | CARPENTRY AND INTERIOR WORKS | Supply & Installation of totally concealed underfloor Al./G.I Trunking. Trunking to be of the following sizes. Excavation & refilling cost is NOT to be included. The same is to be done by Civil agency. Thickness of underfloor raceways shall be 1.60mm up to 38 mm depth and 2.0mm above 40mm depth | 0 | 0 | 0 | 0
13.1.1 | Partition | CARPENTRY AND INTERIOR WORKS | 65 mm x 35 mm x 1.6mm | 305 | 0 | 0 | 0 | Mtrs.
13.1.2 | Partition | CARPENTRY AND INTERIOR WORKS | 80 mm x 40 mm x 2.0mm | 404 | 0 | 0 | 0 | Mtrs.
13.1.3 | Partition | CARPENTRY AND INTERIOR WORKS | 100 mm x 40 mm x 2.00mm | 495 | 0 | 0 | 0 | Mtrs.
13.1.4 | Partition | CARPENTRY AND INTERIOR WORKS | 150mm x 38mm x 1.6 mm G.I Floor Raceway | 572 | 0 | 0 | 0 | Mtrs.
13.1.5 | Partition | CARPENTRY AND INTERIOR WORKS | 300mm x 38mm x 2.0 mm G.I Floor Raceway | 762 | 0 | 0 | 0 | Mtrs.
13.2 | Partition | CARPENTRY AND INTERIOR WORKS | Supply & Installation of Floor Junction Boxes fabricated out of GI / M.S Sheet (Powder Coated) of the following sizes as required complete with 3mm Thick SS Sheet Cover as required. | 0 | 0 | 0 | 0
13.2.1 | Partition | CARPENTRY AND INTERIOR WORKS | 100 x 100 mm | 686 | 0 | 0 | 0 | Nos
13.2.2 | Partition | CARPENTRY AND INTERIOR WORKS | 150 x 150 mm | 911 | 3 | 2733 | 1.2 | Nos
13.2.3 | Partition | CARPENTRY AND INTERIOR WORKS | 200 x 200 mm | 1048 | 2 | 2096 | 0.92 | Nos
13.2.4 | Partition | CARPENTRY AND INTERIOR WORKS | 300 x 300 mm | 1144 | 9 | 10296 | 4.52 | Nos
13.3 | Partition | CARPENTRY AND INTERIOR WORKS | Supply & Installation of totally concealed underfloor rigid PVC pipes of MMS gauge of following sizes. | 0 | 0 | 0 | 0
13.3.1 | Partition | CARPENTRY AND INTERIOR WORKS | 20 mm | 50 | 0 | 0 | 0 | Mtrs.
13.3.2 | Partition | CARPENTRY AND INTERIOR WORKS | 25 mm | 55 | 38 | 2090 | 0.92 | Mtrs.
13.3.3 | Partition | CARPENTRY AND INTERIOR WORKS | 32 mm | 73 | 210 | 15330 | 6.72 | Mtrs.
13.4 | Partition | CARPENTRY AND INTERIOR WORKS | Supply & Installation of the PVC casing capping over the wall, partition from junction box to power point | 0 | 0 | 0 | 0
13.4.1 | Partition | CARPENTRY AND INTERIOR WORKS | 25 mm | 53 | 10 | 530 | 0.23 | Mtrs.
13.4.2 | Partition | CARPENTRY AND INTERIOR WORKS | 50 mm | 97 | 20 | 1940 | 0.85 | Mtrs.
13.5 | Partition | CARPENTRY AND INTERIOR WORKS | Supplying and fixing of the following sizes of G.I Cable Trays , complete with threaded hangers, nuts bolts, washers and couplers as required for fixing of cable trays. | 0 | 0 | 0 | 0
13.5.1 | Partition | CARPENTRY AND INTERIOR WORKS | 300 mm X 40mm x 40 mm x1.6 mm | 861 | 0 | 0 | 0 | R. Mtr
13.5.2 | Partition | CARPENTRY AND INTERIOR WORKS | 150mm x 40mm x 40mm x 1.6 mm | 550 | 0 | 0 | 0 | R. Mtr
13.5.3 | Partition | CARPENTRY AND INTERIOR WORKS | 100mm x 40mm x 40mm x 1.6 mm | 482 | 0 | 0 | 0 | R. Mtr
13.6 | Partition | CARPENTRY AND INTERIOR WORKS | Supply & Installation of totally concealed underfloor / Wall rigid GI pipes conduits of of following sizes. | 0 | 0 | 0 | 0
13.6.1 | Partition | CARPENTRY AND INTERIOR WORKS | 25 mm | 175 | 0 | 0 | 0 | Mtrs.
13.6.2 | Partition | CARPENTRY AND INTERIOR WORKS | 50 mm | 350 | 0 | 0 | 0 | Mtrs.
|  |  | PART ‘13’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 35015 | 15.36
PART - | Partition | CARPENTRY AND INTERIOR WORKS | 14 : FIRE FIGHTING WORKS | 0 | 0 | 0 | 0
14.1 | Partition | CARPENTRY AND INTERIOR WORKS | Supply, Installation, testing, commissioning of sprinkler point complete with MS pipe, flexible pipe, valve and sprinkler complete with all accessories for the smooth operation of the system. (average costing for 1 sprinkler point for the premises of minimum 25 points) (Optional for non-branch premises only where the other part of premises includes sprinkler system: like Mall etc ) | 6059 | 0 | 0 | 0 | set
|  |  | PART ‘14’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 0 | 0
PART- | Partition | CARPENTRY AND INTERIOR WORKS | 15 : MISCELLANEOUS WORK | 0 | 0 | 0 | 0
15.1 | Partition | CARPENTRY AND INTERIOR WORKS | Retaining one electrician at site till completion of IT installation and Branch launch activities. | 17034 | 1 | 17034 | 7.47 | per month per person
15.2 | Partition | CARPENTRY AND INTERIOR WORKS | Provide and fixing of air curtain at main entrance door with Remote and inbuild sensor with effective height of 7 ft to 9 ft having noise level up to 50 db and maximum air flow velocity up to 21 m/s at nozzel. | 0 | 0 | 0 | 0
a | Partition | CARPENTRY AND INTERIOR WORKS | size 900 x 230 x 220, CFM 825 | 12107 | 0 | 0 | 0 | No.s
b | Partition | CARPENTRY AND INTERIOR WORKS | size 1200 x 230 x 220, CFM 1100 | 15134 | 0 | 0 | 0 | No.s
c | Partition | CARPENTRY AND INTERIOR WORKS | size 1500 x 230 x 220, CFM 1380 | 18221 | 0 | 0 | 0 | No.s
15.3 | Partition | CARPENTRY AND INTERIOR WORKS | Supply and installation of 1.5 KW one box /DB timer solution for switching ON/OFF signage boards in auto as per set timing. This box includes Timer, power contactor, SP MCB, Auto / Manual switch, terminal out, internal wiring including Box/DB etc. there should be 3 output from box to connect main signage and lollypop signages. (Make: L&T, Siemens, Legrand, Schneider) | 3334 | 0 | 0 | 0 | Set
|  |  | PART ‘15’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 17034 | 7.47
|  |  | PART ‘1’ POWER DISTRIBUTION PANEL | 0 | 0 | 212537 | 93.22
|  |  | PART ‘2’ CAPACITOR PANEL | 0 | 0 | 0 | 0
|  |  | PART ‘3’ PHASE CORRECTION CIRCUIT | 0 | 0 | 0 | 0
|  |  | PART ‘4’ DISTRIBUTION BOARDS | 0 | 0 | 38366 | 16.83
|  |  | PART ‘5’ CABLES & TERMINATIONS | 0 | 0 | 82487 | 36.18
|  |  | PART ‘6’ CABLING FOR CCTV AND PAS | 0 | 0 | 39404 | 17.28
|  |  | PART ‘7’ EARTHING WORK | 0 | 0 | 0 | 0
|  |  | PART '8’ SERVO BYPASS SWITCH | 0 | 0 | 0 | 0
|  |  | PART ‘9’ LIGHTING & POWER POINT WIRING | 0 | 0 | 97327 | 42.69
|  |  | PART ‘10’ POWER SOCKET & SWITCHES | 0 | 0 | 44657.56 | 19.59
|  |  | PART ‘11' SUBMAINS CIRCUIT WIRING | 0 | 0 | 87241 | 38.26
|  |  | PART ‘12’ LIGHT FITTINGS,EXHAUST FANS ETC. | 0 | 0 | 139586 | 61.22
|  |  | PART ‘13’ RACEWAYS ,CONDUITS, CASSING-CAPPING | 0 | 0 | 35015 | 15.36
|  |  | PART ‘14’ FIRE FIGHTING WORKS | 0 | 0 | 0 | 0
|  |  | PART ‘15’ MISCELLANEOUS WORK | 0 | 0 | 17034 | 7.47
VII | Additional Work | Additional Work | ADDITIONAL WORK | 0 | 0 | 0 | 0
1 | Additional Work | Additional Work | Chess Board | 1500 | 0 | 0 | 0 | Nos
2 | Additional Work | Additional Work | Dart Board | 1800 | 0 | 0 | 0 | Nos
3 | Additional Work | Additional Work | Conference Room Table | 789 | 94.4 | 74481.6 | 32.67 | Sq.ft
4 | Additional Work | Additional Work | Pantry Table | 996 | 54 | 53784 | 23.59 | Sq.ft
5 | Additional Work | Additional Work | Back Painted Glass Divider | 695 | 21 | 14595 | 6.4 | Sq.ft
6 | Additional Work | Additional Work | HDMI Cable | 180 | 15 | 2700 | 1.18 | Mtr
7 | Additional Work | Additional Work | HDMI Cable | 180 | 25 | 4500 | 1.97 | Mtr
8 | Additional Work | Additional Work | LED Profile | 110 | 25 | 2750 | 1.21 | Rft
9 | Additional Work | Additional Work | Photo Frame | 1500 | 5 | 7500 | 3.29 | Nos
10 | Additional Work | Additional Work | UPS DB (100 Amp 4P -1 Nos 63 AMP 2P x 3 nos) - Legrand | 1000 | 1 | 1000 | 0.44 | Nos
11 | Additional Work | Additional Work | LED Tube 40 W - Philips | 500 | 3 | 1500 | 0.66 | Nos
I | Others | Others/Uncategorized | CIVIL & RELATED WORKS | 0 | 0 | 0 | 0
1 | Others | Others/Uncategorized | Demolition / Clearing Works | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | Dismantling of existing dado tiles without plaster | 0 | 0 | 0 | 0
|  |  | Hub Room Old Tiles | 0 | 0 | 0 | 0
|  |  | Gents Washroom | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Conference Room | 0 | 0 | 0 | 0
|  |  | CH Cabin Wall | 0 | 0 | 0 | 0
|  |  | RM Wall | 0 | 0 | 0 | 0
|  |  | RM near Window | 0 | 0 | 0 | 0
|  |  | RM Area Column 1 & 2 | 0 | 0 | 0 | 0
|  |  | RM Area Cloumn 3, 4 & 5 | 0 | 0 | 0 | 0
|  |  | Server Window Granite 7 x 3 | 0 | 0 | 0 | 0
|  |  | Store Window Granite 4 x 3 | 0 | 0 | 0 | 0
|  |  | Store Door Frame 7 x 3 | 0 | 0 | 0 | 0
|  |  | Ladies Window Granite 5.5 x 4 | 0 | 0 | 0 | 0
|  |  | Gents Window Granite 2 x 3 | 0 | 0 | 0 | 0
|  |  | Gents Window Granite 4 x 4 | 0 | 0 | 0 | 0
|  |  | Pantry Window Granite 4 x 4 - 2nos / 5.5 x 4 / 2 x 3 | 0 | 0 | 0 | 0
|  |  | Conf Window Granite 2 x 3 - 4nos | 0 | 0 | 0 | 0
|  |  | CH Window Granite 2 x 3 | 0 | 0 | 0 | 0
|  |  | RM Window Granite 2 x 3 | 0 | 0 | 0 | 0
iii | Partition | CARPENTRY AND INTERIOR WORKS | Dismantling of existing plaster | 0 | 0 | 0 | 0
|  |  | Store Room | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Ladies Washroom | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Deduction - Window | 0 | 0 | 0 | 0
|  |  | Hub Entry Column | 0 | 0 | 0 | 0
|  |  | Graphic Wall | 0 | 0 | 0 | 0
iv | PAINTING WORKS | PAINTING WORKS | Existing flooring including bedding material & PCC/IPS. | 0 | 0 | 0 | 0
|  |  | Hub Room | 0 | 0 | 0 | 0
|  |  | Ladies Washroom | 0 | 0 | 0 | 0
|  |  | Deduction - Column | 0 | 0 | 0 | 0
|  |  | Gents Washroom | 0 | 0 | 0 | 0
|  |  | Pantry near Wash Basin | 0 | 0 | 0 | 0
|  |  | Conference Room | 0 | 0 | 0 | 0
|  |  | CH Cabin | 0 | 0 | 0 | 0
|  |  | RM | 0 | 0 | 0 | 0
|  |  | RM near Window | 0 | 0 | 0 | 0
v | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Existing Doors / Windows | 0 | 0 | 0 | 0
|  |  | Windows - Server / Store / Ladies / Gents -2 / Pantry -4 / Conf- 4 / CH / RM | 0 | 0 | 0 | 0
|  |  | Door - Pantry | 0 | 0 | 0 | 0
xii | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Dismantling of existing RCC 6 "/ 9" thk wall. | 0 | 0 | 0 | 0
|  |  | For Plumbing | 0 | 0 | 0 | 0
2 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Construction of Masonry Walls | 0 | 0 | 0 | 0
d | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Do-do as 2(a) above but 150mm thk siporex / AAC / Aerocon / light weight block wall | 0 | 0 | 0 | 0
|  |  | Hub Room Window | 0 | 0 | 0 | 0
|  |  | Hub Room Entry | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Hub Room | 0 | 0 | 0 | 0
|  |  | Electric Room | 0 | 0 | 0 | 0
|  |  | Utility Entry | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Store Room Wall | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Gents Wall | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Ladies Entry Wall | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Store Room Window | 0 | 0 | 0 | 0
|  |  | Ladies Wall Near Column | 0 | 0 | 0 | 0
|  |  | Ladies Window | 0 | 0 | 0 | 0
|  |  | Gents Window | 0 | 0 | 0 | 0
|  |  | Pantry Wall | 0 | 0 | 0 | 0
|  |  | Pantry Window | 0 | 0 | 0 | 0
|  |  | Conf Window | 0 | 0 | 0 | 0
|  |  | CH Windpw | 0 | 0 | 0 | 0
|  |  | RM Window | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
4 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Plaster | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | P/A 1:4 cement plaster | 0 | 0 | 0 | 0
|  |  | Wall Construction | 0 | 0 | 0 | 0
|  |  | Ladies Column | 0 | 0 | 0 | 0
|  |  | Existing Wall in Ladies Column | 0 | 0 | 0 | 0
|  |  | Deduction - Window | 0 | 0 | 0 | 0
|  |  | Existing Wall in Gents | 0 | 0 | 0 | 0
|  |  | Deduction - Window | 0 | 0 | 0 | 0
|  |  | Pantry Wall | 0 | 0 | 0 | 0
|  |  | Deduction - Windows | 0 | 0 | 0 | 0
|  |  | Deduction - Windows | 0 | 0 | 0 | 0
|  |  | Conference Room | 0 | 0 | 0 | 0
|  |  | Deduction - Windows | 0 | 0 | 0 | 0
|  |  | CH Cabin | 0 | 0 | 0 | 0
|  |  | RM Area | 0 | 0 | 0 | 0
|  |  | RM Arear near Window | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
5 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Waterproofing treatment | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | P/A waterproofing treatment for toilets , pantry counter | 0 | 0 | 0 | 0
|  |  | Ladies - Floor | 0 | 0 | 0 | 0
|  |  | Ladies - Wall | 0 | 0 | 0 | 0
|  |  | Deduction - Column | 0 | 0 | 0 | 0
|  |  | Deduction - Ladies Door | 0 | 0 | 0 | 0
|  |  | Gents - Floor | 0 | 0 | 0 | 0
|  |  | Gents - Wall | 0 | 0 | 0 | 0
|  |  | Deduction - Gents Door | 0 | 0 | 0 | 0
|  |  | Basin Counter | 0 | 0 | 0 | 0
|  |  | Basin Counter Wall | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
6 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Brick Bat Coba | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Proving and Laying brick bat coba up to 150mm thk | 0 | 0 | 0 | 0
|  |  | Ladies - Floor | 0 | 0 | 0 | 0
|  |  | Deduction - Column | 0 | 0 | 0 | 0
|  |  | Gents - Floor | 0 | 0 | 0 | 0
|  |  | Basin Counter | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
7 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Plain Cement Concrete | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | P/E Plain cement concrete | 0 | 0 | 0 | 0
|  |  | Hub Room | 0 | 0 | 0 | 0
|  |  | Conf Room | 0 | 0 | 0 | 0
|  |  | CH Cabin | 0 | 0 | 0 | 0
|  |  | RM Area | 0 | 0 | 0 | 0
|  |  | RM Window Area | 0 | 0 | 0 | 0
|  |  | Lift Area | 0 | 0 | 0 | 0
9 | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Flooring | 0 | 0 | 0 | 0
a | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Vitrified Tile Flooring | 0 | 0 | 0 | 0
i | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Proving and Laying 1000mm x 1000mm / 800mm X 800 mm Vitrified floor tiles | 0 | 0 | 0 | 0
|  |  | Branch / ATM Area | 0 | 0 | 0 | 0
|  |  | Staircase Area | 0 | 0 | 0 | 0
|  |  | Deductions | 0 | 0 | 0 | 0
|  |  | Staircase Area | 0 | 0 | 0 | 0
|  |  | Server room | 0 | 0 | 0 | 0
|  |  | Store room | 0 | 0 | 0 | 0
|  |  | Ladies - Floor | 0 | 0 | 0 | 0
|  |  | Gents - Floor | 0 | 0 | 0 | 0
|  |  | Antilobby | 0 | 0 | 0 | 0
|  |  | Less Balcony | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | Similar to above but for providing and fixing 75mm high skirting/border. | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | RM Area | 0 | 0 | 0 | 0
|  |  | Lift Lobby | 0 | 0 | 0 | 0
b | POP Punning | POP & FALSE CEILING WORKS | Anti-skid and anti-dust vitrified tile Flooring | 0 | 0 | 0 | 0
iii | Partition | CARPENTRY AND INTERIOR WORKS | Proving and Laying 600mm x 600mm anti-skid and Anti-dust Vitrified floor tiles | 0 | 0 | 0 | 0
|  |  | Ground Floor | 0 | 0 | 0 | 0
|  |  | Ladies - Floor | 0 | 0 | 0 | 0
|  |  | Ladies - Wall | 0 | 0 | 0 | 0
|  |  | Deduction - Ladies Door | 0 | 0 | 0 | 0
|  |  | Deduction - Window | 0 | 0 | 0 | 0
|  |  | Gents - Floor | 0 | 0 | 0 | 0
|  |  | Gents - Wall | 0 | 0 | 0 | 0
|  |  | Deduction - Gents Door | 0 | 0 | 0 | 0
|  |  | Deduction - Window | 0 | 0 | 0 | 0
|  |  | Server room | 0 | 0 | 0 | 0
|  |  | Store room | 0 | 0 | 0 | 0
|  |  | Antilobby floor | 0 | 0 | 0 | 0
|  |  | Antilobby wall | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Cafeteria Wall | 0 | 0 | 0 | 0
|  |  | Deduction - Windows | 0 | 0 | 0 | 0
|  |  | Deduction - Windows | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Deduction - Electric Panel | 0 | 0 | 0 | 0
|  |  | Deduction - Graphic Wall | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Deduction - Window | 0 | 0 | 0 | 0
|  |  | Balcony Area | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
iv | PAINTING WORKS | PAINTING WORKS | Similar as 9_b_i but for providing and fixing 75mm high skirting/border. | 0 | 0 | 0 | 0
|  |  | Balcony Area | 0 | 0 | 0 | 0
|  |  | Less door | 0 | 0 | 0 | 0
|  |  | Hub Room | 0 | 0 | 0 | 0
|  |  | Store Room | 0 | 0 | 0 | 0
f | PAINTING WORKS | PAINTING WORKS | Vinyl Flooring | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Providing fixing Vinyl Anti-Static flooring 2mm thick (flexible roll) -Armstrong/LG/Tusker - | 0 | 0 | 0 | 0
|  |  | Conference room | 0 | 0 | 0 | 0
|  |  | Deduction | 0 | 0 | 0 | 0
g | PAINTING WORKS | PAINTING WORKS | False Flooring | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | P/F Raised access floor (false floor app. 150 mm to 230 mm high) . | 0 | 0 | 0 | 0
|  |  | Server | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
h | PAINTING WORKS | PAINTING WORKS | POP covering on Flooring | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | Providing and applying covering on flooring for floor protection | 0 | 0 | 0 | 0
|  |  | Branch | 0 | 0 | 0 | 0
|  |  | Deduction - Washroom & Server | 0 | 0 | 0 | 0
|  |  | Staircase Area | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
10 | POP Punning | POP & FALSE CEILING WORKS | Pantry / Dining / Toilet Counter & Thresholds | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing & fixing 600mm deep pantry counter | 0 | 0 | 0 | 0
|  |  | Pantry counter | 0 | 0 | 0 | 0
d | POP Punning | POP & FALSE CEILING WORKS | Providing & Fixing of size 450mm X 900mm both sides polished divider | 0 | 0 | 0 | 0
|  |  | Gents | 0 | 0 | 0 | 0
e | POP Punning | POP & FALSE CEILING WORKS | Providing & Laying 150mm wide Jet black Granite Threshold at ATM and Main Entrance | 0 | 0 | 0 | 0
|  |  | Hub Room | 0 | 0 | 0 | 0
|  |  | Ladies | 0 | 0 | 0 | 0
|  |  | Gents | 0 | 0 | 0 | 0
|  |  | Antilobby | 0 | 0 | 0 | 0
|  |  | Store | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Office Entry | 0 | 0 | 0 | 0
|  |  | Staircase | 0 | 0 | 0 | 0
f | POP Punning | POP & FALSE CEILING WORKS | Providing & Laying 75 mm wide Black granite Threshold for Toilets & Pantry. (Basic Cost of Jet black granite upto Rs. 180/- sq.ft) | 0 | 0 | 0 | 0
|  |  | Ground Floor | 0 | 0 | 0 | 0
|  |  | Gents | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
11 | POP Punning | POP & FALSE CEILING WORKS | External Paving/Flooring/Window sill | 0 | 0 | 0 | 0
e | POP Punning | POP & FALSE CEILING WORKS | Sill & jambs to windows / Doors. Providing and laying in required positions granite, slab 12 mm thk (Single piece) | 0 | 0 | 0 | 0
|  |  | Gents | 0 | 0 | 0 | 0
|  |  | Ladies | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Pantry Door | 0 | 0 | 0 | 0
f | POP Punning | POP & FALSE CEILING WORKS | Sill & jambs to windows / Doors.Providing and laying in required positions black granite of 18mm thk. Upto 2100mm in length (double piece), | 0 | 0 | 0 | 0
|  |  | Gents Washroom | 0 | 0 | 0 | 0
|  |  | Ladies Washrooom | 0 | 0 | 0 | 0
|  |  | Antilobby | 0 | 0 | 0 | 0
|  |  | Store | 0 | 0 | 0 | 0
15 | POP Punning | POP & FALSE CEILING WORKS | Plumbing | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Internal concealed plumbing . Gents Toilet (2 no Urinal + 1 nos. wash basin + 1 no EWC) | 0 | 0 | 0 | 0
b | POP Punning | POP & FALSE CEILING WORKS | Internal concealed plumbing Ladies Toilet (1 Wash Basin + 1 EWC) | 0 | 0 | 0 | 0
c | POP Punning | POP & FALSE CEILING WORKS | Supply fixing and installation of Concealed stop cocks | 0 | 0 | 0 | 0
d | POP Punning | POP & FALSE CEILING WORKS | Internal Plumbing work for Pantry. Water supply and drainage points for sink. | 0 | 0 | 0 | 0
e | POP Punning | POP & FALSE CEILING WORKS | Supply & fixing of Nahani trap | 0 | 0 | 0 | 0
f | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing machanical driven industrial grade water meter | 0 | 0 | 0 | 0
16 | POP Punning | POP & FALSE CEILING WORKS | Sanitary wares (Pure white colour) | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing first quality European Water closet with attached cisten of Dual Flush Cistern | 0 | 0 | 0 | 0
d | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing of single Urinal pressmatic Flushing system | 0 | 0 | 0 | 0
e | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing under/ Over counter Wash Basin | 0 | 0 | 0 | 0
h | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing Pantry staintless steel sink | 0 | 0 | 0 | 0
17 | POP Punning | POP & FALSE CEILING WORKS | Plumbing Fittings | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing heavy duty pillar cock for pantry | 0 | 0 | 0 | 0
b | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing angular stopcock | 0 | 0 | 0 | 0
c | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing heavy duty C.P. brass short body bibcock (two in one) | 0 | 0 | 0 | 0
d | POP Punning | POP & FALSE CEILING WORKS | providing and fixing of heavy duty bottle trap. | 0 | 0 | 0 | 0
e | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing heavy duty pillar cock for washbasins | 0 | 0 | 0 | 0
g | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing aerators Shower Flow Aerator (Spray) | 0 | 0 | 0 | 0
h | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing hand type Jet Spray with adjustable nozzle | 0 | 0 | 0 | 0
18 | POP Punning | POP & FALSE CEILING WORKS | Toilet Accessories | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Supplying of disposable Soap Dispenser | 0 | 0 | 0 | 0
b | POP Punning | POP & FALSE CEILING WORKS | Supply & fixing of Toilet paper holder | 0 | 0 | 0 | 0
c | POP Punning | POP & FALSE CEILING WORKS | Supply & fixing of SS finish Robe Hooks | 0 | 0 | 0 | 0
d | POP Punning | POP & FALSE CEILING WORKS | CP brass towel ring manufactured by Jaugar or as approved by bank or CPC team | 0 | 0 | 0 | 0
19 | POP Punning | POP & FALSE CEILING WORKS | External plumbing works. | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing & laying CPVC pipes with screwed sockets, joints, and necessary pvc fittings such as socket, elbows, bends, tees etc., including making/ drilling holes in walls/ slabs and remaking good the damages in original conditions. The rate is inclusive of necessary scaffolding ( Make : Astral / Precision / Prince ) | 0 | 0 | 0 | 0
iii | Partition | CARPENTRY AND INTERIOR WORKS | 25mmdia | 0 | 0 | 0 | 0
b | Partition | CARPENTRY AND INTERIOR WORKS | Supplying and fixing of PVC Pipe of SWR Grade of approved company including all necessary fitting fixed with GI Clamp making necessary holes in valets, refilling the same with concrete making good the damaged portions with matching plaster complete in all respects. The rate is inclusive of scaffolding. ( Make : Astral / Precision / Prince ) | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | 4" dia | 0 | 0 | 0 | 0
20 | POP Punning | POP & FALSE CEILING WORKS | Anti Termite Treatment | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Carrying out Ecofriendly Pest control and ant-termite | 0 | 0 | 0 | 0
|  |  | Branch | 0 | 0 | 0 | 0
21 | POP Punning | POP & FALSE CEILING WORKS | Miscellaneous civil work | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Chasing work in the existing brick/siporex up to 200mm wide and max to 75mm deep, | 0 | 0 | 0 | 0
|  |  | Pantry - 6' x 6nos + 4' x 1nos / Server -6' x 1nos / Antilobby - 6' x 1nos / Store - 6' x 1nos | 0 | 0 | 0 | 0
b | POP Punning | POP & FALSE CEILING WORKS | Trenching work as per width and depth required. | 0 | 0 | 0 | 0
c | POP Punning | POP & FALSE CEILING WORKS | Making punctures in existing brick/siporex block up to 200mm diameter, | 0 | 0 | 0 | 0
e | POP Punning | POP & FALSE CEILING WORKS | Filling charges of Diesel in installed D.G. set by Bank (Vendor should submit diesel bill during final billing) | 0 | 0 | 0 | 0
f | POP Punning | POP & FALSE CEILING WORKS | Civil & interior vendor will be responsible for securing the premises till the site is ready for IT hand-over with proper locking mechanism or till project is handed over to Project manager. (Daily 12 hour shift ) | 0 | 0 | 0 | 0
g | POP Punning | POP & FALSE CEILING WORKS | TOILET CUBICLES - Provide and fix Toilet cubicles bottom | 0 | 0 | 0 | 0
|  |  | Gents | 0 | 0 | 0 | 0
h | POP Punning | POP & FALSE CEILING WORKS | Providing and making Core cut of in RCC slab / Beam of thickness up to 300mm, | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Upto 75mm dia | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | Upto 100mm dia | 0 | 0 | 0 | 0
iii | Partition | CARPENTRY AND INTERIOR WORKS | Upto 150mm dia | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing, fixing and Removing MS H type frame scaffolding for branch interior and exterior work. Scafolding should have flat working platform. | 0 | 0 | 0 | 0
|  |  | Plumbing Work - 10 x 35 | 0 | 0 | 0 | 0
k | Partition | CARPENTRY AND INTERIOR WORKS | Prepare and maintain document list, Technical cut sheet, All type of layout, Electrical based calculations, Invoice, Purchase order of purchased goods and Materials for enrollment of the Green building certification.Cost is included with charges towards professional video recording & photo shoot of entire facility available in the premises. | 0 | 0 | 0 | 0
l | Partition | CARPENTRY AND INTERIOR WORKS | Charges towards the preparation of multiple options of proposed or dropped location/s recommended by regional project team (Jobs can not be more than 3 ) | 0 | 0 | 0 | 0
m | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing a desktop model of CO2 Monitoring Unit having CO2 | 0 | 0 | 0 | 0
n | Partition | CARPENTRY AND INTERIOR WORKS | Providing and placing medium size self watering ceramic planters (12 Inch) | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing & fixing Vinly Graphic Film of approved make | 0 | 0 | 0 | 0
|  |  | Cafeteria | 0 | 0 | 0 | 0
|  |  | EP wall | 0 | 0 | 0 | 0
|  |  | L wall | 0 | 0 | 0 | 0
|  |  | Conference Room | 0 | 0 | 0 | 0
|  |  | RM Area | 0 | 0 | 0 | 0
II | POP Punning | POP & FALSE CEILING WORKS | POP & FALSE CEILING WORKS | 0 | 0 | 0 | 0
1 | POP Punning | POP & FALSE CEILING WORKS | POP Punning | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Providing and applying Plaster of Paris punning to wall | 0 | 0 | 0 | 0
|  |  | Hub Room | 0 | 0 | 0 | 0
|  |  | Electric Panel | 0 | 0 | 0 | 0
|  |  | Graphic Wall | 0 | 0 | 0 | 0
|  |  | L wall | 0 | 0 | 0 | 0
|  |  | Less door | 0 | 0 | 0 | 0
|  |  | Store | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | RM | 0 | 0 | 0 | 0
|  |  | Deduction - Window | 0 | 0 | 0 | 0
|  |  | CH Cabin | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
2 | POP Punning | POP & FALSE CEILING WORKS | False Ceiling | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Gypsum board Ceiling - 12.5mm thk. single layer gypsum board | 0 | 0 | 0 | 0
|  |  | Branch | 0 | 0 | 0 | 0
|  |  | Lift Lobby Area | 0 | 0 | 0 | 0
|  |  | Vertical | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Lift Lobby | 0 | 0 | 0 | 0
|  |  | Lift Lobby | 0 | 0 | 0 | 0
|  |  | CH | 0 | 0 | 0 | 0
|  |  | CH Outside | 0 | 0 | 0 | 0
|  |  | Balcony Area | 0 | 0 | 0 | 0
|  |  | Conference Room | 0 | 0 | 0 | 0
|  |  | Deduction - Grid | 0 | 0 | 0 | 0
b | POP Punning | POP & FALSE CEILING WORKS | 600mm x 600mm Modular Grid Ceiling : | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Hub Room | 0 | 0 | 0 | 0
|  |  | Store | 0 | 0 | 0 | 0
|  |  | Antilobby | 0 | 0 | 0 | 0
|  |  | Ladies | 0 | 0 | 0 | 0
|  |  | Gents | 0 | 0 | 0 | 0
|  |  | Lift Lobby | 0 | 0 | 0 | 0
|  |  | Office Area | 0 | 0 | 0 | 0
|  |  | Near CH | 0 | 0 | 0 | 0
|  |  | CH | 0 | 0 | 0 | 0
|  |  | Conference Room | 0 | 0 | 0 | 0
|  |  | Column | 0 | 0 | 0 | 0
c | POP Punning | POP & FALSE CEILING WORKS | Providing rectangular Coves made up of Gypsum board | 0 | 0 | 0 | 0
III | Partition | CARPENTRY AND INTERIOR WORKS | CARPENTRY AND INTERIOR WORKS | 0 | 0 | 0 | 0
1 | Partition | CARPENTRY AND INTERIOR WORKS | Partition | 0 | 0 | 0 | 0
a | Partition | CARPENTRY AND INTERIOR WORKS | Solid Partitions | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing of full height solid partition | 0 | 0 | 0 | 0
|  |  | Conference Room | 0 | 0 | 0 | 0
|  |  | Deduction - Glazing | 0 | 0 | 0 | 0
|  |  | Storage | 0 | 0 | 0 | 0
|  |  | Deduction - Storage Area | 0 | 0 | 0 | 0
|  |  | CH | 0 | 0 | 0 | 0
|  |  | Deduction - Glazing | 0 | 0 | 0 | 0
|  |  | Deduction - Glazing | 0 | 0 | 0 | 0
|  |  | Façade | 0 | 0 | 0 | 0
|  |  | RM Side Façade | 0 | 0 | 0 | 0
b | Partition | CARPENTRY AND INTERIOR WORKS | Glazed Partitions | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | DORMA WC profile single glazed fixed partition for 12 mm toughened glass | 0 | 0 | 0 | 0
|  |  | Conference Room | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | CH Cabin | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Pantry Entry | 0 | 0 | 0 | 0
|  |  | Façade Road Side | 0 | 0 | 0 | 0
|  |  | Façade Near RM | 0 | 0 | 0 | 0
2 | Partition | CARPENTRY AND INTERIOR WORKS | Paneling Work | 0 | 0 | 0 | 0
a | Partition | CARPENTRY AND INTERIOR WORKS | Column / Wall Paneling | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | P/F paneling with Aluminium frame work of 18 gauge of size 50mm x 38mm | 0 | 0 | 0 | 0
|  |  | Electric Panel | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Office Entry | 0 | 0 | 0 | 0
|  |  | Deduction - Door | 0 | 0 | 0 | 0
|  |  | Portal | 0 | 0 | 0 | 0
|  |  | Portal Side | 0 | 0 | 0 | 0
|  |  | Deduction - Beam | 0 | 0 | 0 | 0
|  |  | Graphic Wall | 0 | 0 | 0 | 0
|  |  | Conference Room | 0 | 0 | 0 | 0
|  |  | Deduction - Window | 0 | 0 | 0 | 0
|  |  | Portal | 0 | 0 | 0 | 0
|  |  | Deduction - Window | 0 | 0 | 0 | 0
|  |  | Portal | 0 | 0 | 0 | 0
|  |  | CH | 0 | 0 | 0 | 0
|  |  | Balcony till RM | 0 | 0 | 0 | 0
|  |  | Top | 0 | 0 | 0 | 0
|  |  | Portal | 0 | 0 | 0 | 0
|  |  | Window Sides | 0 | 0 | 0 | 0
|  |  | Façade | 0 | 0 | 0 | 0
viii | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing 6mm thk back painted glass (extra clear glass) | 0 | 0 | 0 | 0
|  |  | Entry | 0 | 0 | 0 | 0
|  |  | RM Lobby | 0 | 0 | 0 | 0
|  |  | CH | 0 | 0 | 0 | 0
|  |  | Outside Conf | 0 | 0 | 0 | 0
|  |  | Conference Room | 0 | 0 | 0 | 0
4 | POP Punning | POP & FALSE CEILING WORKS | Doors | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Main Entrance and ATM door | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | Same as above but of size 1050 mm x 2400 mm , Floor Spring BTS 65 EN 1 - 4 | 0 | 0 | 0 | 0
|  |  | Office & Pantry | 0 | 0 | 0 | 0
b | POP Punning | POP & FALSE CEILING WORKS | Cabin and Meeting Room Doors | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Same as above but size of the door shall be 900mm x 2100mm | 0 | 0 | 0 | 0
|  |  | Conference room | 0 | 0 | 0 | 0
|  |  | CH cabin | 0 | 0 | 0 | 0
c | POP Punning | POP & FALSE CEILING WORKS | Doors for Server Room, Store Room, Pantry and Toilet. | 0 | 0 | 0 | 0
e | POP Punning | POP & FALSE CEILING WORKS | iii. Pantry door : 825mm x 2100mm | 0 | 0 | 0 | 0
|  |  | Store / Washroom Antilobby | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | same as item 4.c-(i) but with out vision panel for toilets and wash rooms. | 0 | 0 | 0 | 0
|  |  | Gents / Ladies | 0 | 0 | 0 | 0
d | POP Punning | POP & FALSE CEILING WORKS | Door Frames | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing architraves made out of rubber wood sections over door frames and finished with approved shade of duco paint finished. (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, paints) | 0 | 0 | 0 | 0
e | POP Punning | POP & FALSE CEILING WORKS | Server Room Door | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | approx size upto 1050 mm x 2100 mm (server room) | 0 | 0 | 0 | 0
5 | POP Punning | POP & FALSE CEILING WORKS | Tables | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Branch Manager's Table | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | CH cabin | 0 | 0 | 0 | 0
d | POP Punning | POP & FALSE CEILING WORKS | Running Counter, Linear Desks (WBO and back office) and Pantry Counter | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | RM Tables - 1200 mm width x 600 mm deep | 0 | 0 | 0 | 0
h | POP Punning | POP & FALSE CEILING WORKS | Meeting table | 0 | 0 | 0 | 0
iii | Partition | CARPENTRY AND INTERIOR WORKS | Same as above item no. 5.h.ii Conference room table having approximate size of table 2700mm x 1050mm. | 0 | 0 | 0 | 0
|  |  | Conference Room Table [24rft] - Additional Item | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Reprography Counter (Requirement to be rechecked with Project Manager at site before providing) | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Reprography Unit of Size :-725(H) x 750mm D | 0 | 0 | 0 | 0
|  |  | Office area | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
6 | Partition | CARPENTRY AND INTERIOR WORKS | Storages | 0 | 0 | 0 | 0
a | Partition | CARPENTRY AND INTERIOR WORKS | Full height storage units (use of BIFMA/Green Guard/ GPSC certified Storage Units) | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing 450mm deep full height storage unit ( 2100mm high) | 0 | 0 | 0 | 0
|  |  | HKC | 0 | 0 | 0 | 0
|  |  | Near CH | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
b | Partition | CARPENTRY AND INTERIOR WORKS | Low height storage units (BIFMA/Green Guard/ GPSC certified Storage Units) | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Storage top made of 25mm thk prelaminated particle board frosty white color | 0 | 0 | 0 | 0
|  |  | Cluster head | 0 | 0 | 0 | 0
|  |  | Conference area | 0 | 0 | 0 | 0
|  |  | Open Office | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
iii | Partition | CARPENTRY AND INTERIOR WORKS | Same as item 6.b-(i) above but overhead storage of approx. height 750mm. | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
c | Partition | CARPENTRY AND INTERIOR WORKS | Slotted Angle Racks | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Steel Slotted Angle Racks | 0 | 0 | 0 | 0
|  |  | Store | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
7 | Partition | CARPENTRY AND INTERIOR WORKS | Shutters | 0 | 0 | 0 | 0
a | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing shutters below pantry counter | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Basin | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
c | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing DB shutters | 0 | 0 | 0 | 0
|  |  | Electrical Panel | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
8 | Partition | CARPENTRY AND INTERIOR WORKS | Façade Treatment | 0 | 0 | 0 | 0
a | Partition | CARPENTRY AND INTERIOR WORKS | Aluminium Composite Panel | 0 | 0 | 0 | 0
i | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing tricolour (Silver - Red - Grey) Aluminium Composite Panels (ACP) | 0 | 0 | 0 | 0
|  |  | Shutter 1 | 0 | 0 | 0 | 0
|  |  | Shutter 2 | 0 | 0 | 0 | 0
|  |  | Elect Panel | 0 | 0 | 0 | 0
|  |  | External Façade | 0 | 0 | 0 | 0
9 | Partition | CARPENTRY AND INTERIOR WORKS | Railing | 0 | 0 | 0 | 0
a | Partition | CARPENTRY AND INTERIOR WORKS | SS Railing | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | Same as item 9.a-(i) above but providing only ss pipe of dia 50 mm on one side of the wall with necessary brackets at required intervals. | 0 | 0 | 0 | 0
|  |  | Staircase periphery | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
11 | POP Punning | POP & FALSE CEILING WORKS | Windows | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Supplying & fixing in position Aluminium extruder two track sliding windows | 0 | 0 | 0 | 0
|  |  | Lift Lobby | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
d | POP Punning | POP & FALSE CEILING WORKS | Louvered windows for toilet and pantry windows | 0 | 0 | 0 | 0
|  |  | Ladies | 0 | 0 | 0 | 0
|  |  | Gents | 0 | 0 | 0 | 0
12 | POP Punning | POP & FALSE CEILING WORKS | Miscellaneous | 0 | 0 | 0 | 0
a | POP Punning | POP & FALSE CEILING WORKS | Soft / Pinup Board | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing 12thk. Soft board | 0 | 0 | 0 | 0
|  |  | Office area | 0 | 0 | 0 | 0
|  |  | CH cabin | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
b | POP Punning | POP & FALSE CEILING WORKS | White Board | 0 | 0 | 0 | 0
iii | Partition | CARPENTRY AND INTERIOR WORKS | Providing and fixing 6mm thk back painted glass | 0 | 0 | 0 | 0
|  |  | Conference room | 0 | 0 | 0 | 0
|  |  | CH cabin | 0 | 0 | 0 | 0
c | Partition | CARPENTRY AND INTERIOR WORKS | Window Blinds | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | Supplying and fixing roller fabric blinds | 0 | 0 | 0 | 0
|  |  | RM Façade | 0 | 0 | 0 | 0
|  |  | Window | 0 | 0 | 0 | 0
|  |  | Conference room | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
d | POP Punning | POP & FALSE CEILING WORKS | Frosted Film | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing of frosted film on glass as per design - make 3M # 7725324 | 0 | 0 | 0 | 0
|  |  | Conference Room | 0 | 0 | 0 | 0
|  |  | CH Cabin | 0 | 0 | 0 | 0
|  |  | Pantry Entry | 0 | 0 | 0 | 0
|  |  | Façade Road Side | 0 | 0 | 0 | 0
|  |  | Façade Near RM | 0 | 0 | 0 | 0
|  |  | Pantry & Office Door | 0 | 0 | 0 | 0
e | POP Punning | POP & FALSE CEILING WORKS | Mirror for Toilets & Strong Room | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing flawless 6 mm thk. mirror of approved quality . | 0 | 0 | 0 | 0
|  |  | Gents | 0 | 0 | 0 | 0
|  |  | Ladies | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
h | POP Punning | POP & FALSE CEILING WORKS | Glass Shelves | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing 300 mm wide and 10 mm thick glass (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) shelves for momentos in Br. manager's cabin fixed with ss brackets. Size of each shelve. | 0 | 0 | 0 | 0
j | POP Punning | POP & FALSE CEILING WORKS | Plastic Board Signages | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing & fixing Steel signage SS 304 in Brush finish | 0 | 0 | 0 | 0
|  |  | IGBC / pantry/Store/Ladies/Gents/Elect/ Server | 0 | 0 | 0 | 0
n | POP Punning | POP & FALSE CEILING WORKS | Key Hanging Box | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Providing and fixing in place key hanging box of size 600mm x 675mm | 0 | 0 | 0 | 0
o | POP Punning | POP & FALSE CEILING WORKS | Aluminium Folding Step Ladder (A` type Self-supporting plate form ladder | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Ladder of height 8 feet (C section and steps on both sides) | 0 | 0 | 0 | 0
p | POP Punning | POP & FALSE CEILING WORKS | Miscellaneous work | 0 | 0 | 0 | 0
i | POP Punning | POP & FALSE CEILING WORKS | Fixing of internal marketing poster frames supplied by the bank. | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | Fixing of modular ATM drop box cum writing ledge supplied by the bank | 0 | 0 | 0 | 0
v | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Supply of carpenter on monthly basis | 0 | 0 | 0 | 0
viii | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and fixing 12 mm Chair / Corner Guard | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Gents | 0 | 0 | 0 | 0
|  |  | Ladies | 0 | 0 | 0 | 0
|  |  | Conference room - column | 0 | 0 | 0 | 0
|  |  | Conference room - glazed | 0 | 0 | 0 | 0
|  |  | Conference room - window | 0 | 0 | 0 | 0
|  |  | CH cabin | 0 | 0 | 0 | 0
|  |  | Lobby | 0 | 0 | 0 | 0
ix | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing Heavy Traffic Entrance Mattin 3M Nomad Terra 8150 Floor Mat | 0 | 0 | 0 | 0
x | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and placing foot operated Dry and Wet Dust made up of 100 % food grade and BPA Free plastice having 19 Liters capacity . Bin should have individual bin slot with removable buckets and covered with outer frame. ( Make : Nayasa or RAGA) (For Desk) | 0 | 0 | 0 | 0
xi | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and placing foot operated Dry and Wet Dust made up of 100 % food grade and BPA Free plastice having 33 Liters capacity . Bin should have individual bin slot with removable buckets and covered with outer frame. ( Make : Nayasa or RAGA) ( For Pantry ) | 0 | 0 | 0 | 0
xiii | ROLLING SHUTTER AND MS WORK | ROLLING SHUTTER AND MS WORK | Providing and placing 6 mm transparant acrylic glass for table top to avoid lnk / stamp marking on white laminated tops. (Basis rate of acrylic is 300 Rs./ Sq.ft) | 0 | 0 | 0 | 0
|  |  | Work stations | 0 | 0 | 0 | 0
|  |  | CH cabin | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
IV | PAINTING WORKS | PAINTING WORKS | PAINTING WORKS | 0 | 0 | 0 | 0
a | PAINTING WORKS | PAINTING WORKS | Paint on Walls | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Providing and applying desired paint luster finish to walls, of approved shade | 0 | 0 | 0 | 0
|  |  | Punning Qnty | 0 | 0 | 0 | 0
|  |  | Misc | 0 | 0 | 0 | 0
b | PAINTING WORKS | PAINTING WORKS | Acrylic Emulsion Paint on Ceiling | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Same as item (a) but applying acrylic emulsion paint on the ceiling | 0 | 0 | 0 | 0
|  |  | Gypsum Ceiling | 0 | 0 | 0 | 0
|  |  | Less Patta | 0 | 0 | 0 | 0
c | PAINTING WORKS | PAINTING WORKS | Synthetic Enamel Paint (over existing MS grilles, gates, shutters etc.) | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | Same as item (a) above but applying synthetic enamel paint to MS grilles, collapsible gates, rolling shutters etc. | 0 | 0 | 0 | 0
|  |  | RM Area | 0 | 0 | 0 | 0
|  |  | Conference room | 0 | 0 | 0 | 0
|  |  | Lift Lobby | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Pantry | 0 | 0 | 0 | 0
|  |  | Balcony | 0 | 0 | 0 | 0
|  |  | Washroom | 0 | 0 | 0 | 0
|  |  | Shutter | 0 | 0 | 0 | 0
d | PAINTING WORKS | PAINTING WORKS | Apex Paint | 0 | 0 | 0 | 0
i | PAINTING WORKS | PAINTING WORKS | The surface of wall or ceiling to be painted | 0 | 0 | 0 | 0
|  |  | Lobby | 0 | 0 | 0 | 0
|  |  | Column | 0 | 0 | 0 | 0
|  |  | Wall | 0 | 0 | 0 | 0
|  |  | Wall Around Lift Opp Side | 0 | 0 | 0 | 0
|  |  | Wall Around Lift | 0 | 0 | 0 | 0
|  |  | Wall Around Lift Opp Side near Office entry | 0 | 0 | 0 | 0
|  |  | Wall Around Lift | 0 | 0 | 0 | 0
|  |  | Ceiling Near Pantry | 0 | 0 | 0 | 0
|  |  | Ceiling Near Office | 0 | 0 | 0 | 0
|  |  | Balcony | 0 | 0 | 0 | 0
|  |  | Ceiling | 0 | 0 | 0 | 0
VI | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 : POWER DISTRIBUTION PANEL | 0 | 0 | 0 | 0
1.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | TYPE I PANEL - Main LT Panel (For 1500-2500 sq. ft) | 0 | 0 | 0 | 0
1.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Supply & Installation of Master Switch with Key comprising of Start and Stop Push Button with key control for Start and Stop complete in powder coated MS box near the entrance of the bank. By Switching off this master switch the entire electrical equipment (Except Critical Bus) in the branch will get switched off. This switch can be operated while closing the branch. We have excluded following load from Master switch : entire UPS Load, Signage, Server room and ATM room AC's, CCTV, emergency lights and any other critical loads if any as per the seperate critical bus mentioned in panels specification as above. | 0 | 0 | 0 | 0
|  |  | PART ‘1’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 : DISTRIBUTION BOARDS | 0 | 0 | 0 | 0
4.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing Lighting / UPS / Power Distribution Boards (Double Door) suitable for 415V, 50 Hz system. Dust and vermin proof having floor / wall mounting cubicle pattern with removable gland plates, with 1 set of 100 amps Copper Bus Bar, Earth and Neutral Link etc as required. | 0 | 0 | 0 | 0
|  |  | ALL MCBS SHALL BE "C" TYPE AND RATED AT 10kA | 0 | 0 | 0 | 0
4.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | UPS DB : | 0 | 0 | 0 | 0
4.1.1.a | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | For 3 Phase UPS | 0 | 0 | 0 | 0
4.1.3.b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | TPN, 8 Way (above 2500 Sq. ft area) | 0 | 0 | 0 | 0
4.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Lighting DB : | 0 | 0 | 0 | 0
4.1.4.b | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | TPN, 8 Way (above 2500 Sq. ft area) | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 5 : CABLES & TERMINATIONS | 0 | 0 | 0 | 0
5.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Supply , Installation of 1100V Grade PVC insulated , PVC sheathed GI wire armored Aluminium/ copper standard conductor , Cable of following sizes to be laid in on wall complete with dressing saddling clamping etc. Including civil work and required accessories. | 0 | 0 | 0 | 0
5.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3½ Core 70 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 0 | 0 | 0 | 0
|  |  | Panel to Near Meter Room | 0 | 0 | 0 | 0
5.1.11 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 4 sq.mm 1.1 KV Grade Copper Ar. Cable | 0 | 0 | 0 | 0
|  |  | Cassatte AC 1 | 0 | 0 | 0 | 0
|  |  | Cassatte AC 2 | 0 | 0 | 0 | 0
|  |  | Cassatte AC 3 | 0 | 0 | 0 | 0
|  |  | Cassatte AC 4 | 0 | 0 | 0 | 0
|  |  | Cassatte AC 5 | 0 | 0 | 0 | 0
5.1.15 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 16 sq.mm. copper flexible cable | 0 | 0 | 0 | 0
|  |  | UPS IN/ UPS DB/ UPS | 0 | 0 | 0 | 0
5.1.16 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 10 sq.mm. copper flexible cable | 0 | 0 | 0 | 0
|  |  | UPS DB To UPS | 0 | 0 | 0 | 0
|  |  | UPS DB To 1st Floor UPS DB | 0 | 0 | 0 | 0
|  |  | LD To Panel | 0 | 0 | 0 | 0
|  |  | PD To Panel | 0 | 0 | 0 | 0
5.2. | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | End termination of the following sizes of 1100V, Aluminium/copper (as per conductor), PVC insulated and sheathed armoured cables with single compression brass cable glands & crimping type Aluminum / Copper lugs, complete with all hardware etc. One end connection of a cable (with 3/4 core) to be consider as 1 end termination. | 0 | 0 | 0 | 0
5.2.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3½ Core 70 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 0 | 0 | 0 | 0
5.2.11 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 4 sq.mm 1.1 KV Grade Copper Ar. Cable | 0 | 0 | 0 | 0
5.2.15 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 16 sq.mm. copper flexible cable | 0 | 0 | 0 | 0
5.2.16 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 Core 10 sq.mm. copper flexible cable | 0 | 0 | 0 | 0
|  |  | PART ‘5’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 6 : CABLING FOR CCTV, PAS AND FAS | 0 | 0 | 0 | 0
6.1.6 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Providing and laying armoured Category 6 (CAT 6) cable for video transmission and to be fixed on ceilling & wall with MS clamps & clips at every 1 mtr distance. (Cost of clamps and clips included with the rates) Make : D-Link | 0 | 0 | 0 | 0
|  |  | Serevr To RM 1 | 0 | 0 | 0 | 0
|  |  | Serevr To RM 2 | 0 | 0 | 0 | 0
|  |  | Serevr To RM 3 | 0 | 0 | 0 | 0
|  |  | Serevr To RM 4 | 0 | 0 | 0 | 0
|  |  | Serevr To Main Entrance | 0 | 0 | 0 | 0
|  |  | Serevr To Pantry | 0 | 0 | 0 | 0
|  |  | Serevr To Server | 0 | 0 | 0 | 0
6.2.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 4 Core 1 sq.mm. shielded copper cable in 20 mm rigid PVC Conduit with its accessories such as PVC spacers, saddles, screws, bends, couplings etc. | 0 | 0 | 0 | 0
|  |  | CH Cabin Panic | 0 | 0 | 0 | 0
|  |  | Main Entrance MC | 0 | 0 | 0 | 0
|  |  | Patry Entrance MC | 0 | 0 | 0 | 0
|  |  | Hotter | 0 | 0 | 0 | 0
|  |  | Serevr Room Door Keypad | 0 | 0 | 0 | 0
6.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | FAS - Fire Alarm System | 0 | 0 | 0 | 0
6.4.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 Core X 1.5 Sqmm solid bare copper conductor, PVC insulated, Laid up, PVC sheathed, GI round wire armoured and overall FRLS RED colour PVS sheathed cable to IS 1554 Part I latest, Cable shall be cleated on ceiling, walls; laid on trays; concealed in timber partitions etc complete as directed and required to complete the installation. (For FAS) | 0 | 0 | 0 | 0
|  |  | SD 1 To SD 2 | 0 | 0 | 0 | 0
|  |  | SD 2 To SD 3 | 0 | 0 | 0 | 0
|  |  | RI | 0 | 0 | 0 | 0
|  |  | SD 3 To SD 4 | 0 | 0 | 0 | 0
|  |  | SD 4 To SD 5 | 0 | 0 | 0 | 0
|  |  | SD 5 To SD 6 | 0 | 0 | 0 | 0
|  |  | SD 6 To SD 7 | 0 | 0 | 0 | 0
|  |  | SD 7 To SD 8 | 0 | 0 | 0 | 0
|  |  | SD 8 To SD 9 | 0 | 0 | 0 | 0
|  |  | SD 9 To SD 10 | 0 | 0 | 0 | 0
|  |  | RI | 0 | 0 | 0 | 0
|  |  | SD 10 To SD 11 | 0 | 0 | 0 | 0
|  |  | SD 11 To SD 12 | 0 | 0 | 0 | 0
|  |  | SD 12 To SD 13 | 0 | 0 | 0 | 0
|  |  | RI | 0 | 0 | 0 | 0
|  |  | SD 13 To SD 14 | 0 | 0 | 0 | 0
|  |  | RI | 0 | 0 | 0 | 0
|  |  | HD | 0 | 0 | 0 | 0
|  |  | RI | 0 | 0 | 0 | 0
|  |  | SD 14 To SD 15 | 0 | 0 | 0 | 0
|  |  | SD 15 To SD 16 | 0 | 0 | 0 | 0
|  |  | Hotter 1 | 0 | 0 | 0 | 0
|  |  | Hotter 2 | 0 | 0 | 0 | 0
|  |  | Panel to 1 SD | 0 | 0 | 0 | 0
|  |  | PART ‘6’ TOTAL CARRIED TO SUMMARY | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 7 : EARTHING WORK | 0 | 0 | 0 | 0
7.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 core 10 sq.mm copper flexible cable for UPS earthing laid through the conduit. | 0 | 0 | 0 | 0
7.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 25 mm x 3 mm copper strip | 0 | 0 | 0 | 0
7.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Chemical Earthing: - Maintenance free Electrical Grounding system comprising of low carbon high tensile solid electrode of sufficient length (Not less than 2.5 Mtrs) with carbon based, combination of highly conductive material to achieve earth resistance less than 2 ohm. as confirming to IS : 3043-1987, Clause 9.2.8 and 9.3 : The material, selected for Earthing Electrode, and material used should be such that it resists the corrosion complete with CI cover (suitable for vehicular movement) and required masonry work. | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 9 : LIGHTING & POWER POINT WIRING | 0 | 0 | 0 | 0
9.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Primary Point : One Light Pt. controlled by one 6 Amps Switch (Point wiring including switches approx. 10 meters. Length) | 0 | 0 | 0 | 0
9.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Secondary light point: looped from primary light point. ( comprising of 3 nos. 1.5 sq.mm PVC ins. Copper cond. Wire in 20mm. Rigid PVC conduit pipe without switches) | 0 | 0 | 0 | 0
9.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Power Point Wiring : | 0 | 0 | 0 | 0
9.2.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 6 amps Light Plug Outlets :- | 0 | 0 | 0 | 0
9.2.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Exhaust Fan Outlet points :- Providing of 6 amps 3Pin socket near the exhaust Fan and switch with the light switch board, G.I / M.S Box for housing the above, complete with earthing with 1.5 sq.mm. PVC insulated copper conductor/wire. | 0 | 0 | 0 | 0
9.2.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 6/16 amps Power Plug Outlets :- Providing of 16 amps Modular type Socket and switch(multicountry type), Box for housing the above, Modular sheet, earthing the third pin with 2.5 sq.mm mm PVC Insulated Copper Conductor Wire, complete in all respects as required (Cost of wire /pipe/raceways is NOT to be included in this cost) | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 10 : POWER SOCKET & SWITCHES | 0 | 0 | 0 | 0
10.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 nos. of 5/15 A power sockets controlled by 1 no. of 15 A switch(multicountry sockets) | 0 | 0 | 0 | 0
10.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 1 nos. of 5/15A power socket controlled by 1 no. of 15 A switch(multicountry sockets) | 0 | 0 | 0 | 0
10.1.5 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 nos. of 5/15 A power sockets without switch for CCTV power Supply unit(multicountry sockets). | 0 | 0 | 0 | 0
10.1.7 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 nos. of 5/15 A power sockets controlled by 1 no. of 15 A switch (multicountry sockets for Display TV) Separate circuit for 3 nos of front side TV's to be provided. | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 11 : SUBMAINS CIRCUIT WIRING | 0 | 0 | 0 | 0
11.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Circuit Wiring (Light & Raw power points): Supply and laying of following sets of wires of PVC insulated , PVC sheathed copper flexible wires in laid PVC conduits Including civil work and required accessories spacers, clamps and hardware etc.(Cost of pipe/raceways is NOT to be included) | 0 | 0 | 0 | 0
11.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 8 meter wires) | 0 | 0 | 0 | 0
11.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 12 meter wires) | 0 | 0 | 0 | 0
11.1.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 18 meter wires) | 0 | 0 | 0 | 0
11.1.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 24 meter wires) | 0 | 0 | 0 | 0
11.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | AC Wiring: Supply and laying of following cables with fixed length mentioned cable should be PVC insulated , PVC sheathed copper flexible wires in laid PVC conduits Including civil work and required accessories spacers, clamps and hardware etc.(Cost of pipe/raceways is NOT to be included) | 0 | 0 | 0 | 0
11.2.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 12 meter wires) | 0 | 0 | 0 | 0
11.2.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 24 meter wires) | 0 | 0 | 0 | 0
11.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Computer / RAW Power Point Wiring: Supply & Installation of 3 core 2.5 sq.mm copper flexible PVC insulated sheathed wire 650V grade with ISI mark for connecting power points on work station in laid PVC conduits/raceways. One circuit wire should contains 2-3 UPS / Raw power points as least. (white colour- UPS and black colour:- RAW). (Cost of pipe/raceway is NOT to be included) | 0 | 0 | 0 | 0
11.3.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 core 2.5 sq.mm copper flexible cable ( set of 8 meter Length) | 0 | 0 | 0 | 0
11.3.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 core 2.5 sq.mm copper flexible cable ( set of 12 meter Length) | 0 | 0 | 0 | 0
11.3.3 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 core 2.5 sq.mm copper flexible cable ( set of 18 meter Length) | 0 | 0 | 0 | 0
11.3.4 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 3 core 2.5 sq.mm copper flexible cable ( set of 24 meter Length) | 0 | 0 | 0 | 0
PART- | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 12 : LIGHT FITTINGS,EXHAUST FANS ETC. | 0 | 0 | 0 | 0
12.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | LED Light fittings | 0 | 0 | 0 | 0
|  |  | LED light design should be such that LPD (lighting Power Density) should be below 0.6 W per Sq.ft. at 400 lux level on table top. | 0 | 0 | 0 | 0
12.1.1 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 600 x 600mm Recess mounting LED panel CRCA powder coated white housing, Slim, aesthetic CRCA powder coated bottom frame, out frame (If requires) Special translucent high transmissivity, non yellowing polycarbonate diffuser, High power, high efficiency LEDs ,Specially designed constant current driver. Lumen output should be 3000 to 4000. Wattage should be inclusive of LED and Driver losses. (cost is including outer frame if lights need to be placed in gypsum celing) | 0 | 0 | 0 | 0
|  |  | Color Temperature 5000-6000K | 0 | 0 | 0 | 0
i | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 35W - 40W | 0 | 0 | 0 | 0
12.1.2 | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | Circular recess mounted LED Down lighter High power, high efficiency Chip-On-Board LED module, High transitivity, non-yellowing PMMA diffuser, Pressure die cast aluminum housing and special, wave shaped radial heat sink, black powder coated, for superior thermal performance, Aesthetic white rim molded in engineering plastic, Specially designed, easy to install mounting clips. Lumen output should be 1000 to 1300 for 16 -18W, 700 - 1000 for 10 - 12W and 600 to 700 for 6 - 8W. Wattage should be inclusive of LED and Driver losses | 0 | 0 | 0 | 0
|  |  | Color Temperature 5000-6000K | 0 | 0 | 0 | 0
i | ELECTRIFICATION AND ALLIED WORKS | ELECTRIFICATION AND ALLIED WORKS | 16W - 18W | 0 | 0 | 0 | 0
ii | POP Punning | POP & FALSE CEILING WORKS | 20W | 0 | 0 | 0 | 0
12.1.8 | POP Punning | POP & FALSE CEILING WORKS | Supply & Installation of 225 mm single phase exhaust fans ( BEE Star rated Fans as suggested by Bank or CPC team as exception / Refer Make and Model sheet,fans) with mounting frame and safety grill etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan. | 0 | 0 | 0 | 0
12.1.10 | POP Punning | POP & FALSE CEILING WORKS | Supply & Installation of bracket fan 400 mm sweep, oscillating type with all fixing accessories, blades etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan. | 0 | 0 | 0 | 0
12.1.11 | POP Punning | POP & FALSE CEILING WORKS | Supply & Installation of pedestal fan 400 mm sweep, oscillating type with all fixing accessories, blades etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan | 0 | 0 | 0 | 0
PART- | POP Punning | POP & FALSE CEILING WORKS | 13 : RACEWAYS ,CONDUITS, CASSING-CAPPING | 0 | 0 | 0 | 0
13.2 | POP Punning | POP & FALSE CEILING WORKS | Supply & Installation of Floor Junction Boxes fabricated out of GI / M.S Sheet (Powder Coated) of the following sizes as required complete with 3mm Thick SS Sheet Cover as required. | 0 | 0 | 0 | 0
13.2.2 | POP Punning | POP & FALSE CEILING WORKS | 150 x 150 mm | 0 | 0 | 0 | 0
13.2.3 | POP Punning | POP & FALSE CEILING WORKS | 200 x 200 mm | 0 | 0 | 0 | 0
13.2.4 | POP Punning | POP & FALSE CEILING WORKS | 300 x 300 mm | 0 | 0 | 0 | 0
13.3 | POP Punning | POP & FALSE CEILING WORKS | Supply & Installation of totally concealed underfloor rigid PVC pipes of MMS gauge of following sizes. | 0 | 0 | 0 | 0
13.3.2 | POP Punning | POP & FALSE CEILING WORKS | 25 mm | 0 | 0 | 0 | 0
13.3.3 | POP Punning | POP & FALSE CEILING WORKS | 32 mm | 0 | 0 | 0 | 0
13.4 | POP Punning | POP & FALSE CEILING WORKS | Supply & Installation of the PVC casing capping over the wall, partition from junction box to power point | 0 | 0 | 0 | 0
13.4.1 | POP Punning | POP & FALSE CEILING WORKS | 25 mm | 0 | 0 | 0 | 0
13.4.2 | POP Punning | POP & FALSE CEILING WORKS | 50 mm | 0 | 0 | 0 | 0
PART- | POP Punning | POP & FALSE CEILING WORKS | 15 : MISCELLANEOUS WORK | 0 | 0 | 0 | 0
15.1 | POP Punning | POP & FALSE CEILING WORKS | Retaining one electrician at site till completion of IT installation and Branch launch activities. | 0 | 0 | 0 | 0
VII | Additional Work | Additional Work | ADDITIONAL WORK (As per site requirement and prior to PM confirmation ) | 0 | 0 | 0 | 0
1 | Additional Work | Additional Work | Chess Board | 0 | 0 | 0 | 0
2 | Additional Work | Additional Work | Dart Board | 0 | 0 | 0 | 0
3 | Additional Work | Additional Work | Conference Room Table | 0 | 0 | 0 | 0
4 | Additional Work | Additional Work | Pantry Table | 0 | 0 | 0 | 0
5 | Additional Work | Additional Work | Back Painted Glass Divider | 0 | 0 | 0 | 0
6 | Additional Work | Additional Work | HDMI Cable 1 | 0 | 0 | 0 | 0
7 | Additional Work | Additional Work | HDMI Cable 2 | 0 | 0 | 0 | 0
8 | Additional Work | Additional Work | LED Profile | 0 | 0 | 0 | 0
9 | Additional Work | Additional Work | Photo Frame | 0 | 0 | 0 | 0
10 | Additional Work | Additional Work | UPS DB (100 Amp 4P -1 Nos 63 AMP 2P x 3 nos) - Legrand | 0 | 0 | 0 | 0
11 | Additional Work | Additional Work | LED Tube 40 W - Philips | 0 | 0 | 0 | 0

## Summary Sheet
Sr. No | Particulars | Amount As per CWI | Rate per sq.feet
I | POP & FALSE CEILING WORKS | 1733162.56 | 760
II | CARPENTRY AND INTERIOR WORKS | 763801.48 | 335
III | PAINTING WORKS | 95319.01 | 42
IV | ROLLING SHUTTER AND MS WORK | 442709.8 | 194
V | ELECTRIFICATION AND ALLIED WORKS | 1576638.64 | 692
VI | Additional Work | 162810.6 | 71
Total | Total | 4774442.09 | 2094

## BOQ
|  | As per Work Order |  |  |  | As per CWI |  |  | Variance: CWI vs WO |  | Excess | Savings | Total | Remarks
Sr. No | Particulars | Qty | Unit | Rate | Amount | Qty | Round off | Amount | Qty. | Amount | Amount | Amount | Amount | Remarks
I | CIVIL & RELATED WORKS
1 | Demolition / Clearing Works
a | Dismantling/Demolishing the following and carting away the debris from the site and unloading at a approved location as per statutory rules and regulations.
i | Dismantling of existing brickwork |  | Sq.ft | 12 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Dismantling of existing dado tiles without plaster |  | Sq.ft | 11 | 0 | 932.39 | 932.39 | 10256.29 | 932.39 | 10256.29 | 10256.29 | 0 | 10256.29 | Quantity measured on best effort basis from photographs and layouts. PM confirmation required for whether items were executed on site and Qty not Present in WO.
iii | Dismantling of existing plaster |  | Sq.ft | 11 | 0 | 459.7317 | 459.73 | 5057.03 | 459.7317 | 5057.03 | 5057.03 | 0 | 5057.03 | Quantity measured on best effort basis from photographs and layouts. PM confirmation required for whether items were executed on site and Qty not Present in WO.
iv | Existing flooring including bedding material & PCC/IPS. |  | Sq.ft | 16 | 0 | 540.8335 | 540.83 | 8653.28 | 540.8335 | 8653.28 | 8653.28 | 0 | 8653.28 | Quantity measured on best effort basis from photographs and layouts. PM confirmation required for whether items were executed on site and Qty not Present in WO.
v | Existing Doors / Windows |  | Nos. | 381 | 0 | 16 | 16 | 6096 | 16 | 6096 | 6096 | 0 | 6096 | Quantity measured on best effort basis from photographs and layouts. PM confirmation required for whether items were executed on site and Qty not Present in WO.
vi | Dismantling of existing Sanitary wares & Plumbing Fittings |  | Nos. | 1199 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
vii | Existing Rolling Shutter , Safety door, collapsible door etc. |  | Sq.ft | 11 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
viii | Existing Electrical fittings and fixtures |  | Sq.ft | 3 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ix | Dismantling of existing wooden & aluminum partitions |  | Sq.ft | 10 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
x | Miscellaneous items such as false ceilings. |  | Sq.ft | 11 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
xi | Shifting /Dismantling existing furniture items (For renovation projects only) |  | Nos. | 487 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
xii | Dismantling of existing RCC 6 "/ 9" thk wall. |  | Sq.ft | 84 | 0 | 2 | 2 | 168 | 2 | 168 | 168 | 0 | 168 | Quantity measured on best effort basis from photographs and layouts. PM confirmation required for whether items were executed on site and Qty not Present in WO.
2 | Construction of Masonry Walls
a | Providing and erecting 115 mm thk , Half brick wall (first class bricks) in cement and sand mortar 1:3 with flush joint complete with material, labour, scaffolding, curing etc. The rate to include Appling chicken mesh at RCC to brickwork joints wherever required and RCC stiffener at every 1 meter intervals in 1:2:4 concrete. (Excluding plastering). The work to include cost for lintels / sills in RCC required for Doors , windows, openings etc. |  | Sq.ft | 114 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Same as 2(a) but 230mm thk ( Single brick wall) |  | Sq.ft | 150 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Do-do as 2(a) above but 100mm thk siporex / AAC / Aerocon / light weight block wall (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,aerocon blocks) |  | Sq.ft | 124 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Do-do as 2(a) above but 150mm thk siporex / AAC / Aerocon / light weight block wall (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,aerocon blocks) | 850 | Sq.ft | 129 | 109650 | 851.395 | 851.4 | 109830.6 | 1.395 | 180.6 | 180.6 | 0 | 180.6 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
3 | R.C.C Works
a | R.C.C work :Providing & casting in-situ reinforced cement concrete 225 mm thick for wall/columns/ as per details/ drawings/ design( The rate to include cost of re-baring/Hilti/drilling and joining with existing beam or lintel including shuttering, steel , concrete, inserts, cutout for ventilator, hacking, curing, bonding chemical / slurry all complete, design and certification from structural consultant. Grade of concrete to be considered shall be M25 & steel to be considered as 12mm dia tor steel @150mm c/c both way in two layers staggered by 75mm in both directions. The thickness of walls to be 225 mm without plaster. 300mm x300mm RCC column to be provided near the strong room door for mounting strong room door. |  | Sq.ft | 444 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Do-do as 3(a) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) |  | Sq.ft | 699 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Similar to above but for Floor slab with single layer of steel comprising 12mm dia @150 mm c/c and concrete jointing compound to be provided in case the premises is located on first floor and floor below does not belong to the bank. |  | Sq.ft | 198 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Do-do as 3(c) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) |  | Sq.ft | 330 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | Similar to above but for Floor slab with double layer of steel comprising of 12 mm dia @ 150 mm c/c Mesh on both ways staggered by 75mm and concrete jointing compound to be provided in case the premises is located on first floor and floor below does not belong to the bank. |  | Sq.ft | 336 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
f | Do-do as 3(f) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) |  | Sq.ft | 453 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
g | Similar to above but without concrete (ceiling reinforcement Mesh to be provided in case upper floor does not belong to the bank) |  | Sq.ft | 129 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
i | Do-do as 3(g) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) |  | Sq.ft | 389 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
j | Similar to item 3(c) i.e. 6mm MS plate instead of reinforcement mesh for wall cladding. Including necessary MS framework. Complete as directed. |  | Sq.ft | 468 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
k | Fixing in place of Strong Room Door by providing necessary grouting in the floor and proper support. The vendor should ensure that the door is fixed in plumb. |  | Job | 8559 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
l | Fixing in place of Ventilator by providing necessary grouting in the floor and proper support. The vendor should ensure that the door is fixed in plumb. |  | Job | 5720 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Plaster
a | P/A 1:4 cement plaster(Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement) with waterproofing compound to brick/RCC work including scaffolding in single coat of minimum 12 mm thick finished to receive Plaster of Paris levelling coat. | 2320 | Sq.ft | 46 | 106720 | 2317.1297 | 2317.13 | 106587.98 | -2.8703 | -132.02 | 0 | -132.02 | -132.02
b | External Plaster in 1:3 with waterproofing compound to brick/RCC work up to 25mm thk including cost of scaffolding up to 20'.( Prior approval of Bank required) (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement) |  | Sq.ft | 62 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Waterproofing treatment
a | Providing & appling water proofing treatement by Mixing and applying two coats of ready-to-use acrylic polymer based waterproofing component on modified cement base of approved make to a thickness of 2 mm over the bottom and sides of toilet and pantry slabs, including preparation of surface, finishing, curing etc. all complete at all levels as per manufacturer's specifications and as directed. | 380 | Sq.ft | 45 | 17100 | 285.0835 | 285.08 | 12828.6 | -94.9165 | -4271.4 | 0 | -4271.4 | -4271.4
6 | Brick Bat Coba
a | Proving and Laying brick bat coba up to 150mm thk in 1:4 cement mortar incl. of necessary slope towards nahni trap, over waterproofing course including finishing the top surface with water proofing compound to receive the floor tiles as per India Waterproofing Co. Measurements of floor area shall only be considered for said works.(Toilet area) | 140 | Sq.ft | 88 | 12320 | 109.2835 | 109.28 | 9616.64 | -30.7165 | -2703.36 | 0 | -2703.36 | -2703.36
7 | Plain Cement Concrete
a | P/E Plain cement concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) of grade M -10 ( 1:3:6 ) including shuttering for levelling course for flooring within the Bank Premise. The thickness may vary from 75mm to 125 mm as per requirement. (As per site condition - Prior approval of Bank required) | 100 | Sq.ft | 50 | 5000 | 534.5 | 534.5 | 26725 | 434.5 | 21725 | 21725 | 0 | 21725 | Quantity measured on best effort basis from photographs and layouts. PM confirmation required for Quantiy has exceeded WO Quantity
b | Same as 7(A) but for depth upto 250 mm |  | Sq.ft | 105 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Do-do as 7(a) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) |  | Sq.ft | 72 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Do-do as 7(b) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) |  | Sq.ft | 139 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | Similar to above but for exterior works (As per site condition - Prior approval of Bank required) |  | Sq.ft | 64 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
f | Do-do as 7(e) above but Ready mix concrete (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,RMC) |  | Sq.ft | 80 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
g | Providing and laying cement concrete flooring 40 - 50 mm thick , C.M. 1:3 laid to proper level and slope cost should including compaction as directed and curing complete in all respect. (As per site condition - Prior approval of Bank required)(Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) |  | Sq.ft | 38 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Drywall Panel
a | Providing and fixing of Solid Dry Wall Panel 75mm thick of size 2400/2700/3000mm in length and 600mm width certified by Green Building council having a unique tongue and groove jointing system. The panels are made of two fibre reinforced cement sheets enclosing a light weight aerated concrete core composed of cement, fly ash and other binders. Density is 720~780kg/cum, panel has Axial load carrying capacity min 83 KN/m with 2.5 times factor safety as per test method of ASTM -E-72:98 . These panels need to meet Uniformly distributed load (Bending load 80 -95kg/sqm & modulus of rupture 40-58kg/sqcm) as per test method ASTM-E-72:98 & IS 2380 Part 4. Thermal Conductivity typical K value - 0.17 ~0.21 W/m K, having a fire rating of 120 minutes as per BS 476 part 20-22 and sound transmission coefficient 36~40 as per IS 9901 (part 1) 1981 The wall panels to be installed with G.I Floor Channel : 14 x 75 x 25 mm size of 1 mm thick at bottom and 38 X75X 38 mm size with 1mm thickness at top. Tongue and Groove joints will be joined with elastomeric cementitious highly polymerized jointing compound as per manufacturer’s recommendation. Non-woven Self-adhesive glass fiber / fiber mesh tape in sufficient width to be applied to reinforce the exposed skin of jointing system. Jointing compound to be applied on joint finally to make good . Rate by the vendor to include scaffolding, lifting charges and jointing material, wastages etc. as a complete item of work excluding finishing etc. The installation will be done as per specification, drawing and as directed by EIC/consultant. All work to be done by certified installer with proper supervision following WMS and as per instruction of Engineering in charge. (Ideal for Server room , Solid Partition, Store rooms ) Approved Brands : HIL Limited , Visaka (Vnext) , Everest Panel) (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Aerocon Panel) |  | Sq.ft | 160 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Do-do as 8(a) above but 100mm thk (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Aerocon Panel) |  | Sq.ft | 254 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Flooring
a | Vitrified Tile Flooring
i | Vitrified Tile Flooring - Proving and Laying 1000mm x 1000mm / 800mm X 800 mm Vitrified floor tiles (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,vitrified floor tiles) over a 75 mm thk cement mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) bedding (1: 4) as per the design. The joints shall be kept up to 4 mm and filled with epoxy grouting of approved shade. (Basic cost of tile up to up to Rs. 110/-Sq. ft). | 2040 | Sq.ft | 152 | 310080 | 2009.7808 | 2009.78 | 305486.56 | -30.2192 | -4593.44 | 0 | -4593.44 | -4593.44
ii | Similar to above but for providing and fixing 75mm high skirting/border. |  | R.ft | 66 | 0 | 86.45 | 86.45 | 5705.7 | 86.45 | 5705.7 | 5705.7 | 0 | 5705.7 | Quantity executed on site and verified during audit but not present in work order
iii | Proving and Laying 600mm x 600mm anti-skid and Anti-dust Vitrified floor tiles for Toilet floors with a 75 mm thk cement mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) bedding (1: 4) as per the design including colour cement in joint to matching shade. The joints shall be kept as thin as possible should not exceeding 1 mm. (Basic cost of tile upto Rs. 60 /-Sq. ft). ( For server room, store, pantry, toilets ) (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, vitrified floor tiles) Somany : Delmon Beige - (600 x 600) | 1660 | Sq.ft | 102 | 169320 | 1359.3185 | 1359.32 | 138650.64 | -300.6815 | -30669.36 | 0 | -30669.36 | -30669.36
iv | Similar as 9_a_iii but for providing and fixing 75mm high skirting/border. | 100 | R.ft | 57 | 5700 | 129.89 | 129.89 | 7403.73 | 29.89 | 1703.73 | 1703.73 | 0 | 1703.73 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
b | Ceramic Tile Flooring
i | Proving and Laying of 300 mm x 300mm Ceramic floor tiles (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,ceramic tiles) (1st quality) of approved make over a 75 mm thk cement mortar (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) bedding (1: 4) as per the pattern given including colour cement joints in matching shade. Rate to include curing, acid wash, etc. complete. The joints shall be kept as thin as possible not exceeding 1 mm. (Basic cost of tile Rs. 35/- Sq. ft) |  | Sq.ft | 76 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Similar to above but for providing and fixing 3" high skirting/border. |  | R.ft | 38 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Granite Flooring
i | Supplying and laying 12 mm thk machine cut & machine polished Granite flooring , on a prefinished surface with 1:3 cement sand mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) .(Basic cost of granite Rs 180 /sq.ft). Rate shall be inclusive of machine polishing edges in case of protruding edges & groove if ordered. . Measurement for payment shall be as per laid area . |  | Sq.ft | 317 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Similar to above but 75mm high skirting/border. |  | R.ft | 128 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Vitrified Tiles in wooden finish (in HNW areas with prior approval)
i | Same as item 9.a-(i) but vitrified tiles in wooden finish. (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,vitrified floor tiles) (Basic cost of tile Rs.85/- per sq ft.) |  | Sq.ft | 122 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | Carpet Flooring (in HNW areas with prior approval)
i | Providing and laying carpet of 20 ounce loop pile in polypropylene in carpet tile (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,vitrified floor tiles)form without underlay. Cost also included surface preparation required for laying of it and carpet protection. ( Basic cost of tile Rs.160 /- per sq ft.) |  | Sq.ft | 152 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
f | Vinyl Flooring
i | Providing fixing Vinyl Anti-Static flooring 5 mm thick Armstrong/LG/Tusker installed on smooth, hard & absolutely levelled sub-floor. Brushed SS edges shall be used at the seams. Conductive adhesives shall be used for fixing . | 430 | Sq.ft | 105 | 45150 | 418.5164 | 418.52 | 43944.6 | -11.4836 | -1205.4 | 0 | -1205.4 | -1205.4
g | False Flooring
i | P/F Raised access floor (false floor app. 150 mm to 230 mm high) .The panel shall be finished with antistatic 600x600x1.5mm laminate laid on base panels with solvent free epoxy, edge shall have 0.6mm PVC lipping & floor shall have UDL of 10 KN/Sq.m point load of 2.5 | 80 | Sq.ft | 339 | 27120 | 73.3244 | 73.32 | 24855.48 | -6.6756 | -2264.52 | 0 | -2264.52 | -2264.52
ii | P/F Raised access floor (false floor app. 300 mm high) .The panel shall be finished with antistatic 600x600x1.5mm laminate laid on base panels with solvent free epoxy, edge shall have 0.6mm PVC lipping & floor shall have UDL of 10 KN/Sq.m point load of 2.5 |  | Sq.ft | 350 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
h | POP covering on Flooring
i | Providing and applying POP covering on flooring for floor protection with plastic sheet between the flooring and POP. The rate should include the cleaning of POP and plastic on completion before handing over completed site. |  | Sq.ft | 12 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Providing and applying covering on flooring for floor protection with Heavy duty bubble sheet on newly placed flooring. The rate should include the cleaning of plastic on completion before handing over completed site. | 2540 | Sq.ft | 12 | 30480 | 2049.088 | 2049.09 | 24589.08 | -490.912 | -5890.92 | 0 | -5890.92 | -5890.92
i | Wall Dado Tiles
i | Proving and Laying Ceramic glaze Wall Tiles (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) ( Colour : White ) of size 450mm x 300mm (1st quality) of somany make or approved make over a cement mortar bedding (1:4) (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) as per the pattern given including filling joint with colour cement in matching shade. (Basic cost of tiles Rs. 50/- Sq.ft). |  | Sq.ft | 76 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Proving and Laying wall dado Vitrified glaze tiles of size 600 mm X 600 mm (1st quality) of approved make over a cement mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) bedding (1:4) as per the pattern given including filling joint with colour cement in matching shade. (Basic cost of tiles upto Rs. 65/- Sq.ft). (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, wall tiles) Somany : Delmon Beige - (600 x 600) |  | Sq.ft | 99 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Pantry / Dining / Toilet Counter & Thresholds
a | Providing & fixing 600mm deep pantry counter made out of 12mm thk black granite supported by 25mm thk Kadappa to be fixed horizontally and vertically. The cost to be included of the platform to have 75mm wide granite fascia horizontally with molded edges as per design. 100mm high granite band over dado level to be provided. 75mm thk platform at floor level inside the counter should be provided finished with 75mm high granite skirting from outside The cost to include of making hole in the counter for fixing sink, End verticals to be fixed made of Kadappa and covered with granite to be provided as per the design. (Basic Cost of Granite 180/- sq.ft). Cost of Storage, CP fittings, SS sink are not included. | 20 | R.ft | 2796 | 55920 | 20 | 20 | 55920 | 0 | 0 | 0 | 0 | 0
b | Providing & Fixing Dining Counter with S.S Angle Bracket in approved Black Granite finish at ht. 750 mm from Finished Floor Level.(Depth of Counter 600 mm) (Basic Cost of Granite 180/- sq.ft) |  | R.ft | 1483 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Providing & fixing wash basin counter in Toilets of 600 mm Deep made of 12 mm thk black granite supported on 25thk Kadappa base. 75 mm wide granite facia to be provided at the edge of the counter. The cost to include of making hole in the counter for fixing wash basin, Cost of CP fittings, Wash basin are not included. (Basic Cost of Granite 180/- sq.ft) |  | R.ft | 1815 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Providing & Fixing of size 450mm X 900mm both sides polished divider for Urinal made of 12mm thk Black Granite embedded in the wall. The edges of the granite to be machine polished. | 2 | Nos. | 1716 | 3432 | 1 | 1 | 1716 | -1 | -1716 | 0 | -1716 | -1716
e | Providing & Laying 150mm wide Black Granite Threshold at ATM and Main Entrance. (Basic Cost of Granite 180/- sq.ft) | 20 | R.ft | 211 | 4220 | 29.41 | 29.41 | 6205.51 | 9.41 | 1985.51 | 1985.51 | 0 | 1985.51 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
f | Providing & Laying 75 mm wide Black Granite Threshold for Toilets & Pantry. (Basic Cost of Granite 180/- sq.ft) | 15 | R.ft | 177 | 2655 | 11.5 | 11.5 | 2035.5 | -3.5 | -619.5 | 0 | -619.5 | -619.5
11 | External Paving/Flooring/Window sill
a | Supplying and laying 20 mm thk glossy chequered tiles heavy duty external grade for paving on a prefinished surface with 1:3 cement (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) sand mortar over a 50 mm thk cement mortar bedding (1: 4) / PCC as per the design including colour cement float joints in matching shade. (Basic cost of tiles Rs.35 /- per sq. ft.) |  | Sq.ft | 91 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Providing and laying inter locking Paver blocks (heavy duty) in two or more shades by excavating the existing surface by @ 150mm to 230mm and providing layer for gravel over the entire area and covering the same with a layer of graded sand limestone, screeding / sinner to the required slope and providing primer locking pave blocks. The rate is inclusive of PCC (1:2:4) bed at the edges of the pattern as per site conditions. (Basic cost of tiles Rs.40 /- per sq. ft.) |  | Sq.ft | 98 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Providing and laying Kotah stone, flooring 25mm-30mm thk. Having sizes not less than 55cms x 55 cms in plain/ diamond pattern and bed of 1:6 cm including cement float filling joints with neat cement slurry, curing, polishing and clearing complete in all respect. (for strong room flooring) |  | Sq.ft | 110 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Treads & risers of steps. Providing and laying in required position polished granite slab 18mm thk with machine cut and machine polish in CM 1:3 for treads/ risers of steps. The rate is inclusive of full rounded nosing for treads and 3 no's groove on treads complete in all respect. ' The granite to be fixed with adhesive (approved Low VOC/No VOC Adhesives to be used by Bank or CPC team as exception / Refer Make and Model sheet, Adhesives) in case the same is to be fixed on a plywood surface. (Basic cost of Jet black granite Rs. 180/- sq.ft.) |  | Sq.ft | 314 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | Sill & jambs to windows / Doors. Providing and laying in required positions granite, slab 12 mm thk (Single piece), of approved make & colour with machine, cut and machine polish up to 145mm wide ; in cement mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) of 1:3 for sills and jambs of windows .The rate is inclusive of full rounded molding at the edges from inside. (Basic cost of granite Rs. 180/- sq.ft.) | 80 | R.ft | 194 | 15520 | 85.04 | 85.04 | 16497.76 | 5.04 | 977.76 | 977.76 | 0 | 977.76 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
f | Providing and laying jambs to door at required positions granite slab 12mm thk. Up to 2100mm in length (Double piece) and machine polish up to 145mm wide ; in cement mortar (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) of 1:3 for jambs of door .The rate is inclusive of fillet rounded molding at the edges from inside. (Basic cost of granite Rs. 180/- sq.ft.) | 70 | R.ft | 385 | 26950 | 84 | 84 | 32340 | 14 | 5390 | 5390 | 0 | 5390 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
g | Treads & risers of steps. Providing and laying in required position granite slab 12mm thk with machine cut and machine polish in 19 mm BWP Plywood (BWP Plywood which are "Free of Added Urea Formaldehyde" (required) approved by Bank or CPC team as exception / Refer Make and Model sheet, BWP Plywood) for treads/ risers of steps of internal staircase of branch. The rate is inclusive of full rounded nosing for treads and 3 no's groove on treads complete in all respect. ' The granite to be fixed with adhesive (approved Low VOC/No VOC Adhesives to be used by Bank or CPC team as exception / Refer Make and Model sheet, Adhesives) in case the same is to be fixed on a plywood surface. (Basic cost of granite Rs. 180/- sq.ft.) |  | Sq.ft | 396 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Façade Treatment
a | P/F 12mm thk Black Granite to be fixed with approved adhesive (approved Low VOC/No VOC Adhesives to be used by Bank or CPC team as exception / Refer Make and Model sheet, Adhesives) and curing on plywood base (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) paneling on the façade. (Cost of plywood paneling not included). (Basic cost of granite Rs. 180/- sq.ft.) |  | Sq.ft | 474 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Handicapped Access Ramp
a | Providing and constructing handicapped ramp at a slope of 1:12 or as per site conditions with raised floor to be made by filling dubber stone soling and compacted by sand dust & 1:4 cement mortar ( Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, cement) to match the required level. The width of ramp should be minimum upto 1200mm |  | R.ft | 1114 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Providing and constructing raised floor for staircase and midlanding by filling dubber stone soling and compacted by sand dust ,1:4 cement mortar (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) to match the required level. |  | Sq.ft | 271 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Ramp Finishes
a | Providing & fixing 100mm wide polished Black Granite Patti of 18mm thk on ramp for maintaining level difference in order to form anti-skid surface. |  | Sq.ft | 305 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Providing & fixing 12mm thk prepolished Black Granite flooring on staircase midlanding at Main Entrance as per approved quality laid to required pattern with cement mortar of required thickness. Joints shall be finished with epoxy based grouting compound. Rate shall be inclusive of Cutting of slab, wastage etc. basic rate of granite delivered at site ( Basic cost of granite Rs.145/- per sq.ft. ) |  | Sq.ft | 345 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Plumbing
a | Internal concealed plumbing works for water supply, drainage and related works per toilet comprising of wash basin, WC, urinals etc. all complete. Gents Toilet (1 no Urinal + 1 nos. wash basin + 1 no EWC) | 1 | Lumpsum per toilet | 11441 | 11441 | 1.25 | 1.25 | 14301.25 | 0.25 | 2860.25 | 2860.25 | 0 | 2860.25 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
b | Internal concealed plumbing works for water supply, drainage and related works per toilet comprising of wash basin, WC etc. all complete. Ladies Toilet (1 Wash Basin + 1 EWC) | 1 | Lumpsum per toilet | 11017 | 11017 | 1 | 1 | 11017 | 0 | 0 | 0 | 0 | 0
c | Supply fixing and installation of heavy duty 20/15 mm Concealed stop cocks ( Make Jaguar Continental Series ) to be provided only at the entry point of plumbing lines within the toilets / pantry | 1 | Nos. | 2012 | 2012 | 1 | 1 | 2012 | 0 | 0 | 0 | 0 | 0
d | Internal Plumbing work for Pantry. Water supply and drainage points for sink, water supply point to water purifier and proper drain point. | 2 | Lumpsum | 6073 | 12146 | 1 | 1 | 6073 | -1 | -6073 | 0 | -6073 | -6073
e | Supply & fixing of Nahani trap ( Make : Nathani , Seko ) with Stainless Steel Chili trap mesh on it. | 5 | Nos. | 1207 | 6035 | 4 | 4 | 4828 | -1 | -1207 | 0 | -1207 | -1207
f | Providing and fixing machanical driven industrial grade water meter made up of solid brass and should have multi jet, anti corrosion and sedimentation free features for horizontal flow of approved make (Make : Kranti , Everest and approved by CPC as expectional basis) | 1 | Nos. | 3919 | 3919 | 1 | 1 | 3919 | 0 | 0 | 0 | 0 | 0
16 | Sanitary wares (Pure white colour)
a | Providing and fixing first quality European Water closet with attached cisten of Dual Flush Cistern of flow rates of 4/2 LPF approved by bank or CPC team as exception/ Refer make and model sheet, water closet cost is including flush tank, seat cover, connection pipe, chair bracket and All complete as per design and specifications. | 2 | Nos. | 14831 | 29662 | 2 | 2 | 29662 | 0 | 0 | 0 | 0 | 0
b | Same as above 16(a) wall hung EWC but with dual Flush Valves for Flow of 25 mm with flush valve of flow rates of 4/2 LPF approved by bank or CPC team as exception/ Refer make and model sheet. |  | Nos. | 15305 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Providing and fixing of single Urinal with electronic Flushing system (large flat back type) (flow rates of max upto 1.5 LPF approved by bank or CPC team as exception/ Refer make and model sheet, urinal) including all connection pipe , necessary brackets, urinal spreader, dome grating All complete as per design and specifications. |  | Nos. | 11059 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Providing and fixing of single Urinal pressmatic Flushing system (large flat back type) (flow rates of max upto 1.5 LPF approved by bank or CPC team as exception/ Refer make and model sheet, urinal) including all urinal valve with auto closing system (Pressmatic taps), connection pipe , necessary brackets, urinal spreader, dome grating All complete as per design and specifications. | 2 | Nos. | 7627 | 15254 | 2 | 2 | 15254 | 0 | 0 | 0 | 0 | 0
e | Providing and fixing under/ Over counter Wash Basin of approved shape (make model as approved by bank or CPC team as exception ). including waste coupling, brackets & connection pipe etc. all required to complete the work and make it functional. All complete as per design and specifications. | 4 | Nos. | 7203 | 28812 | 4 | 4 | 28812 | 0 | 0 | 0 | 0 | 0
f | Same as above 15(c) but half Pedestal Wash Basin |  | Nos. | 7398 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
g | Similar to above but in divider plate (make model as approved by bank or CPC team as exception ) |  | Nos. | 2118 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
h | Providing and fixing Pantry staintless steel sink of size 18" x 16" (make and model as approved by bank or CPC team as exception). cost including waste coupling & connection pipe etc. all required to complete the work and make it functional. All complete as per design and specifications. | 1 | Nos. | 7013 | 7013 | 0 | 0 | 0 | -1 | -7013 | 0 | -7013 | -7013
17 | Plumbing Fittings
a | Providing and fixing heavy duty pillar cock for pantry manufactured by (Pillar Cock with water flow rate or Aerators (flow Restrictors) restricting flow rate upto 3 LPM @ 3 Bar Pressure, approved by bank or CPC team as exception/ Refer make and model sheet, Pillar cock, Aerators) all complete as per standard specifications and as directed by the CPC. | 1 | Nos. | 1716 | 1716 | 0 | 0 | 0 | -1 | -1716 | 0 | -1716 | -1716
b | Providing and fixing angular stopcock manufactured by (make & model as approved by bank or CPC team as exception) 15 mm dia. all complete as per standard specifications and as directed by CPC | 8 | Nos. | 1222 | 9776 | 6 | 6 | 7332 | -2 | -2444 | 0 | -2444 | -2444
c | Providing and fixing heavy duty 15 mm dia C.P. brass short body bibcock (two in one) of approved manufacturer (Bib Cock with water flow rate or Aerators (flow Restrictors) restricting flow rate upto 3 LPM @ 3 Bar Pressure, approved by bank or CPC team as exception/ Refer make and model sheet,two way bib cock) all complete as per standard specifications and as directed by the in - Charge. | 2 | Nos. | 2008 | 4016 | 2 | 2 | 4016 | 0 | 0 | 0 | 0 | 0
d | providing and fixing of heavy duty bottle trap. (Make & model as approved by bank or CPC team as exception). | 6 | Nos. | 1716 | 10296 | 4 | 4 | 6864 | -2 | -3432 | 0 | -3432 | -3432
e | Providing and fixing heavy duty pillar cock auto closing system (Pressmatic taps) for washbasins manufactured by (Pillar Cock with water flow rate or Aerators (flow Restrictors) restricting flow rate upto 3 LPM @ 3 Bar Pressure, approved by bank or CPC team as exception/ Refer make and model sheet, Pillar cock) all complete as per standard specifications and as directed by the CPC | 4 | Nos. | 2309 | 9236 | 4 | 4 | 9236 | 0 | 0 | 0 | 0 | 0
f | Providing and fixing heavy duty sensor pillar cock (Automatic taps) for washbasins manufactured by (Pillar Cock with water flow rate or Aerators (flow Restrictors) restricting flow rate upto 3 LPM @ 3 Bar Pressure, approved by bank or CPC team as exception/ Refer make and model sheet, Pillar cock) all complete as per standard specifications and as directed by the CPC |  | Nos. | 10000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
g | Providing and fixing aerators Shower Flow Aerator (Spray) to lavatory faucets and kitchen faucets with 21mm dia (For Lavatory Faucets - Flow rate restricted to 3 LPM @ 3 Bar Pressure and for Kitchen Faucet - Flow rate restricted to 3.8 LPM @ 3 Bar Pressure. Make & model as approved by bank or CPC team as exception/ refer make and model sheet, Aerators) | 8 | Nos. | 228 | 1824 | 0 | 0 | 0 | -8 | -1824 | 0 | -1824 | -1824
h | Providing and fixing hand type Jet Spray with adjustable nozzle and push type valve and inlet flexible water connection in the toilet manufactured by M/s. Jaguar continental series or as approved by bank or CPC team | 2 | Nos. | 1716 | 3432 | 2 | 2 | 3432 | 0 | 0 | 0 | 0 | 0
18 | Toilet Accessories
a | Supplying of disposable Soap Dispenser of make as approved by bank or CPC team | 5 | Nos. | 1207 | 6035 | 4 | 4 | 4828 | -1 | -1207 | 0 | -1207 | -1207
b | Supply & fixing of Toilet paper holder of make as approved by bank or CPC team | 5 | Nos. | 762 | 3810 | 2 | 2 | 1524 | -3 | -2286 | 0 | -2286 | -2286
c | Supply & fixing of SS finish Robe Hooks of make as approved by bank or CPC team | 3 | Nos. | 495 | 1485 | 2 | 2 | 990 | -1 | -495 | 0 | -495 | -495
d | CP brass towel ring make as approved by bank or CPC team | 5 | Nos. | 805 | 4025 | 4 | 4 | 3220 | -1 | -805 | 0 | -805 | -805
19 | External plumbing works.
a | Providing & laying CPVC pipes with screwed sockets, joints, and necessary pvc fittings such as socket, elbows, bends, tees etc., including making/ drilling holes in walls/ slabs and remaking good the damages in original conditions. The rate is inclusive of necessary scaffolding ( Make : Astral / Precision )
i | 15mm dia |  | R.ft | 94 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | 20mm dia |  | R.ft | 106 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iii | 25mmdia | 25 | R.ft | 131 | 3275 | 5 | 5 | 655 | -20 | -2620 | 0 | -2620 | -2620
iv | 40mmdia |  | R.ft | 150 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Supplying and fixing of PVC Pipe of SWR Grade of approved company including all necessary fitting fixed with GI Clamp making necessary holes in valets, refilling the same with concrete making good the damaged portions with matching plaster complete in all respects. The rate is inclusive of scaffolding. ( Make : Astral / Precision )
i | 2" dia |  | R.ft | 93 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | 4" dia | 25 | R.ft | 156 | 3900 | 30 | 30 | 4680 | 5 | 780 | 780 | 0 | 780 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
iii | 6" dia |  | R.ft | 159 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Providing and fixing CI pipe (heavy duty ) for soil, waste, vent, of approved company with required fittings such as junctions, bends, bowl fixed with GI clamps filling the joints of pipe in cement including making necessary holes in walls, refilling the same with concrete making good the damaged portion with matching plaster, complete with 3 coats of oil paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade. The rate is inclusive of necessary scaffolding.
i | 4 " dia |  | R.ft | 805 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Providing and laying 150mm dia salt glazed stoneware pipes in proper gradient on cement concrete bedding or bricks over compacted soil & including fittings such as bends, single or double junctions, laying, jointing in CM (1:1) including excavation and filling the trench
i | 4 " dia |  | R.ft | 141 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | 6" dia |  | R.ft | 152 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | Providing and fixing 23cm x 23cm salt glazed stone ware gutty trap in cm (1:4:8) outside the building including connecting salt glazed stone ware pipes and mount out of brick masonry finished with cement plaster from inside & out side covered with CI/RCC cover. Complete in all respect. |  | Nos. | 2966 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
f | Providing & constructing brick masonry chamber of size: 2'-0" x 1'-0" & 1-0" to 1'-6" in depth including 6" thk CC (1:4:8) foundation, CC (1:2:4) channels, brick masonry and in CM (1:6) & 20mm thk. plastering from inside and out side in CM (1:3) , providing CI / RCC cover (heavy duty ) with necessary arrangement for lifting. |  | Nos. | 6356 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Anti Termite Treatment
a | Carrying out Eco - Friendly Pest control and ant-termite treatment by appointing specialized agency ( Agency : PCI / Hi-care)* for the premises with one year guarantee. Mode of measurement shall be on carpet area. A certificate of guarantee to be submitted by the vendor along with hand over document. ( * In case PCI / Hi-care do not have reach to particular location vendor to share credentials of pest control vendor with CPC for approvals ) | 2540 | Sq.ft | 18 | 45720 | 2280 | 2280 | 41040 | -260 | -4680 | 0 | -4680 | -4680
21 | Miscellaneous civil work
a | Chasing work in the existing brick/siporex up to 200mm wide and max to 75mm deep, for installation of A.C. copper pipes/drain pipes as required and Making finished surfaces with 1:4 cement mortar (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section), for portions of wall where chasing is done after laying drainage pipes and refrigerant pipes all complete including making good, closing and finishing of holes/openings in walls. | 30 | R.ft | 72 | 2160 | 0 | 0 | 0 | -30 | -2160 | 0 | -2160 | -2160
b | Trenching work as per width and depth required. Making finished surfaces with 1:4 cement mortar (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet,cement section) , portions of floor where trenching is done for laying Raceways for Electrical, Data and Voice cables all complete.(Chasing should be avoided in floors, it should be done only if no alternative is availaible). | 100 | R.ft | 132 | 13200 | 190 | 190 | 25080 | 90 | 11880 | 11880 | 0 | 11880 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
c | Making punctures in existing brick/siporex block up to 200mm diameter, for passing A.C. copper pipes/drain pipes as required and making good the same with cement plaster/POP. | 5 | Nos. | 320 | 1600 | 1 | 1 | 320 | -4 | -1280 | 0 | -1280 | -1280
d | Vendor should provide D.G. set during execution of site while power cut issues remote location. Opex cost, Diesel is included with hireing charges. |  | Per Day | 5525 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | Filling charges of Diesel in installed D.G. set by Bank (Vendor should submit diesel bill during final billing) | 1 | Lumpsum | 17161 | 17161 | 0 | 0 | 0 | -1 | -17161 | 0 | -17161 | -17161
f | Civil & interior vendor will be responsible for securing the premises till the site is ready for IT hand-over with proper locking mechanism or till project is handed over to Project manager. (Daily 12 hour shift ) | 1 | Per month Basis | 19068 | 19068 | 0 | 0 | 0 | -1 | -19068 | 0 | -19068 | -19068
g | TOILET CUBICLES - Provide and fix Toilet cubicles bottom mounted made of high pressure compressed color boards with all necessary mount fittings for fixed panels. Panels to be 300mm above finished floor with door size of 650 x 1750mm Rate to include all necessary hardware's and fittings including door locks with vacant/occupied signage locks. mode of measurement L x H Approved brand Greenlam. Shop drawings to be approved by Architect. | 40 | Sq.ft | 823 | 32920 | 34.5 | 34.5 | 28393.5 | -5.5 | -4526.5 | 0 | -4526.5 | -4526.5
h | Providing and making Core cut of in RCC slab / Beam of thickness up to 300mm, with core cutting machine inclusive of filling of core with fire retardant sealant of HILTI make as per the manufacturer's specification, cleaning etc complete. Note: The contractor should determine the location of beams/post tensioned tendons before carrying out the operation, getting prior approval from the builder/structural consultant and cutting all reinforcement by gas cutting machine or as directed etc. complete. (wherever required) | 0 | Nos. | 104 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
i | Upto 75mm dia | 2 | Nos. | 1695 | 3390 | 0 | 0 | 0 | -2 | -3390 | 0 | -3390 | -3390
ii | Upto 100mm dia | 2 | Nos. | 2067 | 4134 | 0 | 0 | 0 | -2 | -4134 | 0 | -4134 | -4134
iii | Upto 150mm dia | 2 | Nos. | 2584 | 5168 | 1 | 1 | 2584 | -1 | -2584 | 0 | -2584 | -2584
i | Providing, fixing and Removing MS H type frame scaffolding for branch interior and exterior work. Scafolding should have flat working platform. | 100 | Sq.ft | 76 | 7600 | 350 | 350 | 26600 | 250 | 19000 | 19000 | 0 | 19000 | Quantity measured on best effort basis from photographs and layouts. PM confirmation required for Quantiy has exceeded WO Quantity
j | Providing and fixing a 1000 Lits over head watertank at branchs cost is including with necessary ball cock operated inlet connection and NRC valve output connection, internal connection and entire conncection should have emergency stop cock on inlet and outlet line. |  | Nos. | 15255 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
k | Prepare and maintain document list, Technical cut sheet, All type of layout, Electrical based calculations, Invoice, Purchase order of purchased goods and Materials for enrollment of the Green building certification.Cost is included with charges towards professional video recording & photo shoot of entire facility available in the premises. | 1 | Lumpsum | 15560 | 15560 | 1 | 1 | 15560 | 0 | 0 | 0 | 0 | 0 | Quantity not measureable during audit, PM confirmation required if these items should be added to the bill and Qty not Present in the WO
l | Charges towards the preparation of multiple options of proposed or dropped location/s recommended by regional project team (Jobs can not be more than 3 ) | 1 | Job | 10212 | 10212 | 1 | 1 | 10212 | 0 | 0 | 0 | 0 | 0 | Quantity not measureable during audit, PM confirmation required if these items should be added to the bill and Qty not Present in the WO
m | Providing and fixing a desktop model of CO2 Monitoring Unit having CO2 Detection Range: 400-5000PPM , Sensitivity: 1PPM , AC / DC operated. | 3 | Nos. | 11441 | 34323 | 3 | 3 | 34323 | 0 | 0 | 0 | 0 | 0
n | Providing and placing medium size self watering ceramic planters (12 Inch)with plant of given list of Botanical (Areca palm / Mother in law’s tongue/ Lady Palm/ Janet Craig / Dragon Tree / Warneckii or Dracanaenai / Spider Plant / Money plant) Cost including plantation , soil and fertilizers. ( Max 15 Planters to be place in branch). | 30 | Nos. | 1296 | 38880 | 30 | 30 | 38880 | 0 | 0 | 0 | 0 | 0
i | Providing & fixing Vinly Graphic Film of approved make, with recommended adhesive(Low VOC/No VOC Adhesives as suggested by Bank or CPC team as exception / Refer Make and Model sheet,adhesives) of approved make & sample as per manufacturer's specifications. Rate of Wall Graphics film shall be inclusive of Image cost. | 550 | Sq.ft. | 211 | 116050 | 461.5876 | 461.59 | 97395.49 | -88.4124 | -18654.51 | 0 | -18654.51 | -18654.51
| Total Cost of Civil & related works |  |  |  | 1504620 |  |  | 1444213.22 |  | -60406.78 | 102419.15 | -162825.93 | -60406.78
II | POP & FALSE CEILING WORKS
1 | POP Punning
a | Providing and applying Plaster of Paris punning to wall of average thickness 12mm to18mm thk to existing wall surfaces to achieve smooth surface in true level and plumb complete as directed. The rate to include cost for making grooves up to 12mm thick if required in horizontal or vertical direction near doors, windows, skirting (use Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Gypsum Plaster) | 1050 | Sq.ft | 28 | 29400 | 1047.1893 | 1047.19 | 29321.32 | -2.8107 | -78.68 | 0 | -78.68 | -78.68
2 | False Ceiling
a | Gypsum board Ceiling - 12.5mm thk. single layer gypsum board fixed on suspended G.I. tubular channels as per manufacturers' specifications, including jointing, finishing with gypsum compound, jointing tape and top coat. The surface shall up be duly sanded and finished. Rate shall include cost of marking as/ reflected ceiling plan and making all the necessary cutouts for lights, grills, diffusers etc. The rate shall also include providing perimeter channel for grills, lights, diffusers as called for in HVAC and Electrical Drawings. The rate shall also include providing for edge/ angle bits at all corners, necessary taping, filling with jointing compound as per manufacturers specifications. The rate shall be exclusive of trap door which shall be paid for separately. (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Gypsum Ceiling) | 300 | Sq.ft | 76 | 22800 | 528.89 | 528.89 | 40195.64 | 228.89 | 17395.64 | 17395.64 | 0 | 17395.64 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
b | 600mm x 600mm Modular Grid Ceiling (providing and fixing modular ceiling systems (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Modular Ceiling) with mineral fibre board ceiling tiles as per following specifications, rate to include all fastening accessories with approved finishes. Fire retardant tiles of size 600mm x 600mm x 15mm thick of approved colour and type with acoustical property of 0.7 NRC. (Armstrong / USG Boral) Suspension shall be as per manufacturer specific stitched, sillhouette reveal profile grid system with 15mm wide flanges incorporating 6mm central recess colour (all black reveal). Sillhouette main runners and cross tees to have metered ends (bird's mouth or manufacturer specific) and profiled notches to provide cruciform junctions. The perimeter runners should have the shadow edge detail forming a uniform groove (minimum 6mm) between the vertical partition / panelling / wall and the modular false ceiling grid as per detail drawing. | 2360 | Sq.ft | 114 | 269040 | 1917.9425 | 1917.94 | 218645.16 | -442.0575 | -50394.84 | 0 | -50394.84 | -50394.84
c | Providing rectangular Coves made up of Gypsum board (Green Pro certified Gypsum Board and make approved by Bank or CPC team as exception / Refer Make and Model sheet, gypsum board) upto a size of 450 mm height and 100 mm facia and including the cost of additional frameworks and overlap , verticals and other necessary requirement (Prior approval of Bank required) | 30 | R.ft | 96 | 2880 | 72 | 72 | 6912 | 42 | 4032 | 4032 | 0 | 4032 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
3 | Trap Doors
a | Providing and fixing trap doors for access to the areas above false ceiling. The trap door shall have an external frame made of 50mm x 50 mm in good quality seasoned wood scantling on which the shutter is hinged. Shutter shall be made of 19mm thk ply and finished with 1.0mm thick laminate externally and enamel paint (using paints with Low VOC/ No VOC approved by bank or CPC team as exception/ Refer make and model sheet, Paints - Applicable only if painted at site) internally. Concealed heavy duty hinges shall be used to mount the shutters and locking shall be provided with panel locks. The shutter shall be molded in level with the false ceiling forming a groove all around. Sufficient number of hinges and locks shall be provided to avoid sagging of the shutter. Key also shall be supplied for opening the shutter. No extra rate shall be provided for suspenders or frame works around for linking the trap door to gypsum board false ceiling. (Green Pro certified make approved by bank or CPC team as exception/ Refer make and model sheet, Gypsum Ceiling) |  | Sq.ft | 398 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Same as item above but trap door shutters to be of Lay - in type. |  | Sq.ft | 411 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Providing and fixing modular trap doors for access to the areas above false ceiling having size 1200 mm x 600 mm ( Make Knauf ) |  | Nos. | 6780 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Cost of POP and False Ceiling Work |  |  |  | 324120 |  |  | 295074.12 |  | -29045.88 | 21427.64 | -50473.52 | -29045.88
III | CARPENTRY AND INTERIOR WORKS
1 | Partition
a | Solid Partitions
i | Providing and fixing of full height solid partition made with Aluminum framework of 20 gauge of size 50 mm x 50mm fixed @600mm c/c both ways and covered with 9mm thk BWR plywood (Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished with 1.0mm thk laminate of approved shade. 75 mm wide aluminium skirting is to be provided. Cost to include wooden inserts of sal-wood at the door opening for fixing of floor spring pivot etc. (The measurements will be taken from flooring to bottom of false ceiling) ( Basic cost of laminate up to Rs. 45/- Per sq.ft) | 120 | Sq.ft | 462 | 55440 | 325.3562 | 325.36 | 150316.32 | 205.3562 | 94876.32 | 94876.32 | 0 | 94876.32 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
ii | Portion of the partition above the ceiling level to be made of Aluminum framework of 20 gauge of size 50 mm x 50mm. And covered from one side with 12.5 mm thick gypsum board of ( Green Pro certified Gypsum Board and make approved by Bank or CPC team as exception / Refer Make and Model sheet, gypsum board) specified Make.(The measurements will be taken from bottom of false ceiling up to slab bottom) | 80 | Sq.ft | 131 | 10480 |  | 0 | 0 | -80 | -10480 | 0 | -10480 | -10480
iii | Same as item 1.a-(i) above but partition framework to be covered with one side BRW plywood (Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) of 9mm thickness finished with 1.0mm thick laminate and other side with gypsum of 12.5mm thickness finished with 3 coats of luster paint (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, paints) of approved shade. 75 mm wide aluminium skirting is to be provided. (The measurements will be taken from flooring to bottom of false ceiling) ( Basic cost of laminate up to Rs. 45/- Per sq.ft) |  | Sq.ft | 380 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iv | Same as item 1.a-(i) but partition framework to be covered with both side gypsum board (Green Pro certified Gypsum Board and make approved by Bank or CPC team as exception / Refer Make and Model sheet, gypsum board) of 12.5mm thickness with 3 coats of luster paint (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, paints) of approved shade |  | Sq.ft | 340 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
v | Providing and fixing of full height solid partition made with Aluminum framework of 20 gauge of size 50 mm x 38mm fixed @600mm c/c both ways and covered with 12 mm thk Fire rated plywood (Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Fire rated Plywood) and finished with 1.0mm thk laminate of approved shade. 75 mm wide aluminium skirting is to be provided. Cost to include inserts of stainless steel at the door opening for fixing of floor spring pivot etc. Rate shall be inclusive of Glass Wool Rate shall include filling all cutouts using Acrylic Firestop Sealant Hilti CP 606. |  | Sq.ft | 543 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Glazed Partitions
i | Glazing profile (size: 26mm x 32mm) single glazed fixed partition for 12 mm toughened glass Complete systems (Entrance Partition & BM Cabin) Sap Code : EAPS- 1032 - WCP With Cover - 12mm - Non safety Profile for 12mm Glass Aluminum S.S Finish 3MTR W.C.P End Cap H Profile 12mm glass to glass 180 deg Stock Length 3000mm with 3M Adhesive (approved Low VOC/No VOC Adhesives to be used by Bank or CPC team as exception / Refer Make and Model sheet, Adhesives) Finish EV 101 Glass 12 mm Tuff Clear Crystal Edge Polished with cut out and Holes Silicon Seal Clear - Dow / Wacker S.S Screw for Fixing Metal / Wooden 38mm x 6mm CSK Philip Head with Plastic Anchor Grip | 680 | Sq.ft | 434 | 295120 | 517.4222 | 517.42 | 224560.28 | -162.5778 | -70559.72 | 0 | -70559.72 | -70559.72
ii | Providing & fixing of Semi glazed partitions solid upto 4'0" ht The solid portion of the partitions is made by using the Al. frame work of size 50mm x 50mm fixed @600mm c/c bothways covered with 9mm thick BWR plywood (Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (optional) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished with 1.0mm thick laminate of approved shade. Glazing profile (size: 26mm x 32mm) single glazed fixed partition for 12 mm toughened glass Complete systems (Entrance Partition & BM Cabin) Sap Code : EAPS- 1032 - WCP With Cover - 12mm - Non safety Profile for 12mm Glass Aluminum S.S Finish 3MTR W.C.P End Cap H Profile 12mm glass to glass 180 deg Stock Length 3000mm with 3M Adhesive (approved Low VOC/No VOC Adhesives to be used by Bank or CPC team as exception / Refer Make and Model sheet, Adhesives) Finish EV 101 Glass 12 mm Tuff Clear Crystal Edge Polished with cut out and Holes Silicon Seal Clear - Dow / Wacker S.S Screw for Fixing Metal / Wooden 38mm x 6mm CSK Philip Head with Plastic Anchor Grip |  | Sq.ft | 442 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Low Height Solid Partition
i | Same as item 1.a-(i) but low height solid partition up to 1200 mm height. The partition framework to be covered with 12mm thick BWR plywood ( Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished with 1.0mm thick laminate. Wooden trim of size 75mm x 12mm made of Teak wood to be provided at the edge of the partition finished with approved shade of laminate and 75 mm wide aluminium skirting is to be provided. |  | Sq.ft | 408 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Providing and fixing of 55 mm thick Low ht Modular partition up to 1200 mm height. The partition framework to be covered with 12mm thick partical board and finished with 1.0mm thick laminate. Powder coated trim of size 75mm x 12mm made of aluminium profile to be provided at the edge of the partition finished with approved shade of coating and 75 mm wide aluminium skirting is to be provided. |  | Sq.ft | 434 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Low Height Semi Solid Partition
i | Same as item 1.c-(i) above but low height solid partition to have 12mm thick clear float glass (Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) of 300mm high fixed by way of ss brackets . The glass edges to be machine Polished and rounded at the corner. |  | Sq.ft | 427 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Paneling Work
a | Column / Wall Paneling
i | P/f paneling of 12mm thick BWP plywood (BWP Plywood which are "Free of Added Urea Formaldehyde" (required) make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWP Plywood) fixed on leveled wall and finished with 1.00mm thk. laminate of approved Make and shade , on all exposed surfaces on all exposed surfaces as per details, cost should also include molding made out of 25 mm x 12 mm teak wood of at the top and side edge of the paneling finished with 2 mm thk PVC edge banding tap and 75 mm wide aluminium skirting is to be provided. |  | Sq.ft | 275 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | P/F paneling with Aluminium frame work of 20 gauge of size 50 mm x 38mm with 600mm c/c covered by 12mm thick BWP plywood (BWP Plywood which are "Free of Added Urea Formaldehyde" (required) make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWP Plywood) fixed on frame and finished with 1.00mm thk laminate having 25 mm x 12 mm teak wood of at the top and side edge of the paneling finished with 2 mm thk PVC edge banding tap and 75 mm wide aluminium skirting is to be provided. | 800 | Sq.ft | 351 | 280800 | 989.0292 | 989.03 | 347149.53 | 189.0292 | 66349.53 | 66349.53 | 0 | 66349.53 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
iii | same as item 2.a-(ii) above covered with 12.5mm gypsum board (Green Pro certified Gypsum Board and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Gypsum Board) and finished with 3 coats of approved shade of luster paint. (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) |  | Sq.ft | 177 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iv | Same as above 2.a-(i) but with 12 mm thick bison board and finished with 1 mm thk laminate of approved shade. |  | Sq.ft | 211 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
v | Same as above 2.a-(ii) but with 12 mm thick bison board and finished with 1 mm thk laminate of approved shade. |  | Sq.ft | 275 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
vi | same as item 2.a-(i) above but with 12mm thick bison board finished with 3 coats of approved shade of luster paint. (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) |  | Sq.ft | 182 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
vii | same as item 2.a-(ii) above but with 12mm thick bison board finished with 3 coats of approved shade of luster paint.(Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) |  | Sq.ft | 261 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
viii | Providing and fixing 6mm thk back painted glass (extra clear glass) (Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) as per approved shade on 6mm thk MDF (exterior grade only) backing for partitions/walls as per design and detail drawing. The glass should be glued to the MDF backing using 3M double tape. cost is including 8mm width aluminium hat section in to the grooves between ply paneling / back painted glass | 480 | Sq.ft | 442 | 212160 | 513.064 | 513.06 | 226772.52 | 33.064 | 14612.52 | 14612.52 | 0 | 14612.52 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
3 | Plywood Boxing
a | P/f BOXING FOR ROLLING SHUTTER up to 600mm wide x 600mm high with open able panels for accessing rolling shutter made of Salwood internal framework and 19mm thk plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) finished with 1.0mm thk laminate of approved shade on all exposed surfaces including boxing top. Openable panel for accessing the rolling shutter to be provided .Rate to include cutouts for lights, necessary hardware, etc., all complete. (surface area will be measured for the purpose of billing) |  | Sq.ft | 288 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | P/f wooden boxing for covering AC Piping, windows with Aluminium frame work of 20 gauge of size 25 mm x 25 mm with 600mm c/c internal framework and covered with by 12mm thick BWP plywood (use BWP Plywood which are "Free of Added Urea Formaldehyde" (required) make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWP Plywood) finished with 1.0mm thk laminate of approved shade on all exposed surfaces including boxing top.(surface area will be measured for the purpose of billing) |  | Sq.ft | 244 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | P/f wooden boxing for covering AC Piping, windows with Aluminium frame work of 20 gauge of size 25 mm x 25 mm with 600mm c/c internal framework and covered with by 12mm thick BWP plywood (use BWP Plywood which are "Free of Added Urea Formaldehyde" (required) make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWP Plywood) finished with 3 coats of paints (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade on all exposed surfaces including boxing top.(surface area will be measured for the purpose of billing) |  | Sq.ft | 244 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Doors
a | Main Entrance and ATM door
i | Providing and fixing in place main entrance single leaf toughen glass ( Make : Sain Globain , Modi and Asashi )door for branch and ATM of overall size of 1050mm x 2100 mm. Rate is Tobe include cost of heavy duty floor spring of approved Make and model, ss handle of size 450 mm, mortise lock), necessary patches and all required hardware complete as directed. |  | Nos. | 22035 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Providing and fixing in place main entrance single leaf toughen glass ( Make : Saint Gobin, Asashi)door for branch and ATM of overall size of 1050mm x 2400 mm. Rate is Tobe include cost of heavy duty floor spring (Make : Enox/Ozone), ss handle of size 450 mm, mortise lock), necessary patches ( Make : Enox/Ozone)and all required hardware complete as directed. | 2 | Nos. | 24789 | 49578 | 2 | 2 | 49578 | 0 | 0 | 0 | 0 | 0
iii | Extra for providing and fixing Enox/Ozone Make floor spring of 120 kg capacity ( only in the case of existing doors ) |  | Nos. | 6568 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Cabin and Meeting Room Doors
i | Same as item no.4.a-(i) above but size of the door shall be 900mm x 2100mm |  | Nos. | 20975 | 0 | 2 | 2 | 41950 | 2 | 41950 | 41950 | 0 | 41950 | Quantity executed on site and verified during audit but not present in work order
ii | Same as item no.4.a-(ii) above but size of the door shall be 900mm x 2400mm | 2 | Nos. | 21505 | 43010 |  | 0 | 0 | -2 | -43010 | 0 | -43010 | -43010
c | Doors for Server Room, Store Room, Pantry and Toilet.
i | Providing & fixing Solid Flush Door of 38mm thickness in laminate finish on both sides With Vision Panel of size 300mm x 300mm made of 6mm thk glass (Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) for Server, Teller, store and Pantry. Door to be mounted on hinges and heavy duty door closer to be provided including Handles & necessary hardware fittings ( All hardware Make : Enox/Ozone ). the sizes of the doors to be considered as under:
a | i. server room door : 975mm x 2100mm |  | Nos. | 14259 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | i. server room door : 975mm x 2400mm |  | Nos. | 15664 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | ii. Teller and store room door : 900mm x 2100mm |  | Nos. | 13884 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | ii. Teller and store room door : 900mm x 2400mm |  | Nos. | 15664 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | iii. Pantry door : 825mm x 2100mm |  | Nos. | 13136 | 0 | 3 | 3 | 39408 | 3 | 39408 | 39408 | 0 | 39408 | Quantity executed on site and verified during audit but not present in work order
f | iii. Pantry door : 825mm x 2400mm | 3 | Nos. | 15255 | 45765 |  | 0 | 0 | -3 | -45765 | 0 | -45765 | -45765
ii | same as item 4.c-(i) but with out vision panel for toilets and wash rooms. The size of the door to be 825mm x 2100mm | 2 | Nos. | 12994 | 25988 | 2 | 2 | 25988 | 0 | 0 | 0 | 0 | 0
iii | P/f. solid wicket gate door of size 675mm x 900mm made of 38mm thick flush door and mounted on heavy duty soft closing hinges and with locking arrangement for Welcome Desk. |  | Nos. | 5169 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Door Frames
i | Providing and fixing including necessary civil work door frames made out of salwood section of size 100mm x 75mm including providing 3 nos. anchor hold fasts, applying black jaipan paint (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, paints) on the surface of the frame touching the edge of the wall. The frames to be finished with 1.0 mm thick laminate or paint (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade.
i | i. Server room frame: as per door size mentioned in item no.4.c-(a) above | 1 | Nos. | 3432 | 3432 | 1 | 1 | 3432 | 0 | 0 | 0 | 0 | 0
b | ii. Server room frame: as per door size mentioned in item no.4.c-(b) above |  | Nos. | 3432 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | iii. Teller room door/ Store room door : as per door size mentioned in item no. 4.c-(c) above |  | Nos. | 3432 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | iv. Teller room door/ Store room door : as per door size mentioned in item no. 4.c-(d) above |  | Nos. | 3432 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | iv. Pantry door : as per door size mentioned in item no. 4.c-(e) above |  | Nos. | 3432 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
f | iv. Pantry door : as per door size mentioned in item no. 4.c-(f) above |  | Nos. | 3432 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | Server Room Door
i | Wooden Fire Rated Door - Supply and Installation of 2hrs Fire Rated Wooden Doors 45 mm thk. (Single shutter) along with door frame with approved SS ball bearing hinges (CE Marked). Fire Rated doors to be manufactured with internal stiles and rails of tropical hardwoods, kiln seasoned and chemically treated under vacuum pressure with suitable wood preservatives having antiseptic and Fire Retardant properties in a pressure vessel. The construction is sandwich type infill material of Cera Wool Blanket and Calcium Silicate boards of required thickness for 2hour Fire Rated Door). The sandwich construction is further bonded with LEED Rated LEED Rated Ply wood on both sides which is waterproof and bonded with Phenol Formaldehyde Synthetic Resin. The doors are further given an external timber lipping of 6.5mm thickness in which intumescent strips are affixed which impart expansion properties to the door to seal them against fire / smoke escaping to the adjoining areas. Concealed door closer ITS 96 shall be used. The Fire Rated doors should achieve the criteria of STABILITY, INTEGRITY & THERMAL INSULATION PROPERTIES as per the standards laid down in BS 476”. The door frame and shutter shall be finished as per detail drgs. Skinning of the door (both side) Fire rated laminate make shall be considered. Fire and Smoke Seal Strips of size 10mm x 4mm mounted in the grooves in the shutter on all sides except bottom. Intumescent sealant is used to seal the gaps of approved make. All Test reports and warranties/guarantee to be taken from manufacturer and submitted to engineer in charge before installation. Approved Make: Kenwood / Promat Rate to be inclusive of all hardwares and vision panels in fire rated glass of size as per drgs. approx size upto 1050 mm x 2100 mm (server room) | 1 | Nos. | 47602 | 47602 | 1 | 1 | 47602 | 0 | 0 | 0 | 0 | 0
5 | Tables
NOTE : First drawer at each workstation must have shelves for segregating currency notes pens/staplers / stamps etc.)Drawer at each workstation to divided in 2 equal parts by a horizontal partition and the front partition among these to be divided into 3 equal partitions by vertical partitions.(As per 5S requirement) Modular furniture makes should have BIFMA / Green Guard / Green Pro Certification and approved by bank or CPC team as exception (Refer make and model sheet)
a | Branch Manager's Table
i | Providing and fixing in place, branch manager's table of size 1575mm x 675mm(worktop size)comprising of 25mm thick table top made of medium density particle board with side credenza of size 400mm deep and 900mm long having sliding shutters with locks ( Make : Ebco ) and a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high Density particle board. The table top to have post form edge. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware .( Make : Ebco) all the external surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with 0.8 mm thick laminate of approved shade. all complete as directed.( All furniture hardware should be Ebco Make ) | 1 | Nos. | 28249 | 28249 | 1 | 1 | 28249 | 0 | 0 | 0 | 0 | 0
ii | same as item 5.a - i but table of size 1425 x 675mm.(worktop size). |  | Nos. | 25340 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | P.B./RM worktables
i | Providing and fixing in place, Personal manager's table of size 1350 x 675mm.(worktop size)comprising of 25mm thick table top made of medium density particle board with side credenza of size 400mm deep and 900mm long having sliding shutters with locks ( Make : Ebco )and a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board.. The table top to have post form edge. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware. all the external surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with 0.8 mm thick laminate of approved shade. all complete as directed.( All furniture hardware should be Ebco Make ) |  | Nos. | 25213 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | same as item 5(a) above but size of the worktable to be 1200mm x 675mm with side credenza having two nos. top drawers and openable shutters below and without drawer pedestal. |  | Nos. | 20128 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iii | same as item 5(a) above but size of the worktable to be 1200mm x 675mm with drawer pedestal and without side credenza. |  | Nos. | 20488 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | RM's worktables in HNW area (cockpit type)
i | Providing and fixing cockpit type workstation of average size of 1500mm x 1500mm comprising of 25mm thick table top having post form edge. 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware. All the exposed surfaces to be finished with 1.0mm thick laminate and internal surfaces with 0.8mm thick laminate. ( All furniture hardware should be Ebco Make ) |  | Nos. | 22458 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Same as item 5.c-(i) above but of size 1425mm x 1425mm. |  | Nos. | 20340 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Running Counter, Linear Desks (WBO and back office) and Pantry Counter
i | Providing and fixing in place 600mm deep running counter made of medium density particle board with post form edge profile for 25mm thick table top, Consisting of a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware.All the exposed surfaces to be finished with 1.0mm thick laminate.( All furniture hardware should be Ebco Make ) | 19 | Nos. | 16568 | 314792 | 21 | 21 | 347928 | 2 | 33136 | 33136 | 0 | 33136 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
ii | Back Office Tables -1200mm width x 600 mm x750mm deep Free Standing Table top made of 25mm thk prelaminated particle board of approved color laminate with front longer edge having post form dome type head with alumminium access flap with soft closing mechanism. Understructure shall have Square looped legs with min size of section 46mm x45mmx 1.2 mm thk made of MS Extrusion duly powder coated . It is fitted with M8x 25mm Dome shape leveller to have better look & it's size should be matching to leg pipe size. Front Apron wooden Modesty of 18mm prelaminated twin laminated shall be fixed with minfix with metal leg .The ht. of modesty is 700mm All wiring mecahnism /swith plates are to be mounted on below access flap with vertical/horizontal post to carry wires from junction post heavy duty keyboard Tray made of MS duly powder coated with wrist pad 3 Drawer wooden fixed pedestal of size 700mm ht x 380mm w x 450mm D. Pedestal should be opened with single Key & all drawers & doors shall have no handles Entire body except back is made of 18mm prelaminated board of approved color, & back is in 9mm white All Facia vetical edges shall have reverse waterfall edge in such a way for easy finger grip to user & shall have no external handle. Cost of soft Pin board cum writing board dividor inclusive with cost . |  | Nos. | 17043 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iii | same as item 5.d-(i) above but made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) All the External & internal surfaces to be laminated Polished. |  | Nos. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iv | Providing and fixing lunch counter with top made up of 19 mm ply, fascia and brackets in 12 mm thick ply and finished with 1 mm thick laminate on top, bottom and facia Complete as directed. |  | R.ft | 1268 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | Welcome Desk
i | Providing and fixing welcome desk consisting of two worktops (laminate and glass/granite) with a cabinet to house FRFC made of 19mm thick BWR plywood top, sides finished in 1.0mm thick laminate of approved shade. The table shall have a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board. with key boards and CPU stand complete with all hardware etc. all the exposed edges to have wooden lipping stained to match the laminate and Melaminee finished. all the internal surfaces to be hand Melamine Polished. ( All furniture hardware should be Ebco Make ) |  | Nos. | 24336 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Providing and fixing double set welcome desk consisting of two worktops (laminate and Glass (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass)) with a common cabinet to house FRFC made of 19mm thick BWR plywood top, sides finished in 1.0mm thick laminate of approved shade. The table shall have a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board, with key boards and CPU stand complete with all hardware etc. all the exposed edges to have wooden lipping stained to match the laminate and Melaminee finished. all the internal surfaces to be hand Melamine Polished. ( All furniture hardware should be Ebco Make ) |  | Nos. | 37247 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
f | Teller Counter
i | P/f Double level teller counter made out of 19mm thick plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished in laminate one at 750mm and other at 1200mm level. Top level counter to be finished in jet black granite with double molding. The upper most worktop to have vertical barriers in form of 8 mm thick toughen glass mounted on ss finish fabricated brackets for cash transactions. Teller to be provided with 4 nos. equal sized drawers, one key board at every 1200mm length. There should be a vertical barrier separating the adjacent counter at every 1200mm length. All the exposed surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with hand Melamine Polish. all 5 S compliances as per bank's requirements to be followed. ( All furniture hardware should be Ebco Make ) |  | R.ft | 3813 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
g | Demat Counter
i | Same as item 5.f-(i) above but without glass partition. |  | R.ft | 3203 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
h | Meeting table
i | Providing and fixing meeting room table made out of 12mm thick glass (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) table top of size up to 900mm dia. Glass edges to have machine cut. The base of the table to be made of Powder coated MS base finished with approved shade of PU paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) and finished . Glass to be fixed to the base with PVC vacuum holders. |  | Nos. | 12757 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Providing and fixing in place conference room table for 10 persons made out of 19mm thick plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) finished with 1.0mm thick laminate externally and hand Melamine Polish internally. Provision to be 8 module POP Up box of Ebco made for wire management on the table top as per design. (All furniture hardware should be Ebco Make ) |  | Nos. | 32035 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iii | Same as 5.h.ii but for 8 persons |  | Nos. | 21738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
iv | Same as 5.h.ii but for 12 persons |  | Nos. | 32035 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
v | Same as 5.h.ii but for 16 persons | 1 | Nos. | 43476 | 43476 |  | 0 | 0 | -1 | -43476 | 0 | -43476 | -43476
i | Reprography Counter (Requirement to be rechecked with Project Manager at site before providing)
i | Providing and fixing low height storage cabinet for Reprography Counter of height 600mm and depth 750mm made of 19mm plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) with drawers on top and shutters below. All the exposed surfaces to be finished with 1.0mm thick laminate and internal surfaces to be hand Melamine Polished. | 10 | Sq.ft | 889 | 8890 | 10 | 10 | 8890 | 0 | 0 | 0 | 0 | 0
J | Gold loan desk / Table
| Gold Loan Desk - 1985 mm width x 675 mm deep (with Flap door & Front Toughened Glass with SS Stud) Providing and fixing in place, Gold loan manager's table of 1985 mm width x 675 mm deep (worktop size)comprising of 25mm thick table top made of medium density particle board with side credenza of size 400mm deep and 900mm long having sliding shutters with locks ( Make : Ebco ) and a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board. The table top to have post form edge. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware .( Make : Ebco) all the external surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with 0.8 mm thick laminate of approved shade. all complete as directed.( All furniture hardware should be Ebco Make ) All Facia vetical edges shall have postformed reverse waterfall edge in such a way for easy finger grip to user & shall have no external handle. (Above Table 12mm toughned Glass Fix with SS Stud 40x40x450/600 mm ) SS stud can be locally fabricated( as per attached image) or equivalent of model- Kich DT32-1-G12 which will require holes in toughened glass |  | Nos. | 26696 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Storages
a | Full height storage units (use of BIFMA/Green Guard/ GPSC certified Storage Units)
i | Providing and fixing 450mm deep full height storage unit made of 19mm thick plywood/HD particle board and finished with 1.0mm thick laminate externally and internally. Shutter made of 19mm thick plywood/ Particle board to be provided finished with 1.0mm thick laminate internally and externally. Intermediate shelves made of 19mm thick plywood (Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) to provided at every 400mm (as per size of box file/office file) finished with white 0.8 mm laminate. The exposed edges of the shelves should have post form edges All complete including necessary hardware, heavy duty hinges, handles, locks etc. ( All furniture hardware should be Ebco Make ) | 20 | Sq.ft | 779 | 15580 | 38.5 | 38.5 | 29991.5 | 18.5 | 14411.5 | 14411.5 | 0 | 14411.5 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
b | Low height storage units (BIFMA/Green Guard/ GPSC certified Storage Units)
i | Providing and fixing 450mm deep Low height storage unit (Upto 1050 mm high) made of 19mm thick plywood/Particle board and finished with 1.0mm thick laminate externally and internally. Openable shutter made of 19mm thick plywood to be provided finished with 1.0mm thick laminate internally and externally. Intermediate shelves made of 19mm thick plywood to provided (as per size of box file/office file) finished with 1 mm laminate. The exposed edges of the shelves should have post form edges All complete including necessary hardware, heavy duty hinges, handles, locks etc. ( All furniture hardware should be Ebco Make )(use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) | 130 | Sq.ft | 610 | 79300 | 103.84 | 103.84 | 63342.4 | -26.16 | -15957.6 | 0 | -15957.6 | -15957.6
ii | same as item 6.b-(i) above but shutters of the storage to be made sliding with locking arrangement. (Specifically for BM Cabin) |  | Sq.ft | 610 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iii | Same as item 6.b-(i) above but overhead storage of approx. height 750mm. | 15 | Sq.ft | 678 | 10170 | 0 | 0 | 0 | -15 | -10170 | 0 | -10170 | -10170
iv | Providing and fixing wall mounted storage rack for DVR having front side opened and all the sides closed with 19mm thick BWR plywood. All the external surfaces to be finished with 1.0mm thick laminate and internal surfaces Tobe finished with hand Melamine Polish. Aluminium ventilation grille to be provided on either sides of the storage rack. size of the rack W 600mm x H 530mm x D 400mm (Requirement to be confirmed by Bank before providing) (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood |  | Nos. | 3856 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
v | A 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood/high density particle board. (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) |  | Nos. | 2669 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Slotted Angle Racks
i | Steel Slotted Angle Racks Open Type of size 1829 H x 915 W x 260 D mm of 14 gauge thick with 6 panels of 18 gauge thick making 5 compartments with 3 sides covered by cladding sheet of 22 gauge thick with required bolts and nuts and other hardware complete as directed. | 70 | Sq.ft | 205 | 14350 | 117 | 117 | 23985 | 47 | 9635 | 9635 | 0 | 9635 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
d | Pigeon hole storage
i | Providing and fixing in place pigeon hole storages made of 19mm thick BWR Plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) or HD Partical Board and finished with 1.0mm thick laminate externally. The shelves and internal verticals for the pigeon hole to be made of 12mm thick plywood and finished in hand Melamine Polish. All complete as per the 5 S requirements of the Bank. |  | Sq.ft | 966 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Shutters
a | Providing and fixing shutters below pantry counter made of 19mm thick plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished with 1.0mm thick laminate internally and externally. The cost to include wooden frame of size 50 mm x 38mm for fixing of the shutters. All complete including necessary hardware like hinges, handles etc. aluminum perforated grilles for ventilation. | 55 | Sq.ft | 466 | 25630 | 51.5174 | 51.52 | 24008.32 | -3.4826 | -1621.68 | 0 | -1621.68 | -1621.68
b | Same as item 7(a) but shutters without ventilation grille for built in niches . |  | Sq.ft | 466 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Providing and fixing DB shutters/ Electrical cabinate in 19 mm thick FR Grade Plywood (use FR Plywood which are "Free of Added Urea Formaldehyde" (required) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, FR Plywood) of approved make only to be finished with 1.0mm thick laminate externally & Internally should have of aluminum perforated grille at bottom and all hardware, tower bolts, locks etc. to be included. | 40 | Sq.ft | 457 | 18280 | 31.5 | 31.5 | 14395.5 | -8.5 | -3884.5 | 0 | -3884.5 | -3884.5
8 | Façade Treatment
a | Aluminium Composite Panel
i | Providing and fixing tricolour (Silver - Red - Grey) Aluminium Composite Panels (ACP) of A2 FR Grade exterior grade for cladding near entrance of approved make for external wall / column / canopy cladding in combination of solid / Metallic colours, including all necessary frame work and complete weather sealing. The composite panel should consist of 3mm thermoplastic core of LDPE sandwiched between 2 skins of 0.5mm thick aluminium sheet (alloy designation 310S) making a total panel thickness of 4mm. The surface will be furnished with Lumiflon based flourcarbon coating on top sides and service coating on reverse side. Coatings shall conform to specifications of specifications of ECCA / AAMA and conforming to the mechanical properties of panel as per detailed technical specifications. the system shall be fixed using GI brackets and stainless steel bolts and nuts complete with spring washers and cap nuts and all other necessary accessories. The bracket support shall be designed as per manufactures specification and shall withstand a wind pressure of 150 kg / sqm. all hardware shall corrosion resistant frame out of anodised aluminium member. | 200 | Sq.ft | 286 | 57200 | 111.8 | 111.8 | 31974.8 | -88.2 | -25225.2 | 0 | -25225.2 | -25225.2
9 | Railing
a | SS Railing
i | Providing and fixing SS railing of 304 quality as per design for staircase/ramps etc. | 65 | R.ft | 1167 | 75855 |  | 0 | 0 | -65 | -75855 | 0 | -75855 | -75855
ii | Same as item 9.a-(i) above but providing only ss pipe of dia 50 mm on one side of the wall with necessary brackets at required intervals. |  | R.ft | 808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | MS Railing
i | Providing and fixing MS railing with powder coated finish of approved shade |  | R.ft | 712 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Same as item 9.b-(i) but providing only MS pipe of dia 50mm on one side of the wall with necessary brackets at required intervals. |  | R.ft | 570 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Loose Furniture (use of BIFMA/Green Guard/ GPSC certified Sofa Units)
a | Single Seater Sofa in composite leather as per design. ( Make: Amardeep Design or approved by CPC ) |  | Nos. | 10627 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Two Seater Sofa in composite leather as per design.( Make: Amardeep Design or approved by CPC ) |  | Nos. | 17628 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Three Seater Sofa in composite leather as per design.( Make: Amardeep Design or approved by CPC ) |  | Nos. | 21687 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Corner Tables of size 450 mm x450mm made of glass top (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) and Powder coated MS base finished with approved shade of paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) and finished . ( Make: Amardeep Design or approved by CPC ) |  | Nos. | 10610 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | Centre Table of size 600mm x 1200mm made of glass top (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) and Powder coated MS base finished with approved shade of paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) and finished . ( Make: Amardeep Design or approved by CPC ) |  | Nos. | 11017 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Windows
a | Supplying & fixing in position Aluminium extruder sections of 16 gauge of approved Makes two track sliding windows with outer frame made from section overall size 62mm x 45mm, with shutters of sections made of 19mm x 40mm with 6mm plain sheet glass (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) of approved Make with new neoprene gasket, shutters to be provided with nylon encased S.S. rollers, necesarry locks, and handles etc. The A1 section should be, treated with powder coating of approved colour/ shade. Complete in all respect. |  | Sq.ft | 300 | 0 | 133.8375 | 133.84 | 40152 | 133.8375 | 40152 | 40152 | 0 | 40152 | Quantity executed on site and verified during audit but not present in work order
b | Same as item 11(a) above but for 3 tracks | 60 | Sq.ft | 296 | 17760 |  | 0 | 0 | -60 | -17760 | 0 | -17760 | -17760
c | Same as item 11(a) as above but openable type with friction hinges of approved co. |  | Sq.ft | 319 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | Louvered windows for toilet and pantry windows |  | Sq.ft | 794 | 0 | 8.625 | 8.63 | 6852.22 | 8.625 | 6852.22 | 6852.22 | 0 | 6852.22 | Quantity executed on site and verified during audit but not present in work order
12 | Miscellaneous
a | Soft / Pinup Board
i | Providing and fixing 12thk. Soft board comprising of 12mm thk. back Ply (use FR Plywood which are "Free of Added Urea Formaldehyde" (required) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, FR Plywood) fixed on wall with 12mm thk pinup board (Soft board) covered with fabric of approved shade (Basic cost Rest. 110/- per running meter.) | 70 | Sq.ft | 177 | 12390 | 72 | 72 | 12744 | 2 | 354 | 354 | 0 | 354 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
b | White Board
i | Providing and fixing of magnetic white board of 3'-0" X 4'-0" size for Branch Manager & Meeting Room including accessories like markers, dusters , tray etc. |  | Nos. | 3203 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Similar to above but 6'-0" x4'-0" size |  | Nos. | 6576 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iii | Same as b (i) but toughened glass writing board of size 3' x 4' on S.S. studs | 2 | Nos. | 5367 | 10734 | 0 | 0 | 0 | -2 | -10734 | 0 | -10734 | -10734
c | Window Blinds
i | Supplying and fixing 4" wide vertical fabric blinds of approved made and colour and texture including all fittings of approved quality complete. Blinds made using 100% polyester with acrylic polymer coating. |  | Sq.ft | 66 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Supplying and fixing roller fabric blinds of approved made and colour and texture including all fittings of approved quality complete. Blinds made using 100% polyester with acrylic polymer coating. | 200 | Sq.ft | 106 | 21200 | 201.9165 | 201.92 | 21403.52 | 1.9165 | 203.52 | 203.52 | 0 | 203.52 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
d | Frosted Film
i | Providing and fixing of frosted film on glass as per design - Make Garware. |  | Sq.ft | 67 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Providing and fixing of frosted film on glass as per design - Make 3M | 500 | Sq.ft | 105 | 52500 | 489.504 | 489.5 | 51397.5 | -10.496 | -1102.5 | 0 | -1102.5 | -1102.5
iii | Providing and fixing Sun control film on the main glazing - Make 3M |  | Sq.ft | 50 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | Mirror for Toilets & Strong Room
i | Providing and fixing flawless 6 mm thk. mirror of approved quality . The mirror shall be fixed on 12mm thk marine plywood (use FR Plywood which are "Free of Added Urea Formaldehyde" (required) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Plywood) backing with stainless steel mirror screws. | 30 | Sq.ft | 226 | 6780 | 12 | 12 | 2712 | -18 | -4068 | 0 | -4068 | -4068
ii | same as above but with pedestal unit of total 600 mm x 450 mm to be provided wherever it is not possible to fix the mirror on the strong room walls |  | Nos. | 6419 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
f | Curtain with SS Rod
i | Providing and fixing of curtain with SS rod in Strong Room ( size upto 1500 mm x 2100mm) |  | Job | 1966 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
g | Aluminium Skirting
i | providing and fixing 75 mm ht approved aluminium extruded profile skirting (readymade section) made out of 18 gauge aluminium, powder coated with shade as approved by architect with a thickness of 50 microns. Skirting to include all nesessary fixing details all complete as per detail drawing. Rate to include 12mm thk marine plywood backing (use FR Plywood which are "Free of Added Urea Formaldehyde" (required) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Plywood) for solid partition/ wall. Rate to be inclusive of providing 12mm groove between the skirting and the partition skinning. |  | R.ft | 97 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
h | Glass Shelves
i | Providing and fixing 300 mm wide and 10 mm thick glass (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) shelves for momentos in Br. manager's cabin fixed with ss brackets. Size of each shelve. | 5 | Sq.ft | 661 | 3305 | 0 | 0 | 0 | -5 | -3305 | 0 | -3305 | -3305
i | Wooden Shelf
i | Providing and fixing 19mm thk ply shelf for DVR in Server Room. Size (1'-6" X 9") |  | Nos. | 518 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Similar to above but shelf of size(2'-0" X 9") for Strong Room below vanity mirror |  | Nos. | 847 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
j | Plastic Board Signages
i | Providing and fixing plastic board signage and numbers | 6 | Nos. | 423 | 2538 | 12 | 12 | 5076 | 6 | 2538 | 2538 | 0 | 2538 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
k | Writing Ledge (Requirement to be checked with the Project Manager before provision)
i | Providing and fixing of writing ledge as per design. |  | Nos. | 4025 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
l | Notice Board
i | Providing and fixing Notice board made up of soft board comprising of 12mm thk. back Ply (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) fixed on wall with 12 mm thk pinup board (Soft board) covered with fabric of approved shade Board to be covered with four way frame of 75 mm thik 12 mm plywood and to be finished with approved laminated shade |  | Sq.ft | 220 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Providing and fixing modular Notice board made up of soft board comprising of 18 Gauge thik back aluminium foil on wall with 10 mm thk pinup board (Soft board) covered with fabric of approved shade and Board to be covered with four way frame of 35 mm thik aluminium extruded profile. |  | Sq.ft | 211 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
m | Pelmet (as per site conditions and window / ceiling intersection)
i | Providing and fixing in place 150mm deep pelmet made out of 19mm thick plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished internally with enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) . The pelmet to be provided at the junction of window and false ceiling only as per site conditions. The pelmet to be concealed inside the false ceiling such as to receive the vertical blinds. |  | R.ft | 243 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Providing and fixing in place 150mm deep pelmet made out of 12.5 mm thick gypsum board (use Green Pro certified Gypsum Board and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Gypsum Board) and finished with luster paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) . The pelmet to be provided at the junction of window and false ceiling only as per site conditions. The pelmet to be concealed inside the false ceiling such as to receive the vertical blinds. |  | R.ft | 262 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
n | Key Hanging Box
i | Providing and fixing in place key hanging box of size 600mm x 675mm made out of 19mm thick plywood and finished with 1.0 mm thick laminate of approved shade. The shutter of the key box to be made of 19mm thick plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) with 60mm wide frame on all sides with 6mm thick glass embedded in it. The key box to be provided with key hooks. | 1 | Nos. | 3326 | 3326 | 1 | 1 | 3326 | 0 | 0 | 0 | 0 | 0
o | Aluminium Folding Step Ladder (A` type Self-supporting plate form ladder
i | Ladder of height 8 feet (C section and steps on both sides) | 1 | Nos. | 6186 | 6186 | 1 | 1 | 6186 | 0 | 0 | 0 | 0 | 0
ii | Ladder of height 10 feet (C section and steps on both sides) |  | Nos. | 7909 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iii | Ladder of height 12 feet (C section and steps on both sides) |  | Nos. | 9513 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
p | Miscellaneous work
i | Fixing of internal marketing poster frames supplied by the bank. | 15 | Nos. | 95 | 1425 | 0 | 0 | 0 | -15 | -1425 | 0 | -1425 | -1425
ii | Fixing of modular ATM drop box cum writing ledge supplied by the bank | 1 | Nos. | 137 | 137 | 0 | 0 | 0 | -1 | -137 | 0 | -137 | -137
iii | Providing and fixing weather shed made of GI sheet of 16/18 gauge. All complete with waterproofing, vata, drip mould etc. |  | Sq.ft | 286 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iv | Providing and fixing folding/retractable mechanical operation canopy awning made of high quality tensile plastic sheet. Cost is inclusive of all necessary accessaries, gears etc. |  | Sq.ft | 548 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
v | Supply of carpenter on monthly basis (8 hour shift per day) after handing over of the site for branch pre-launch activity. | 1 | per month basis | 15466 | 15466 | 1 | 1 | 15466 | 0 | 0 | 0 | 0 | 0 | Quantity not measureable during audit, PM confirmation required if these items should be added to the bill and Qty not Present in the WO
vi | Removing and re-applying laminate on existing furniture. |  | Sq.ft | 129 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
vii | Providing and fixing in place, media & offer zone made out of 12mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) with 230 mm deep niche of size 710mm X 750 mm 2 nos for net banking and phone banking and 1 no of size 710mm X 1050mm for offer zone finished with 1.0mm thick laminate of approved shade as per design. All niches to have a 18mm thick granite top of size 710mm X 350 mm with grommet hole of 75 mm dia with wire manager complete with round Melamine Polish on all exposed edges. Center niche to have cabinet with hinged shutter for housing CPU unit as per detail drawing. All the external surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with 0.8 mm thick laminate of approved shade. All complete including necessary hardware. |  | Sq.ft | 805 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
viii | Providing and fixing 12 mm Chair / Corner Guard of approved aluminium extruded profile (readymade section) as approved by architect. Rate to include all nesessary fixing details all complete as per detail drawing. | 1100 | R.ft | 101 | 111100 | 617.18 | 617.18 | 62335.18 | -482.82 | -48764.82 | 0 | -48764.82 | -48764.82
ix | Providing Heavy Traffic Entrance Mattin 3M Nomad Terra 8150 Floor Mat size upto 8'0" x 3'0" | 2 | Nos. | 3356 | 6712 | 2 | 2 | 6712 | 0 | 0 | 0 | 0 | 0
x | Providing and placing foot operated Dry and Wet Dust made up of 100 % food grade and BPA Free plastice having 19 Liters capacity . Bin should have individual bin slot with removable buckets and covered with outer frame. ( Make : Nayasa or RAGA) (For Desk) | 18 | Nos. | 1695 | 30510 | 18 | 18 | 30510 | 0 | 0 | 0 | 0 | 0
xi | Providing and placing foot operated Dry and Wet Dust made up of 100 % food grade and BPA Free plastice having 33 Liters capacity . Bin should have individual bin slot with removable buckets and covered with outer frame. ( Make : Nayasa or RAGA) ( For Pantry ) | 3 | Nos. | 1678 | 5034 | 3 | 3 | 5034 | 0 | 0 | 0 | 0 | 0
xii | Providing and fixing folding/retractable mechanical operation canopy awning made of high quality tensile plastic sheet. Cost is inclusive of all necessary accessaries, gears etc. |  | Sq.ft | 529 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
xii | Providing and fixing 12 mm froster glass partion to be placed in between interconnected workstation. Rate to include all nesessary fixing details all complete as per detail drawing. |  | Sq.ft | 381 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
xiii | Providing and placing 6 mm transparant acrylic glass for table top to avoid lnk / stamp marking on white laminated tops. (Basis rate of acrylic is 300 Rs./ Sq.ft) | 230 | Sq.ft | 343 | 78890 | 0 | 0 | 0 | -230 | -78890 | 0 | -78890 | -78890
q | Fire Exit Door
a | Supply & Fixing single leaf Metal Fire Doors of Size : 1200mm X 2400mm with a vision panel 310mm X 310mm & without panic bar of 60 minutes Rated Insulated Fire Door Tested in accordance to BS: 476 Part – 20 and IS: 3809: 1979, CNP – 2150 Door Frame: Providing of Door Frame of section 120mm X 70mm with fire intumescent seal strip of size 10mm X 4mm for fire and smoke sealing mounted in the grooves of the frame and coated with fire retardant intumescent Primer coating. Hinges: Providing of ball bearing hinges with S.S. Screws - 4 nos per shutter. Handle: Fire rated handles in SS finish to be included in cost. |  | Nos. | 33391 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Same as 12_p_xiii_a but included Supply and installation of Panic Bar with Hooter |  | Nos. | 36442 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Cost of Carpentry and Interior works |  |  |  | 2147140 |  |  | 1999427.59 |  | -147712.41 | 364478.61 | -512191.02 | -147712.41
IV | PAINTING WORKS
a | Paint on Walls
i | Providing and applying desired paint luster finish to walls, of approved shade.. The surface of wall to be painted shall be prepared and applied with two coats of primer, two coats of putty and touch up putty if required to achieve smooth finish. The surface shall be painted with three coats of luster paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of Dulux - akzonobel / Asian. | 1050 | Sq.ft | 25 | 26250 | 1047.1893 | 1047.19 | 26179.75 | -2.8107 | -70.25 | 0 | -70.25 | -70.25
b | Acrylic Emulsion Paint on Ceiling
i | Same as item (a) but applying acrylic emulsion paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) on the ceiling | 300 | Sq.ft | 20 | 6000 | 478.5775 | 478.58 | 9571.6 | 178.5775 | 3571.6 | 3571.6 | 0 | 3571.6 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
c | Synthetic Enamel Paint (over existing MS grilles, gates, shutters etc.)
i | Same as item (a) above but applying synthetic enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) to MS grilles, collapsible gates, rolling shutters etc. | 520 | Sq.ft | 21 | 10920 | 858.4502 | 858.45 | 18027.45 | 338.4502 | 7107.45 | 7107.45 | 0 | 7107.45 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
d | Apex Paint
i | The surface of wall or ceiling to be painted shall be prepared as per the manufacturers specification. Cracks if any visible on the surface to be treated by opening up the cracks, filling the same using polymer based waterproofing compound. The surface shall be applied with a priming coat of white cement or approved primer. The primed surface shall be painted with the desired paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) with two or more coats as per specifications of the manufacturer. | 300 | Sq.ft | 16 | 4800 | 1592.7034 | 1592.7 | 25483.2 | 1292.7034 | 20683.2 | 20683.2 | 0 | 20683.2 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
e | Texture Paint
i | Textured superfine paint shall be applied after preparing the surface to get the antique finish. The paint shall be applied using texture roller to give a uniform roller texture finish with two coats different colours of acrylic emulsion paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) . The texture paint used shall be of spectrum make. |  | Sq.ft | 63 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
f | Duco Paint ( over existing Locker room door only )
i | Same as item (a) above but applying duco paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) to existing locker room only etc. |  | Sq.ft | 102 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
g | Fire rated paint on wall
i | Providing and applying three coats of fire rated paint of approved make, with low voc - leed certified, wherever required to internal walls/ceiling surfaces after thoroughly sand papering surfaces to remove dust, dirt etc. and repairing dents, cracks, holes with pop to achieve level surface and finishing with two coats of primer, putty and three coats of paint including cost of material, labour etc. all complete as directed by the engineer in charge. Rate to include application at all heights and levels, surfaces and textures. approval required of engineer in charge after each coat. | 360 | Sq.ft | 61 | 21960 |  | 0 | 0 | -360 | -21960 | 0 | -21960 | -21960
| Total Cost of Painting works |  |  |  | 69930 |  |  | 79262 |  | 9332 | 31362.25 | -22030.25 | 9332
V | ROLLING SHUTTER AND MS WORK
1 | MS Window grill
a | Providing and fixing of MS Box type window grille made out of 10mm X 10 mm MS square section with the depth fof 300 mm in standard pattern as per design. The grille to be finished with red oxide and 2 coats of enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade (Black) | 200 | Sq.ft | 144 | 28800 |  | 0 | 0 | -200 | -28800 | 0 | -28800 | -28800
2 | M.S. Fabrication work.
a | Providing, Fixing and fabrication of MS structure for staircase, under/overdeck strengthing of slab, columns, and MS Brackets. Cost includes cost of all types of MS members requires to build structure, Additional supports, fabrication, bolting, grouting and other neccesary structure elements. MS structure should treated with anti corrotion treament before final finishing. Cost is inclusive of anti corrontion and 2 coats of enamal paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) , Structure certificate etc. ( This item is applicable for MS Brackets of signages, MS Staircase, MS Strengthing work) |  | KG. | 139 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Rolling Shutter / Collapsible Gate
a | P/f. ROLLING SHUTTER in 18 gauge GI 2" wide flat interlocking slats, with bottom lock rail, necessary handles and locking arrangement, guides on sides including providing vision panel of size 450mm x length at 1500mm from the floor finish level. Shutters to be coated with 2 coats of anti-rust paint and 3 coats of 1st quality enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) in Blue colour as per HDFC logo. Rate to include top cover box . |  | Sq.ft | 247 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | Add extra for providing mechanical gear for rolling shutter wherever required as per site condition. |  | Job | 7517 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | All type of modification at Existing Rolling Shutter for introducing grill at Eye Level / making two or more other parts from single Shutter. |  | Sq.ft | 129 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d | servicing/greasing of existing rolling shutters to make it workable. |  | Job | 7627 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Collapsible Gate
a | Providing and erecting in position MS Collapsible grill gate with heavy duty standard sections, channel, flats, top and bottom guides, pivots, rollers, stoppers, handles with proper locking arrangement & necessary accessories. The gate shall be finished with 1 coat of red oxide and two coats of enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade. |  | Sq.ft | 239 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Collapsible MS Shutter
a | Similar to above 4(a) but for Collapsible MS Shutter |  | Sq.ft | 466 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VSAT Monkey cage / MS enclosure
a | Provide and installation of Mild steel Vsat monkey cage of size 8 ft x 8 ft x 8 ft and fixed at bottom with MS angle frame of size 40/40/5 and also having intermediate supports MS flats of size 25/25/5 and frame covered with MS mesh size of 10 Gauge 4'' x 4'' the cage having access gate Size 6 ft x 3 ft strength by angle with proper locking arrangement, Cage shall be finished with 1 coat of anti-rusting paint and two coats of enamel paint (use of approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, Paints) of approved shade. |  | Sq.ft | 245 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Cost of Rolling Shutter and MS Work |  |  |  | 28800 |  |  | 0 |  | -28800 | 0 | -28800 | -28800
VI | ELECTRIFICATION AND ALLIED WORKS
PART- | 1 : POWER DISTRIBUTION PANEL
Supply, Installation, Testing & commissioning of the following panels/DBs fabricated with 16 gauge CRCA steel & 14 gauge CRCA sheet for the frame sheet painted in 7 tank process with 2 coats of red oxide & 2 coats of Smokey grey colour similar to RAL7032 Siemens grey colour. Interconnecting wires of panel should be Cu flexible / PVC wires as per following details : - PT control circuit for voltmeter - 1.5mm2, CT control circuit for ammeter - 2.5mm2, 20A circuit - 4mm2, 30A circuit - 6mm2, 40A circuit - 10mm2, 50/60A circuit - 16mm2,
1.1.1 | TYPE I PANEL - Main LT Panel (For upto 1000 sq. ft) |  | Nos. | 83902 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
This Panel includes MCB for Power and AC distributions hence there is no separate LDB, PDB and ACDB required.
Metering:-
2 nos of Separate KWH sub-meter to be installed, 1 no. for critical load and other for remaining load. It should be complient with the RS485 port.
Digital VAF meter to show voltage, current and frequency parameters of the entire load
Phase Indication Lamps - 3 Nos.
I/c- 63A.25KA 4P TPN MCCB:- 1 no. (Changeover can be consider seperately as per line item in BoQ below)
O/g:- 40 A, TPN MCB:- 4 nos.
32/40 A,DP MCB:- 2 Nos.
40 A,100mA, DP ELCB:-1 nos
10,16,20 A,SP MCB:-6 nos
25 A,30mA, DP ELCB:-2 nos
40 A,DP ISOLATOR:-2 NOS
1.1.2 | TYPE I PANEL - Main LT Panel (For 1000-1500 sq. ft) |  | Nos. | 127675 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
This panel includes MCB's for AC hence separate ACBD is not required
Metering:-
2 nos of Separate KWH sub-meter to be installed, 1 no. for critical load and other for remaining load. It should be complient with the RS485 port.
Digital VAF meter to show voltage, current and frequency parameters
Phase Indication Lamps - 3 Nos.
Incomer 1 - 100 A. 25KA 4P MCCB:- 1 nos. (Changeover can be consider seperately as per line item in BoQ below)
100A TP Power Contactor with 2NO and 2NC contacts
Normal Bus (during bank hours)
O/g:- 63 A, TPN MCB:- 3 nos.
32/40 A,DP MCB:- 4Nos.
32 A,TPN MCB:-1 nos
Critical Bus (24/7)
Incomer 1 - 63A TP MCCB
O/g:- 40 A, TPN MCB:- 1 nos.
32A DP MCB - 4 nos.
1.1.2 | TYPE I PANEL - Main LT Panel (For 1500-2500 sq. ft) | 1 | Nos. | 155313 | 155313 | 1 | 1 | 155313 | 0 | 0 | 0 | 0 | 0
This panel includes MCB's for AC hence separate ACBD is not required
Metering:-
2 nos of Separate KWH sub-meter to be installed, 1 no. for critical load and other for remaining load. It should be complient with the RS485 port.
Digital VAF meter to show voltage, current and frequency parameters
Phase Indication Lamps - 3 Nos.
Incomer 1 - 125 A. 25KA 4P MCCB:- 1 nos. (Changeover can be consider seperately as per line item in BoQ below)
125A TP Power Contactor with 2NO and 2NC contacts
Normal Bus (during bank hours)
O/g:- 63 A, TPN MCB:- 7 nos.
| 32/40 A,DP MCB:- 2 Nos. |  | Not on site |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80/100 A TPN MCCB:- 1 nos. |  | Not on site |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 32 A,TPN MCB:-1 nos |  | Not on site |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Critical Bus (24/7)
Incomer 1 - 80A TP MCCB
| O/g:- 63 A, TPN MCB:- 1 nos. |  | Not on site |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 40A TPN MCB - 1 no |  | Not on site |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 32A DP MCB - 3 nos. |  | Not on site |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3 | TYPE II PANEL - Main LT Panel (For 2500-4500 sq. ft) |  | Nos. | 161759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
This panel includes MCB's for AC hence separate ACBD is not required
Metering:-
2 nos of Separate KWH sub-meter to be installed, 1 no. for critical load and other for remaining load. It should be complient with the RS485 port.
Digital VAF meter to show voltage, current and frequency parameters
Phase Indication Lamps - 3 Nos.
Incomer 1 - 160 A. 25KA 4P MCCB:- 1 nos. (Changeover can be consider seperately as per line item in BoQ below)
160A TP Power Contactor with 2NO and 2NC contacts
Normal Bus (during bank hours)
O/g:- 63 A, TPN MCB:- 7 nos.
32/40 A,DP MCB:- 3 Nos.
80/100 A TPN MCCB:- 1 nos.
32 A,TPN MCB:-1 nos
Critical Bus (24/7)
Incomer 1 - 80A TP MCCB
O/g:- 63 A, TPN MCB:- 1 nos.
40A TPN MCB - 1 no
32A DP MCB - 3 nos.
1.1.4 | Supply & Installation of Master Switch with Key comprising of Start and Stop Push Button with key control for Start and Stop complete in powder coated MS box near the entrance of the bank. By Switching off this master switch the entire electrical equipment (Except Critical Bus) in the branch will get switched off. This switch can be operated while closing the branch. We have excluded following load from Master switch : entire UPS Load, Signage, Server room and ATM room AC's, CCTV, emergency lights and any other critical loads if any as per the seperate critical bus mentioned in panels specification as above. | 2 | Nos. | 28612 | 57224 | 2 | 2 | 57224 | 0 | 0 | 0 | 0 | 0
1.2 | Supply, installation, testing and commissioning of the following rating of MCCBs in Sheet Steel enclosure duly housed in CRCA Sheet Enclosure , front operated Powder coated.
1.2.1 | 63 Amps TP&N (16 Ka) MCCB- 1. No. |  | Nos. | 9175 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2 | 80 Amps TP&N (16 Ka) MCCB- 1. No. |  | Nos. | 10137 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.3 | 100 Amps TP&N (16 Ka) MCCB- 1. No. |  | Nos. | 11624 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.4 | 125 Amps TP&N (25 Ka) MCCB- 1. No. | 2 | Nos. | 12602 | 25204 |  | 0 | 0 | -2 | -25204 | 0 | -25204 | -25204
1.2.5 | 160 Amps TP&N (25 Ka) MCCB- 1. No. |  | Nos. | 15784 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.6 | 63 Amps FP MCB 10 ka in Powder Coated Steel Sheet Enclosure- 1 no. |  | Nos. | 3457 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.7 | 80 Amps FP MCB 10 ka in Powder Coated Steel Sheet Enclosure- 1 no. |  | Nos. | 4237 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PART ‘1’ TOTAL CARRIED TO SUMMARY |  |  |  | 237741 |  |  | 212537 |  | -25204 | 0 | -25204 | -25204
PART- | 2 : CAPACITOR PANEL
2.1 | APFCR PANEL - 10 kVAR |  | Nos. | 35086 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
This Panel is for area 1000 till 1500 sq. ft.
Incomer section
63A TP MCCB 25kA, O/C+S/C with rotary handle - 1no
0-500V, Voltmeter with selector switch and 3 nos. 2A MCBs - 1set
R Y B Phase Indicating lamps - 3 nos
APFC RELAY - 4 STEP - 1no
Control wiring with Fuses - 1 set
Outgoing Section
2 nos 5kVAR Capacitor banks comprising of the following items:
20A TP MCB "D" Curve - 2 nos
5kVAR Capacitor Duty Contactor with damping resistor - 2nos.
ON/OFF Push Button with indicating lamps - 6 nos
5kVAR MPP type 415V capacitor - 2sets
2.2 | APFCR PANEL - 15 kVAR | 1 | Nos. | 55333 | 55333 |  | 0 | 0 | -1 | -55333 | 0 | -55333 | -55333
This Panel is for area 1500 till 2500 sq. ft.
Incomer section
63A TP MCCB 25kA, O/C+S/C with rotary handle - 1no
0-500V, Voltmeter with selector switch and 3 nos. 2A MCBs - 1set
R Y B Phase Indicating lamps - 3 nos
APFC RELAY - 4 STEP - 1no
Control wiring with Fuses - 1 set
Outgoing Section
3 nos 5kVAR Capacitor banks comprising of the following items:
20A TP MCB "D" Curve - 3 nos
5kVAR Capacitor Duty Contactor with damping resistor - 3 nos.
ON/OFF Push Button with indicating lamps - 6 nos
5kVAR MPP type 415V capacitor - 3sets
2.3 | APFCR PANEL - 30 kVAR |  | Nos. | 90152 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
This Panel is for area 2500 till 4500 sq. ft.
Incomer section
100A TP MCCB 25kA, O/C+S/C with rotary handle - 1no
0-500V, Voltmeter with selector switch and 3 nos. 2A MCBs - 1set
R Y B Phase Indicating lamps - 3 nos
APFC RELAY - 4 STEP - 1no
Control wiring with Fuses - 1 set
Outgoing Section
2 nos 5kVAR Capacitor banks comprising of the following items:
20A TP MCB "D" Curve - 2 nos
5kVAR Capacitor Duty Contactor with damping resistor - 2 nos.
ON/OFF Push Button with indicating lamps - 4 nos
5kVAR MPP type 415V capacitor - 2 sets
2 nos 10kVAR Capacitor banks comprising of the following items:
32A TP MCB "D" Curve - 2 nos
10kVAR Capacitor Duty Contactor with damping resistor - 2 nos.
ON/OFF Push Button with indicating lamps - 4 nos
10kVAR MPP type 415V capacitor - 2 sets
| PART ‘2’ TOTAL CARRIED TO SUMMARY |  |  |  | 55333 |  |  | 0 |  | -55333 | 0 | -55333 | -55333
PART- | 3 : PHASE CORRECTION CIRCUIT
PHASE CORRECTION DB SHOULD BE INSTALLED BEFORE STABILISER AND AFTER ELECTRICITY METER
TRAINING SHOULD BE PROVIDED TO BRANCH TEAM AND FA'S
3.1 | MANUAL PHASE CORRECTION CIRCUIT
Providing Phase Correction Distribution Boards (Double Door) suitable for 415V, 50 Hz system. Dust and vermin proof having floor / wall mounting cubicle pattern with removable gland plates, with 1 set of 100 amps Copper Bus Bar, Earth and Neutral Link etc as required.
3.1.1 | 20-30KVA Phase correction DB (For upto 1000 sq. ft) |  | Nos. | 22119 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63A 4P Onload Changeover
Phase Sequence Relay (2 C/O) - 63 A - 1 no.
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
3.1.2 | 30-40 KVA Phase correction DB (For 1000-1500 sq. ft)
100A 4P Onload Changeover
| Phase Sequence Relay (2 C/O) - 100 A - 1 no. |  | Nos. | 31188 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
3.1.3 | 40-50 KVA Phase correction DB (For 1500-2500 sq. ft) |  | Nos. | 36612 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
125A 4P Onload Changeover
Phase Sequence Relay (2 C/O) - 63 A - 1 no.
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
3.1.4 | 50-60 KVA Phase correction DB (For 2500-4500 sq. ft) |  | Nos. | 41951 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
160A 4P Onload Changeover
Phase Sequence Relay (2 C/O) - 100 A - 1 no.
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
3.2 | AUTO PHASE CORRECTION CIRCUIT (with Auto-Manual provision) - CONTACTOR LOGIC
Providing Phase Correction Distribution Boards (Double Door) suitable for 415V, 50 Hz system. Dust and vermin proof having floor / wall mounting cubicle pattern with removable gland plates, with 1 set of 100 amps Copper Bus Bar, Earth and Neutral Link etc as required.
3.2.1 | 20 KVA Phase correction DB |  | Nos. | 23263 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPN MCCB - 63 A - 1 no.
TP Contactor - 63 A - 2 Nos.
Auto Manual Selector switch - 10 A - 1 No.
Stop-Start P.B (Red, Green) - 10A - 4 nos.
Phase Sequence Relay (2 C/O) - 63 A - 1 no.
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
On-delay timer - 0-30 Sec - 1 no.
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
3.2.2 | 30 KVA Phase correction DB |  | Nos. | 30510 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPN MCCB - 100 A - 1 no.
TP Contactor - 100 A - 2 Nos.
Auto Manual Selector switch - 10 A - 1 No.
Stop-Start P.B (Red, Green) - 10A - 4 nos.
Phase Sequence Relay (2 C/O) - 100 A - 1 no.
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
On-delay timer - 0-30 Sec - 1 no.
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
3.2.3 | 40-50 KVA Phase correction DB (For 1500-2500 sq. ft) |  | Nos. | 38137 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPN MCCB - 125 A - 1 no.
TP Contactor - 125 A - 2 Nos.
Auto Manual Selector switch - 10 A - 1 No.
Stop-Start P.B (Red, Green) - 10A - 4 nos.
Phase Sequence Relay (2 C/O) - 125 A - 1 no.
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
On-delay timer - 0-30 Sec - 1 no.
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
3.2.4 | 50-60 KVA Phase correction DB (For 2500-4500 sq. ft) |  | Nos. | 44620 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPN MCCB - 160 A - 1 no.
TP Contactor - 160 A - 2 Nos.
Auto Manual Selector switch - 10 A - 1 No.
Stop-Start P.B (Red, Green) - 10A - 4 nos.
Phase Sequence Relay (2 C/O) - 160A - 1 no.
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
On-delay timer - 0-30 Sec - 1 no.
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
3.3 | AUTO PHASE CORRECTION CIRCUIT (with Auto-Manual provision) - ATS LOGIC
Providing Phase Correction Distribution Boards (Double Door) suitable for 415V, 50 Hz system. Dust and vermin proof having floor / wall mounting cubicle pattern with removable gland plates, with 1 set of 100 amps Copper Bus Bar, Earth and Neutral Link etc as required.
3.3.1 | 20 KVA Phase correction DB |  | Nos. | 32035 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPN MCCB - 63 A - 1 no.
FP ATS (Auto C/O) - 63 A - 1 No.
Auto Manual Selector switch - 10 A - 1 No.
Stop-Start P.B (Red, Green) - 10A - 4 nos.
Phase Sequence Relay (2 C/O) - 63 A - 1 no.
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
On-delay timer - 0-30 Sec - 1 no.
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
3.3.2 | 30 KVA Phase correction DB |  | Nos. | 35467 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPN MCCB - 100 A - 1 no.
FP ATS (Auto C/O) - 100 A - 1 No.
Auto Manual Selector switch - 10 A - 1 No.
Stop-Start P.B (Red, Green) - 10A - 4 nos.
Phase Sequence Relay (2 C/O) - 100 A - 1 no.
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
On-delay timer - 0-30 Sec - 1 no.
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
3.3.3 | 40-50 KVA Phase correction DB (For 1500-2500 sq. ft) |  | Nos. | 42714 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPN MCCB - 125 A - 1 no.
FP ATS (Auto C/O) - 125 A - 1 No.
Auto Manual Selector switch - 10 A - 1 No.
Stop-Start P.B (Red, Green) - 10A - 4 nos.
Phase Sequence Relay (2 C/O) - 125 A - 1 no.
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
On-delay timer - 0-30 Sec - 1 no.
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
3.3.4 | 50-60 KVA Phase correction DB (For 2500-4500 sq. ft) |  | Nos. | 49578 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPN MCCB - 160 A - 1 no.
FP ATS (Auto C/O) - 160 A - 1 No.
Auto Manual Selector switch - 10 A - 1 No.
Stop-Start P.B (Red, Green) - 10A - 4 nos.
Phase Sequence Relay (2 C/O) - 160 A - 1 no.
Phase sequence indicating lamp (Red) - 2 W - 2 Nos.
control Mcb - 6 A - 3 nos
On-delay timer - 0-30 Sec - 1 no.
R-Y-B indicating lamp (Red, Yellow, Blue) - 2 W - 3 nos
| PART ‘3’ TOTAL CARRIED TO SUMMARY |  |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0
PART- | 4 : DISTRIBUTION BOARDS
4.1 | Providing Lighting / UPS / Power Distribution Boards (Double Door) suitable for 415V, 50 Hz system. Dust and vermin proof having floor / wall mounting cubicle pattern with removable gland plates, with 1 set of 100 amps Copper Bus Bar, Earth and Neutral Link etc as required.
ALL MCBS SHALL BE "C" TYPE AND RATED AT 10kA
4.1.1 | UPS DB :
4.1.1.a | For 3 Phase UPS |  | Nos. | 8771 | 0 | 1 | 1 | 8771 | 1 | 8771 | 8771 | 0 | 8771 | Quantity executed on site and verified during audit but not present in work order
TPN, 4 Way
| I/c:- 63 A TPN MCB. |  |  | 40 mccb 1
O/g. 10/16/20 A SPMCB:- 12 nos.
OR
4.1.1.b | For 1 Phase UPS |  | Nos. | 6483 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPN, 16 Way
I/c:- 63 A DP MCB.
O/g. 10/16/20 A SPMCB:- 12 nos.
4.1.2 | Emergency DB (If required/Optional) |  | Nos. | 6483 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPN, 12 Way
I/c:- 40 A DP MCB/ELCB
O/g. 10/16 A SPMCB- 6 nos.
4.1.3 | Power DB :
4.1.3.a | TPN, 6 Way (for 1500 to 2500 sq. ft area) | 1 | Nos. | 13638 | 13638 |  | 0 | 0 | -1 | -13638 | 0 | -13638 | -13638
I/c:- 63 A TPN MCB
O/g - 3 nos 32A DP RCCB 100mA
O/g. 16/20 A SPMCB:- 12 nos. (4 nos per phase)
4.1.3.b | TPN, 8 Way (above 2500 Sq. ft area) |  | Nos. | 14574 | 0 | 1 | 1 | 14574 | 1 | 14574 | 14574 | 0 | 14574 | Quantity executed on site and verified during audit but not present in work order
I/c:- 63 A TPN MCB
O/g - 3 nos 40A DP RCCB 100mA
O/g. 16/20 A SPMCB:- 18 nos. (6 nos per phase)
4.1.4 | Lighting DB :
4.1.4.a | TPN, 6 Way (for 1500 to 2500 sq. ft area) | 1 | Nos. | 13666 | 13666 |  | 0 | 0 | -1 | -13666 | 0 | -13666 | -13666
I/c:- 63 A TPN MCB
O/g - 3 nos 32A DP RCCB 30mA
O/g. 10 A SPMCB:- 12 nos. (4 nos per phase)
4.1.4.b | TPN, 8 Way (above 2500 Sq. ft area) |  | Nos. | 15021 | 0 | 1 | 1 | 15021 | 1 | 15021 | 15021 | 0 | 15021 | Quantity executed on site and verified during audit but not present in work order
I/c:- 63 A TPN MCB
O/g - 3 nos 32A DP RCCB 30mA
O/g. 10 A SPMCB:- 18 nos. (6 nos per phase)
| PART ‘4’ TOTAL CARRIED TO SUMMARY |  |  |  | 27304 |  |  | 38366 |  | 11062 | 38366 | -27304 | 11062
PART- | 5 : CABLES & TERMINATIONS
5.1 | Supply , Installation of 1100V Grade PVC insulated , PVC sheathed GI wire armored Aluminium/ copper standard conductor , Cable of following sizes to be laid in on wall complete with dressing saddling clamping etc. Including civil work and required accessories.
5.1.1 | 3½ Core 120 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Mtrs. | 805 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.2 | 3½ Core 95 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Mtrs. | 716 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.3 | 3½ Core 70 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 60 | Mtrs. | 553 | 33180 | 28 | 28 | 15484 | -32 | -17696 | 0 | -17696 | -17696
5.1.4 | 3½ Core 50 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Mtrs. | 466 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.5 | 4 Core 35 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Mtrs. | 387 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.6 | 4 Core 25 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Mtrs. | 340 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.7 | 4 Core 16 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Mtrs. | 262 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.8 | 4 Core 10 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Mtrs. | 250 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.9 | 4 Core 10 sq.mm 1.1 KV Grade Copper Ar. Cable |  | Mtrs. | 762 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.10 | 4 Core 6 sq.mm 1.1 KV Grade Copper Ar. Cable |  | Mtrs. | 508 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.11 | 4 Core 4 sq.mm 1.1 KV Grade Copper Ar. Cable | 200 | Mtrs. | 409 | 81800 | 90 | 90 | 36810 | -110 | -44990 | 0 | -44990 | -44990
5.1.12 | 3 Core 6 sq.mm 1.1 KV Grade Copper Ar. Cable |  | Mtrs. | 423 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.13 | 1 Core 35 sq. mm. copper flexible cable |  | Mtrs. | 593 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.14 | 1 Core 25 sq.mm. copper flexible cable | 40 | Mtrs. | 411 | 16440 |  | 0 | 0 | -40 | -16440 | 0 | -16440 | -16440
5.1.15 | 1 Core 16 sq.mm. copper flexible cable |  | Mtrs. | 282 | 0 | 50 | 50 | 14100 | 50 | 14100 | 14100 | 0 | 14100 | Quantity executed on site and verified during audit but not present in work order
5.1.16 | 1 Core 10 sq.mm. copper flexible cable | 50 | Mtrs. | 211 | 10550 | 48 | 48 | 10128 | -2 | -422 | 0 | -422 | -422
5.2. | End termination of the following sizes of 1100V, Aluminium/copper (as per conductor), PVC insulated and sheathed armoured cables with single compression brass cable glands & crimping type Aluminum / Copper lugs, complete with all hardware etc. One end connection of a cable (with 3/4 core) to be consider as 1 end termination.
5.2.1 | 3½ Core 120 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Nos. | 953 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.2 | 3½ Core 95 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Nos. | 798 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.3 | 3½ Core 70 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Nos. | 722 | 0 | 2 | 2 | 1444 | 2 | 1444 | 1444 | 0 | 1444 | Quantity executed on site and verified during audit but not present in work order
5.2.4 | 3½ Core 50 sq.mm 1.1 KV Grade Aluminium Ar. Cable | 8 | Nos. | 632 | 5056 |  | 0 | 0 | -8 | -5056 | 0 | -5056 | -5056
5.2.5 | 4 Core 35 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Mtrs. | 461 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.6 | 4 Core 25 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Nos. | 416 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.7 | 4 Core 16 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Nos | 415 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.8 | 4 Core 10 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  | Nos | 381 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.9 | 4 Core 10 sq.mm 1.1 KV Grade Copper Ar. Cable |  | Nos. | 555 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.10 | 4 Core 6 sq.mm 1.1 KV Grade Copper Ar. Cable |  | Nos. | 490 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.11 | 4 Core 4 sq.mm 1.1 KV Grade Copper Ar. Cable | 20 | Nos. | 427 | 8540 | 5 | 5 | 2135 | -15 | -6405 | 0 | -6405 | -6405
5.2.12 | 3 Core 6 sq.mm 1.1 KV Grade Copper Ar. Cable |  | Nos. | 371 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.13 | 1 Core 35 sq. mm. copper flexible cable |  | Nos. | 165 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.14 | 1 Core 25 sq.mm. copper flexible cable | 4 | Nos. | 144 | 576 |  | 0 | 0 | -4 | -576 | 0 | -576 | -576
5.2.15 | 1 Core 16 sq.mm. copper flexible cable |  | Nos. | 137 | 0 | 8 | 8 | 1096 | 8 | 1096 | 1096 | 0 | 1096 | Quantity executed on site and verified during audit but not present in work order
5.2.16 | 1 Core 10 sq.mm. copper flexible cable | 12 | Nos. | 129 | 1548 | 10 | 10 | 1290 | -2 | -258 | 0 | -258 | -258
| PART ‘5’ TOTAL CARRIED TO SUMMARY |  |  |  | 157690 |  |  | 82487 |  | -75203 | 16640 | -91843 | -75203
PART- | 6 : CABLING FOR CCTV, PAS AND FAS
6.1 | CCTV
6.1.1 | 2 Core 1.0 sq.mm. FRLS, tinned copper, armoured cable. For camera power supply. |  | Mtrs. | 113 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.2 | RG59 FRLS, tinned copper, armoured cable for video transmission / TV connection (if any) |  | Mtrs. | 94 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
OR
6.1.3 | RG 59 FRLS tinned copper , flexible cable for video transmission through the conduit (including cost of conduit and its proper installation on ceiling / wall etc.) |  | Mtrs. | 76 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.4 | Providing and laying flexible Category 6 (CAT 6) cable for video transmission through the conduit (including cost of conduit and its proper installation on celling / wall etc.) Make : D-Link |  | Mtrs. | 87 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.5 | Providing and laying shield Category 6 (CAT 6) cable for video transmission through the conduit (including cost of conduit and its proper installation on celling / wall etc.) Make : D-Link |  | Mtrs. | 92 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.6 | Providing and laying armoured Category 6 (CAT 6) cable for video transmission and to be fixed on ceilling & wall with MS clamps & clips at every 1 mtr distance. (Cost of clamps and clips included with the rates) Make : D-Link | 300 | Mtrs. | 97 | 29100 | 160 | 160 | 15520 | -140 | -13580 | 0 | -13580 | -13580
6.2 | IAS - Intrusion Alarm System
6.2.1 | 4 Core 1 sq.mm. shielded copper cable in 20 mm rigid PVC Conduit with its accessories such as PVC spacers, saddles, screws, bends, couplings etc. | 200 | Mtrs. | 120 | 24000 | 75 | 75 | 9000 | -125 | -15000 | 0 | -15000 | -15000
6.3 | PAS - Panic Alarm System
6.3.1 | 2 X 40/36, SWG flexible wire for Speakers connections |  | Mtrs. | 99 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4 | FAS - Fire Alarm System
6.4.1 | 2 Core X 1.5 Sqmm solid bare copper conductor, PVC insulated, Laid up, PVC sheathed, GI round wire armoured and overall FRLS RED colour PVS sheathed cable to IS 1554 Part I latest, Cable shall be cleated on ceiling, walls; laid on trays; concealed in timber partitions etc complete as directed and required to complete the installation. (For FAS) | 200 | Mtrs. | 122 | 24400 | 122 | 122 | 14884 | -78 | -9516 | 0 | -9516 | -9516
6.4.2 | 2 Core X 1.5 Sqmm flexible copper conductor wires laid through conduits (including cost of conduit and its proper installation on ceiling / wall etc.) |  | Mtrs. | 106 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PART ‘6’ TOTAL CARRIED TO SUMMARY |  |  |  | 77500 |  |  | 39404 |  | -38096 | 0 | -38096 | -38096
PART- | 7 : EARTHING WORK
7.1 | Supplying and fixing following sizes of copper earth strips/cable complete with connections as required.
7.1.1 | 1 core 6 sq.mm copper flexible cable for UPS earthing laid through the conduit. |  | Mtrs. | 141 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.1.2 | 1 core 10 sq.mm copper flexible cable for UPS earthing laid through the conduit. | 150 | Mtrs. | 194 | 29100 | 0 | 0 | 0 | -150 | -29100 | 0 | -29100 | -29100
7.1.3 | 25 mm x 3 mm copper strip | 6 | Mtrs. | 724 | 4344 | 0 | 0 | 0 | -6 | -4344 | 0 | -4344 | -4344
7.1.4 | 25 mm x 3 mm G.I. strip |  | Mtrs. | 76 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.1.5 | 8 Swg bare copper conductor laid through the conduit |  | Mtrs. | 114 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.1.6 | 14 Swg bare copper conductor laid through the conduit |  | Mtrs. | 83 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.2 | Plate Earthing: - Supply, Installation testing and commissioning of permanent earth stations with 600 mm x 600 mm x 3.15 mm copper earth plate & (G.I. pipe for watering) buried in specially prepared, 3 meters. deep earth pits with alternate layers of charcoal & salt, complete with reducer, funnel, wire mesh & test link and brick masonry chamber with hinged type cast iron cover etc. |  | Nos. | 13842 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.3 | Pipe Earthing: - Supply, Installation testing and commissioning GI pipe earthing station including excavation, back filling, 50 mm diameter GI pipe of 3 m long, construction of inspection chamber, chamber cover (C.I), disconnecting link etc. as per specifications. |  | Nos. | 11759 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.4 | Chemical Earthing: - Maintenance free Electrical Grounding system comprising of low carbon high tensile solid electrode of sufficient length (Not less than 2.5 Mtrs) with carbon based, combination of highly conductive material to achieve earth resistance less than 2 ohm. as confirming to IS : 3043-1987, Clause 9.2.8 and 9.3 : The material, selected for Earthing Electrode, and material used should be such that it resists the corrosion complete with CI cover (suitable for vehicular movement) and required masonry work. | 3 | Nos. | 16017 | 48051 | 0 | 0 | 0 | -3 | -48051 | 0 | -48051 | -48051
| PART ‘7' TOTAL CARRIED TO SUMMARY |  |  |  | 81495 |  |  | 0 | -159 | -81495 | 0 | -81495 | -81495
PART- | 8 : SERVO BYPASS SWITCH
8.1 | Supplying, installation, testing and commissioning the following type front operated cubicle type front operated panels made out of 14 swg powder coated CRCA Sheet Steel with adequate space for cables (4 Nos)
8.1.1 | 80 Amps FP BYPASS - |  | Nos. | 13729 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.1.2 | 100 Amps FP BYPASS - |  | Nos. | 14492 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.1.3 | 125 Amps FP BYPASS - |  | Nos. | 15954 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.1.4 | 160 Amps FP BYPASS - |  | Nos. | 18009 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.1.5 | 200 Amps FP BYPASS - |  | Nos. | 19675 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PART ‘8’ TOTAL CARRIED TO SUMMARY |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
PART- | 9 : LIGHTING & POWER POINT WIRING
9.1 | Point Wiring : Wiring for the following points with 3 x 1.5 sq.mm PVC Insulated, Copper Wire in 20mm rigid PVC Conduit pipes with its accessories such as PVC spacers, saddles, screws etc. complete with 1 no. 1.5 sq.mm PVC Insulated copper wire to be used as earthing including the cost of switches / back box, plate etc.
9.1.1 | Primary Point : One Light Pt. controlled by one 6 Amps Switch (Point wiring including switches approx. 10 meters. Length) | 30 | Nos. | 1137 | 34110 | 44 | 44 | 50028 | 14 | 15918 | 15918 | 0 | 15918 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
9.1.2 | Secondary light point: looped from primary light point. ( comprising of 3 nos. 1.5 sq.mm PVC ins. Copper cond. Wire in 20mm. Rigid PVC conduit pipe without switches) | 45 | Nos. | 522 | 23490 | 46 | 46 | 24012 | 1 | 522 | 522 | 0 | 522 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
9.1.3 | Secondary light point (Two way) looped from 1st light point but inclusive of switch.(3 nos. 1.5 sq.mm PVC ins. Copper cond. Wire in 20mm. Rigid PVC conduit pipe but excluding circuit wiring) |  | Nos. | 1483 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.2 | Power Point Wiring :
9.2.1 | 6 amps Light Plug Outlets :- | 25 | Nos. | 587 | 14675 | 20 | 20 | 11740 | -5 | -2935 | 0 | -2935 | -2935
Providing of 6 amps Modular type Socket and switch(multicountry type), M.S/ G.I Box for housing the above, Modular sheet, earthing the third pin with 1.00 mm PVC Insulated Copper Conductor as a earth conductor complete in all respects as required. (Cost of wire /pipe/raceways is NOT to be included in this cost)
9.2.2 | Exhaust Fan Outlet points :- Providing of 6 amps 3Pin socket near the exhaust Fan and switch with the light switch board, G.I / M.S Box for housing the above, complete with earthing with 1.5 sq.mm. PVC insulated copper conductor/wire. | 3 | Nos. | 839 | 2517 | 0 | 0 | 0 | -3 | -2517 | 0 | -2517 | -2517
9.2.3 | 6/16 amps Power Plug Outlets :- Providing of 16 amps Modular type Socket and switch(multicountry type), Box for housing the above, Modular sheet, earthing the third pin with 2.5 sq.mm mm PVC Insulated Copper Conductor Wire, complete in all respects as required (Cost of wire /pipe/raceways is NOT to be included in this cost) | 25 | Nos. | 1283 | 32075 | 9 | 9 | 11547 | -16 | -20528 | 0 | -20528 | -20528
9.2.4 | Split A/c outdoor Box :- Providing and fixing of 20 Amps Industrial Socket outlet with top controlled by 20 A 10ka SP MCB all housed in M.S Box duly painted with IP 65, earthing the 3rd Pin with 2.5 sq.mm PVC Insulated copper conductor/wire. (excluding the cost of wires / cables) | 5 | Nos. | 2288 | 11440 |  | 0 | 0 | -5 | -11440 | 0 | -11440 | -11440
| PART ‘9’ TOTAL CARRIED TO SUMMARY |  |  |  | 118307 |  |  | 97327 |  | -20980 | 16440 | -37420 | -20980
PART- | 10 : POWER SOCKET & SWITCHES
10.1 | Supply, Installation, testing, commissioning of following feeders for Incoming/ outgoing in weatherproof MS sheet box, power sockets etc.
10.1.1 | 32 Amps 10ka SPN MCB Housed in M.S Sheet Box. |  | Nos. | 758 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.1.2 | 63 Amps 10ka FP MCB Housed in M.S Sheet Box. |  | Nos. | 1991 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.1.3 | 3 nos. of 5/15 A power sockets controlled by 1 no. of 15 A switch(multicountry sockets) | 30 | Nos. | 1226 | 36780 | 25 | 25 | 30650 | -5 | -6130 | 0 | -6130 | -6130
10.1.4 | 1 nos. of 5/15A power socket controlled by 1 no. of 15 A switch(multicountry sockets) | 25 | Nos. | 608 | 15200 | 21 | 21 | 12768 | -4 | -2432 | 0 | -2432 | -2432
10.1.5 | 3 nos. of 5/15 A power sockets without switch for CCTV power Supply unit(multicountry sockets). | 4 | Nos. | 932 | 3728 | 1.33 | 1.33 | 1239.56 | -2.67 | -2488.44 | 0 | -2488.44 | -2488.44
10.1.6 | RG -6 T.V Coaxial TV outlet Socket with Modular sheet and M.S Box included with 2 no.s of 5 Amp socket controlled by 1 No. of 15 Amp switch. |  | Nos. | 1439 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.1.7 | 2 nos. of 5/15 A power sockets controlled by 1 no. of 15 A switch (multicountry sockets for Display TV) Separate circuit for 3 nos of front side TV's to be provided. | 2 | Nos. | 1105 | 2210 | 0 | 0 | 0 | -2 | -2210 | 0 | -2210 | -2210
| PART ‘10’ TOTAL CARRIED TO SUMMARY |  |  |  | 57918 |  |  | 44657.56 |  | -13260.44 | 0 | -13260.44 | -13260.44
PART- | 11 : SUBMAINS CIRCUIT WIRING
11.1 | Circuit Wiring (Light & Raw power points): Supply and laying of following sets of wires of PVC insulated , PVC sheathed copper flexible wires in laid PVC conduits Including civil work and required accessories spacers, clamps and hardware etc.(Cost of pipe/raceways is NOT to be included)
11.1.1 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 8 meter wires) | 6 | set | 854 | 5124 | 6 | 6 | 5124 | 0 | 0 | 0 | 0 | 0
11.1.2 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 12 meter wires) | 4 | set | 1340 | 5360 | 4 | 4 | 5360 | 0 | 0 | 0 | 0 | 0
11.1.3 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 18 meter wires) | 4 | set | 2045 | 8180 | 2 | 2 | 4090 | -2 | -4090 | 0 | -4090 | -4090
11.1.4 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 24 meter wires) | 4 | set | 2733 | 10932 | 4 | 4 | 10932 | 0 | 0 | 0 | 0 | 0
11.2 | AC Wiring: Supply and laying of following cables with fixed length mentioned cable should be PVC insulated , PVC sheathed copper flexible wires in laid PVC conduits Including civil work and required accessories spacers, clamps and hardware etc.(Cost of pipe/raceways is NOT to be included)
11.2.1 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 12 meter wires) | 4 | set | 1340 | 5360 | 7 | 7 | 9380 | 3 | 4020 | 4020 | 0 | 4020 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
11.2.2 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 18 meter wires) | 5 | set | 2030 | 10150 |  | 0 | 0 | -5 | -10150 | 0 | -10150 | -10150
11.2.3 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 24 meter wires) | 4 | set | 2690 | 10760 | 6 | 6 | 16140 | 2 | 5380 | 5380 | 0 | 5380 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
11.2.4 | 2 X 4 sqmm and 1 X 2.5 sqmm (set of 12 meter wires) |  | set | 1528 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.2.5 | 2 X 4 sqmm and 1 X 2.5 sqmm (set of 18 meter wires) |  | set | 2400 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.2.6 | 2 X 4 sqmm and 1 X 2.5 sqmm (set of 24 meter wires) |  | set | 3034 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.2.7 | 2 X 6 sqmm and 1 X 4 sqmm (set of 12 meter wires) |  | set | 2284 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.2.8 | 2 X 6 sqmm and 1 X 4 sqmm (set of 18 meter wires) |  | set | 3279 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.2.9 | 2 X 6 sqmm and 1 X 4 sqmm (set of 24 meter wires) |  | set | 4979 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.3 | Computer / RAW Power Point Wiring: Supply & Installation of 3 core 2.5 sq.mm copper flexible PVC insulated sheathed wire 650V grade with ISI mark for connecting power points on work station in laid PVC conduits/raceways. One circuit wire should contains 2-3 UPS / Raw power points as least. (white colour- UPS and black colour:- RAW). (Cost of pipe/raceway is NOT to be included)
11.3.1 | 3 core 2.5 sq.mm copper flexible cable ( set of 8 meter Length) | 4 | set | 1093 | 4372 | 3 | 3 | 3279 | -1 | -1093 | 0 | -1093 | -1093
11.3.2 | 3 core 2.5 sq.mm copper flexible cable ( set of 12 meter Length) | 4 | set | 1622 | 6488 | 2 | 2 | 3244 | -2 | -3244 | 0 | -3244 | -3244
11.3.3 | 3 core 2.5 sq.mm copper flexible cable ( set of 18 meter Length) | 6 | set | 2509 | 15054 | 4 | 4 | 10036 | -2 | -5018 | 0 | -5018 | -5018
11.3.4 | 3 core 2.5 sq.mm copper flexible cable ( set of 24 meter Length) | 5 | set | 3276 | 16380 | 6 | 6 | 19656 | 1 | 3276 | 3276 | 0 | 3276 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
| PART 11’ TOTAL CARRIED TO SUMMARY |  |  |  | 98160 |  |  | 87241 |  | -10919 | 12676 | -23595 | -10919
PART- | 12 : LIGHT FITTINGS,EXHAUST FANS ETC.
12.1 | LED Light fittings
LED light design should be such that LPD (lighting Power Density) should be below 0.6 W per Sq.ft. at 400 lux level on table top.
12.1.1 | 600 x 600mm Recess mounting LED panel CRCA powder coated white housing, Slim, aesthetic CRCA powder coated bottom frame, out frame (If requires) Special translucent high transmissivity, non yellowing polycarbonate diffuser, High power, high efficiency LEDs ,Specially designed constant current driver. Lumen output should be 3000 to 4000. Wattage should be inclusive of LED and Driver losses. (cost is including outer frame if lights need to be placed in gypsum celing)
Color Temperature 5000-6000K
i | 35W - 40W | 40 | Nos | 2118 | 84720 | 34 | 34 | 72012 | -6 | -12708 | 0 | -12708 | -12708
ii | 30W - 34W |  | Nos | 2118 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iii | 25W - 30W |  | Nos | 2118 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.1.2 | Circular recess mounted LED Down lighter High power, high efficiency Chip-On-Board LED module, High transitivity, non-yellowing PMMA diffuser, Pressure die cast aluminum housing and special, wave shaped radial heat sink, black powder coated, for superior thermal performance, Aesthetic white rim molded in engineering plastic, Specially designed, easy to install mounting clips. Lumen output should be 1000 to 1300 for 16 -18W, 700 - 1000 for 10 - 12W and 600 to 700 for 6 - 8W. Wattage should be inclusive of LED and Driver losses
Color Temperature 5000-6000K
i | 16W - 18W | 35 | Nos | 922 | 32270 | 50 | 50 | 46100 | 15 | 13830 | 13830 | 0 | 13830 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
ii | 10W - 12W |  | Nos | 833 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iii | 6W - 8W |  | Nos | 715 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.1.3 | Rectangular recess mounted LED Down lighter High power, high efficiency Chip-On-Board LED module, High transitivity, non-yellowing PMMA diffuser, Pressure die cast aluminum housing and special, wave shaped radial heat sink, black powder coated, for superior thermal performance, Aesthetic white rim molded in engineering plastic, Specially designed, easy to install mounting clips. Lumen output should be 1000 to 1300 for 16 -18W, 700 - 1000 for 10 - 12W and 600 to 700 for 6 - 8W. Wattage should be inclusive of LED and Driver losses
Color Temperature 5000-6000K
i | 16W - 18W |  | Nos | 922 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | 10W - 12W |  | Nos | 833 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iii | 6W - 8W |  | Nos | 717 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.1.4 | 150mm x 1200mm recess mounting White powder coated finish CRCA housing with extruded Aluminium lip. High efficiency LEDs with long life. Special translucent satin finish virgin PMMA diffuser, Luminaire system wattage. Specially designed driver. Wattage should be inclusive of LED and Driver losses.
Color Temperature 5000-6000K
i | 25W - 28W |  | Nos | 3841 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.1.5 | 300mm x 1200mm recess mounting White powder coated finish CRCA housing with extruded Aluminium lip. High efficiency LEDs with long life. Special translucent satin finish virgin PMMA diffuser, Luminaire system wattage . Specially designed driver. Wattage should be inclusive of LED and Driver losses.
Color Temperature 5000-6000K
i | 25W - 28W |  | Nos | 4258 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.1.6 | High power, high efficiency Chip-On-Board LED module LED BAR type fitting for installation in trough lighting (similar to28W T5) for Cove lighting applications
Color Temperature 3000-4000K
i | 10W |  | Nos | 466 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | 20W | 15 | Nos | 542 | 8130 | 0 | 0 | 0 | -15 | -8130 | 0 | -8130 | -8130
Color Temperature 5000-6000K
iii | 10W |  | Nos | 466 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iv | 20W |  | Nos | 527 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.1.7 | Circular recess mounted Rechargable LED emergency Down lighter High power, high efficiency Chip-On-Board LED module, High transitivity, non-yellowing PMMA diffuser, Pressure die cast aluminum housing and special, wave shaped radial heat sink, black powder coated, for superior thermal performance, Aesthetic white rim molded in engineering plastic, Specially designed, easy to install mounting clips. Lumen output should be 1000 to 1300 for 16 -18W, 700 - 1000 for 10 - 12W and 600 to 700 for 6 - 8W. Wattage should be inclusive of LED and Driver losses
Color Temperature 5000-6000K
i | 16W - 18W |  | Nos | 988 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | 10W - 12W |  | Nos | 876 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
iii | 6W - 8W |  | Nos | 716 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.1.8 | Supply & Installation of 225 mm single phase exhaust fans ( BEE Star rated Fans as suggested by Bank or CPC team as exception / Refer Make and Model sheet,fans) with mounting frame and safety grill etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan. | 3 | Nos | 2002 | 6006 | 3 | 3 | 6006 | 0 | 0 | 0 | 0 | 0
12.1.9 | Supply & Installation of ceiling fan (BEE Star rated Fans as suggested by Bank or CPC team as exception / Refer Make and Model sheet,fans) 1400 mm sweep with all hanging accessories, electronics regulator, blades etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan. |  | Nos | 2034 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.1.10 | Supply & Installation of bracket fan 400 mm sweep, oscillating type with all fixing accessories, blades etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan. | 2 | Nos | 2449 | 4898 | 4 | 4 | 9796 | 2 | 4898 | 4898 | 0 | 4898 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
12.1.11 | Supply & Installation of pedestal fan 400 mm sweep, oscillating type with all fixing accessories, blades etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan | 2 | Nos | 2836 | 5672 | 2 | 2 | 5672 | 0 | 0 | 0 | 0 | 0
| PART ‘12’ TOTAL CARRIED TO SUMMARY |  |  |  | 141696 |  |  | 139586 |  | -2110 | 18728 | -20838 | -2110
PART- | 13 : RACEWAYS ,CONDUITS, CASSING-CAPPING
13.1 | Supply & Installation of totally concealed underfloor Al./G.I Trunking. Trunking to be of the following sizes. Excavation & refilling cost is NOT to be included. The same is to be done by Civil agency. Thickness of underfloor raceways shall be 1.60mm up to 38 mm depth and 2.0mm above 40mm depth
13.1.1 | 65 mm x 35 mm x 1.6mm |  | Mtrs. | 305 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.1.2 | 80 mm x 40 mm x 2.0mm |  | Mtrs. | 404 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.1.3 | 100 mm x 40 mm x 2.00mm |  | Mtrs. | 495 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.1.4 | 150mm x 38mm x 1.6 mm G.I Floor Raceway |  | Mtrs. | 572 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.1.5 | 300mm x 38mm x 2.0 mm G.I Floor Raceway |  | Mtrs. | 762 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.2 | Supply & Installation of Floor Junction Boxes fabricated out of GI / M.S Sheet (Powder Coated) of the following sizes as required complete with 3mm Thick SS Sheet Cover as required.
13.2.1 | 100 x 100 mm |  | Nos | 686 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.2.2 | 150 x 150 mm | 4 | Nos | 911 | 3644 | 3 | 3 | 2733 | -1 | -911 | 0 | -911 | -911
13.2.3 | 200 x 200 mm | 5 | Nos | 1048 | 5240 | 2 | 2 | 2096 | -3 | -3144 | 0 | -3144 | -3144
13.2.4 | 300 x 300 mm | 8 | Nos | 1144 | 9152 | 9 | 9 | 10296 | 1 | 1144 | 1144 | 0 | 1144 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
13.3 | Supply & Installation of totally concealed underfloor rigid PVC pipes of MMS gauge of following sizes.
13.3.1 | 20 mm | 4 | Mtrs. | 50 | 200 |  | 0 | 0 | -4 | -200 | 0 | -200 | -200
13.3.2 | 25 mm | 25 | Mtrs. | 55 | 1375 | 38 | 38 | 2090 | 13 | 715 | 715 | 0 | 715 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
13.3.3 | 32 mm | 200 | Mtrs. | 73 | 14600 | 210 | 210 | 15330 | 10 | 730 | 730 | 0 | 730 | Quantiy has exceeded WO Quantity, PM Approval is required for excess quantity
13.4 | Supply & Installation of the PVC casing capping over the wall, partition from junction box to power point
13.4.1 | 25 mm | 10 | Mtrs. | 53 | 530 | 10 | 10 | 530 | 0 | 0 | 0 | 0 | 0
13.4.2 | 50 mm | 20 | Mtrs. | 97 | 1940 | 20 | 20 | 1940 | 0 | 0 | 0 | 0 | 0
13.5 | Supplying and fixing of the following sizes of G.I Cable Trays , complete with threaded hangers, nuts bolts, washers and couplers as required for fixing of cable trays.
13.5.1 | 300 mm X 40mm x 40 mm x1.6 mm |  | R. Mtr | 861 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.5.2 | 150mm x 40mm x 40mm x 1.6 mm |  | R. Mtr | 550 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.5.3 | 100mm x 40mm x 40mm x 1.6 mm |  | R. Mtr | 482 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.6 | Supply & Installation of totally concealed underfloor / Wall rigid GI pipes conduits of of following sizes.
13.6.1 | 25 mm |  | Mtrs. | 175 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.6.2 | 50 mm |  | Mtrs. | 350 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PART ‘13’ TOTAL CARRIED TO SUMMARY |  |  |  | 36681 |  |  | 35015 |  | -1666 | 2589 | -4255 | -1666
PART - | 14 : FIRE FIGHTING WORKS
14.1 | Supply, Installation, testing, commissioning of sprinkler point complete with MS pipe, flexible pipe, valve and sprinkler complete with all accessories for the smooth operation of the system. (average costing for 1 sprinkler point for the premises of minimum 25 points) (Optional for non-branch premises only where the other part of premises includes sprinkler system: like Mall etc ) |  | set | 6059 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PART ‘14’ TOTAL CARRIED TO SUMMARY |  |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0
PART- | 15 : MISCELLANEOUS WORK
15.1 | Retaining one electrician at site till completion of IT installation and Branch launch activities. | 1 | per month per person | 17034 | 17034 | 1 | 1 | 17034 | 0 | 0 | 0 | 0 | 0 | Quantity not measureable during audit, PM confirmation required if these items should be added to the bill and Qty not Present in the WO
15.2 | Provide and fixing of air curtain at main entrance door with Remote and inbuild sensor with effective height of 7 ft to 9 ft having noise level up to 50 db and maximum air flow velocity up to 21 m/s at nozzel.
a | size 900 x 230 x 220, CFM 825 |  | No.s | 12107 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b | size 1200 x 230 x 220, CFM 1100 |  | No.s | 15134 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | size 1500 x 230 x 220, CFM 1380 |  | No.s | 18221 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.3 | Supply and installation of 1.5 KW one box /DB timer solution for switching ON/OFF signage boards in auto as per set timing. This box includes Timer, power contactor, SP MCB, Auto / Manual switch, terminal out, internal wiring including Box/DB etc. there should be 3 output from box to connect main signage and lollypop signages. (Make: L&T, Siemens, Legrand, Schneider) |  | Set | 3334 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PART ‘15’ TOTAL CARRIED TO SUMMARY |  |  |  | 17034 |  |  | 17034 |  | 0 | 0 | 0 | 0
| PART ‘1’ POWER DISTRIBUTION PANEL |  |  |  | 237741 |  |  | 212537 |  | -25204 | 0 | -25204 | -25204
| PART ‘2’ CAPACITOR PANEL |  |  |  | 55333 |  |  | 0 |  | -55333 | 0 | -55333 | -55333
| PART ‘3’ PHASE CORRECTION CIRCUIT |  |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0
| PART ‘4’ DISTRIBUTION BOARDS |  |  |  | 27304 |  |  | 38366 |  | 11062 | 38366 | -27304 | 11062
| PART ‘5’ CABLES & TERMINATIONS |  |  |  | 157690 |  |  | 82487 |  | -75203 | 16640 | -91843 | -75203
| PART ‘6’ CABLING FOR CCTV AND PAS |  |  |  | 77500 |  |  | 39404 |  | -38096 | 0 | -38096 | -38096
| PART ‘7’ EARTHING WORK |  |  |  | 81495 |  |  | 0 |  | -81495 | 0 | -81495 | -81495
| PART '8’ SERVO BYPASS SWITCH |  |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0
| PART ‘9’ LIGHTING & POWER POINT WIRING |  |  |  | 118307 |  |  | 97327 |  | -20980 | 16440 | -37420 | -20980
| PART ‘10’ POWER SOCKET & SWITCHES |  |  |  | 57918 |  |  | 44657.56 |  | -13260.44 | 0 | -13260.44 | -13260.44
| PART ‘11' SUBMAINS CIRCUIT WIRING |  |  |  | 98160 |  |  | 87241 |  | -10919 | 12676 | -23595 | -10919
| PART ‘12’ LIGHT FITTINGS,EXHAUST FANS ETC. |  |  |  | 141696 |  |  | 139586 |  | -2110 | 18728 | -20838 | -2110
| PART ‘13’ RACEWAYS ,CONDUITS, CASSING-CAPPING |  |  |  | 36681 |  |  | 35015 |  | -1666 | 2589 | -4255 | -1666
| PART ‘14’ FIRE FIGHTING WORKS |  |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0
| PART ‘15’ MISCELLANEOUS WORK |  |  |  | 17034 |  |  | 17034 |  | 0 | 0 | 0 | 0
| Total Cost of Electrification and Allied Works |  |  |  | 1106859 |  |  | 793654.56 |  | -313204.44 | 105439 | -418643.44 | -313204.44
VII | ADDITIONAL WORK
1 | Chess Board |  | Nos | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Dart Board |  | Nos | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Conference Room Table |  | Sq.ft | 789 | 0 | 94.4 | 94.4 | 74481.6 | 94.4 | 74481.6 | 74481.6 | 0 | 74481.6 | Quantity executed on site and verified during audit but not present in work order
4 | Pantry Table |  | Sq.ft | 996 | 0 | 54 | 54 | 53784 | 54 | 53784 | 53784 | 0 | 53784 | Quantity executed on site and verified during audit but not present in work order
5 | Back Painted Glass Divider |  | Sq.ft | 695 | 0 | 21 | 21 | 14595 | 21 | 14595 | 14595 | 0 | 14595 | Quantity executed on site and verified during audit but not present in work order
6 | HDMI Cable |  | Mtr | 180 | 0 | 15 | 15 | 2700 | 15 | 2700 | 2700 | 0 | 2700 | Quantity executed on site and verified during audit but not present in work order
7 | HDMI Cable |  | Mtr | 180 | 0 | 25 | 25 | 4500 | 25 | 4500 | 4500 | 0 | 4500 | Quantity executed on site and verified during audit but not present in work order
8 | LED Profile |  | Rft | 110 | 0 | 25 | 25 | 2750 | 25 | 2750 | 2750 | 0 | 2750 | Quantity executed on site and verified during audit but not present in work order
9 | Photo Frame |  | Nos | 1500 | 0 | 5 | 5 | 7500 | 5 | 7500 | 7500 | 0 | 7500 | Quantity executed on site and verified during audit but not present in work order
10 | UPS DB (100 Amp 4P -1 Nos 63 AMP 2P x 3 nos) - Legrand |  | Nos | 1000 | 0 | 1 | 1 | 1000 | 1 | 1000 | 1000 | 0 | 1000 | Quantity executed on site and verified during audit but not present in work order
11 | LED Tube 40 W - Philips |  | Nos | 500 | 0 | 3 | 3 | 1500 | 3 | 1500 | 1500 | 0 | 1500 | Quantity executed on site and verified during audit but not present in work order
| Total Cost of Additional works |  |  |  | 0 |  |  | 162810.6 | 239.4 | 162810.6 | 162810.6 | 0 | 162810.6
Note on G6: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G7: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 932.39)
Note on G8: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 459.7317)
Note on G9: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 540.8335)
Note on G10: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 16)
Note on G11: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G12: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G13: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 513.064) Found in: Measurement sheet (513.064)
Note on G14: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2) Found in: Measurement sheet (2)
Note on G15: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 18) Found in: Measurement sheet (18)
Note on G16: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 3) Found in: Measurement sheet (3)
Note on G17: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G20: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G21: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G22: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G23: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 851.395)
Note on G26: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G27: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G28: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G29: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 851.395) Found in: Measurement sheet (851.395)
Note on G30: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 29.41) Found in: Measurement sheet (29.41)
Note on G31: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G32: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G33: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G34: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G35: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G36: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G39: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2317.1297)
Note on G40: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G43: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 285.0835)
Note on G46: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 109.2835)
Note on G49: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 534.5)
Note on G50: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G51: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G52: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 851.395) Found in: Measurement sheet (851.395)
Note on G53: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 29.41) Found in: Measurement sheet (29.41)
Note on G54: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G55: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G58: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G59: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G63: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2088.4058)
Note on G64: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 86.45)
Note on G65: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1359.3185)
Note on G66: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 129.89)
Note on G69: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G70: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G73: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G74: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G77: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G80: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G83: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 418.5164)
Note on G86: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 73.3244)
Note on G87: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G90: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G91: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2191.5)
Note on G94: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G95: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G98: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 20)
Note on G99: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G100: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G101: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G102: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 29.41)
Note on G103: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 11.5)
Note on G106: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G107: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G108: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G109: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 851.395) Found in: Measurement sheet (851.395)
Note on G110: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 85.04)
Note on G111: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 84)
Note on G112: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G115: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G118: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G119: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G122: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G123: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G126: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1.25)
Note on G127: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G128: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G129: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G130: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 4)
Note on G131: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G134: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G135: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G136: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G137: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G138: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 4)
Note on G139: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G140: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G141: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G144: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G145: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 6)
Note on G146: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G147: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 4)
Note on G148: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 4)
Note on G149: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G150: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G151: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G154: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 4)
Note on G155: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G156: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G157: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 4)
Note on G161: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G162: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G163: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 5)
Note on G164: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 540.8335) Found in: Measurement sheet (540.8335)
Note on G166: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G167: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 30)
Note on G168: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G170: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G172: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G173: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G174: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 29.41) Found in: Measurement sheet (29.41)
Note on G175: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G178: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2280)
Note on G181: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G182: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 190)
Note on G183: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G184: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 851.395) Found in: Measurement sheet (851.395)
Note on G185: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G186: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G187: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 34.5)
Note on G188: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G189: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G190: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G191: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G192: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 350)
Note on G193: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G194: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G195: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G196: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 3)
Note on G197: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 30)
Note on G198: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 461.5876)
Note on G205: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1047.1893)
Note on G208: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 528.89)
Note on G209: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1917.9425)
Note on G210: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 72)
Note on G213: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G214: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G215: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G223: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 325.3562)
Note on G224: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G225: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G226: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 540.8335) Found in: Measurement sheet (540.8335)
Note on G227: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 16) Found in: Measurement sheet (16)
Note on G230: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 517.4222)
Note on G231: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G234: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G235: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G238: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G242: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G243: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 989.0292)
Note on G244: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G245: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 540.8335) Found in: Measurement sheet (540.8335)
Note on G246: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 16) Found in: Measurement sheet (16)
Note on G247: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G248: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G249: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 513.064)
Note on G252: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G253: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G254: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G258: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G259: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G260: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G263: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G264: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G268: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G269: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G270: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G271: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 851.395) Found in: Measurement sheet (851.395)
Note on G272: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 3)
Note on G273: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G274: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G275: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G279: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G280: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G281: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G282: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 851.395) Found in: Measurement sheet (851.395)
Note on G283: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 29.41) Found in: Measurement sheet (29.41)
Note on G284: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G286: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G290: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G291: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G294: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G295: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G296: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G299: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G300: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G303: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 21)
Note on G304: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G305: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G306: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 540.8335) Found in: Measurement sheet (540.8335)
Note on G309: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G310: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G313: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G316: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G319: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G320: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G321: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G322: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 540.8335) Found in: Measurement sheet (540.8335)
Note on G323: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 16) Found in: Measurement sheet (16)
Note on G326: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 10)
Note on G329: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G333: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 38.5)
Note on G336: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 103.84)
Note on G337: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G338: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G339: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 540.8335) Found in: Measurement sheet (540.8335)
Note on G340: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 16) Found in: Measurement sheet (16)
Note on G343: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 117)
Note on G346: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G349: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 51.5174)
Note on G350: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G351: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 31.5)
Note on G355: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 111.8)
Note on G359: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G360: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G363: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G364: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G367: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G368: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G369: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G370: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 851.395) Found in: Measurement sheet (851.395)
Note on G371: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 29.41) Found in: Measurement sheet (29.41)
Note on G374: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 133.8375)
Note on G375: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G376: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G377: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 8.625)
Note on G381: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 72)
Note on G384: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G385: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G386: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G389: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G390: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 201.9165)
Note on G393: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G394: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 489.504)
Note on G395: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G398: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 12)
Note on G399: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G402: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G405: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G408: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G411: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G412: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G415: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 12)
Note on G418: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G421: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G422: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G425: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G426: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G429: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G432: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G433: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G434: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G437: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G438: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G439: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G440: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 540.8335) Found in: Measurement sheet (540.8335)
Note on G441: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G442: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G443: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G444: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 617.18)
Note on G445: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G446: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 18)
Note on G447: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 3)
Note on G448: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2) Found in: Measurement sheet (2)
Note on G449: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2) Found in: Measurement sheet (2)
Note on G450: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G453: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G454: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G461: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1047.1893)
Note on G464: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 478.5775)
Note on G467: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 858.45025)
Note on G470: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1592.7034)
Note on G473: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G476: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G479: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G486: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G488: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G492: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G494: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G496: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G498: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 851.395) Found in: Measurement sheet (851.395)
Note on G501: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G504: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G507: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G515: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G529: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G546: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G556: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G557: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G558: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G561: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G562: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G563: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G565: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G584: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G588: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G590: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G592: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G594: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G596: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G598: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G600: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G606: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G621: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G636: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G663: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G671: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G675: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G681: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G690: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G700: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G711: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G721: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G734: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G744: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G755: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G765: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G784: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G789: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G794: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G800: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G805: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G812: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G817: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G828: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G830: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G832: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 28)
Note on G834: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G836: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G838: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G840: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G842: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G844: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G846: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G848: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 90)
Note on G850: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G852: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G854: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G856: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 50)
Note on G858: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 48)
Note on G862: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G864: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G866: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G868: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G870: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G872: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G874: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G876: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G878: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G880: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G882: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 5)
Note on G884: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G886: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G888: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G890: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 8)
Note on G892: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 10)
Note on G899: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G900: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G902: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G903: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G904: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G905: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 160)
Note on G908: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 75)
Note on G911: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G914: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 122)
Note on G915: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G923: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G925: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G927: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G929: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G931: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G933: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G935: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G937: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G939: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G946: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G948: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G950: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G952: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G954: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G962: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 44)
Note on G964: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 46)
Note on G966: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G969: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 20)
Note on G972: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G974: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 9)
Note on G976: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G984: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G986: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G988: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 25)
Note on G990: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 21)
Note on G992: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1.33)
Note on G994: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G996: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G1003: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 6)
Note on G1004: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 4)
Note on G1005: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G1006: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 4)
Note on G1009: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 7)
Note on G1010: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2) Found in: Measurement sheet (2)
Note on G1011: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 6)
Note on G1012: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1013: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1014: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1015: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1016: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1017: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1020: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 3)
Note on G1021: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G1022: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 4)
Note on G1023: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 6)
Note on G1033: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 34)
Note on G1034: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G1035: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G1039: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 50)
Note on G1040: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G1041: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G1045: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G1046: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G1047: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G1051: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G1055: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G1059: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G1060: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G1062: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G1063: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 540.8335) Found in: Measurement sheet (540.8335)
Note on G1067: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2088.4058) Found in: Measurement sheet (2088.4058)
Note on G1068: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 932.39) Found in: Measurement sheet (932.39)
Note on G1069: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 459.7317) Found in: Measurement sheet (459.7317)
Note on G1071: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 3)
Note on G1073: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1075: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 4)
Note on G1077: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G1084: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1085: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1086: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1087: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1088: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1091: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1092: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 3)
Note on G1093: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 2)
Note on G1094: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 9)
Note on G1097: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1098: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 38)
Note on G1099: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 210)
Note on G1102: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 10)
Note on G1103: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 20)
Note on G1106: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1107: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1108: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1111: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 38) Found in: Measurement sheet (38)
Note on G1112: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 20) Found in: Measurement sheet (20)
Note on G1117: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1122: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G1125: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 2317.1297) Found in: Measurement sheet (2317.1297)
Note on G1126: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1127: ?? NOT LINKED & MISMATCH. (BOQ: 0, Total Found: 1) Found in: Measurement sheet (1)
Note on G1129: ?? NOT LINKED. (BOQ: 0, No matching item found in any measurement sheet)
Note on G1152: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G1153: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 0)
Note on G1154: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 94.4)
Note on G1155: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 54)
Note on G1156: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 21)
Note on G1157: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 15)
Note on G1158: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 25)
Note on G1159: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 25)
Note on G1160: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 5)
Note on G1161: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 1)
Note on G1162: ? CORRECTLY LINKED to a valid total in 'Measurement sheet'. (Value: 3)

## Measurement sheet
HDFC BANK ICHALKARANJI (SECOND FLOOR) - MEASUREMENT SHEET
Sr. No. | PARTICULARS | NO | L | B/D | QTY | Remark
I | CIVIL & RELATED WORKS
1 | Demolition / Clearing Works
ii | Dismantling of existing dado tiles without plaster
| Hub Room Old Tiles | 1 | 10.52 | 9 | 94.68
|  | 1 | 6.97 | 9 | 62.73
| Gents Washroom | 1 | 16.17 | 9 | 145.53
| Pantry | 1 | 12 | 9 | 108
| Conference Room | 1 | 18.33 | 9 | 164.97
| CH Cabin Wall | 1 | 5.36 | 9 | 48.24
| RM Wall | 1 | 5.36 | 9 | 48.24
| RM near Window | 1 | 8 | 3 | 24
| RM Area Column 1 & 2 | 2 | 3.5 | 9 | 63
| RM Area Cloumn 3, 4 & 5 | 3 | 2 | 9 | 54 | Photos and CAD File with marking
| Server Window Granite 7 x 3 | 1 | 20 | 0.5 | 10
| Store Window Granite 4 x 3 | 1 | 48 | 0.5 | 24
| Store Door Frame 7 x 3 | 1 | 20 | 0.5 | 10
| Ladies Window Granite 5.5 x 4 | 1 | 19 | 0.5 | 9.5
| Gents Window Granite 2 x 3 | 1 | 10 | 0.5 | 5
| Gents Window Granite 4 x 4 | 1 | 16 | 0.5 | 8
| Pantry Window Granite 4 x 4 - 2nos / 5.5 x 4 / 2 x 3 | 1 | 45 | 0.5 | 22.5
| Conf Window Granite 2 x 3 - 4nos | 1 | 40 | 0.5 | 20
| CH Window Granite 2 x 3 | 1 | 10 | 0.5 | 5
| RM Window Granite 2 x 3 | 1 | 10 | 0.5 | 5
|  | TOTAL |  |  | 932.39
iii | Dismantling of existing plaster
| Store Room | 1 | 8.95 | 9 | 80.55
| Deduction - Door | -1 | 3 | 6.82 | -20.46
| Ladies Washroom | 1 | 5.36 | 9 | 48.24 | Photos and CAD FILE with marking
| Pantry | 1 | 10.78 | 9 | 97.02
| Deduction - Window | -1 | 5.79 | 3.77 | -21.8283
| Hub Entry Column | 1 | 2 | 9 | 18
| Graphic Wall | 1 | 28.69 | 9 | 258.21
|  | TOTAL |  |  | 459.7317
iv | Existing flooring including bedding material & PCC/IPS.
| Hub Room | 1 | 12 | 2 | 24
| Ladies Washroom | 1 | 7.93 | 5.45 | 43.2185
| Deduction - Column | -1 | 1.54 | 2.5 | -3.85
| Gents Washroom | 1 | 10.42 | 5.75 | 59.915
| Pantry near Wash Basin | 1 | 9 | 9.25 | 83.25
| Conference Room | 1 | 10 | 9 | 90
|  | 1 | 7 | 2.5 | 17.5
| CH Cabin | 1 | 5 | 7 | 35
| RM | 1 | 5 | 7 | 35
| RM near Window | 1 | 19.6 | 8 | 156.8
|  | TOTAL |  |  | 540.8335
v | Existing Doors / Windows
| Windows - Server / Store / Ladies / Gents -2 / Pantry -4 / Conf- 4 / CH / RM |  |  |  | 15 | Photos and CAD FILE with marking
| Door - Pantry |  |  |  | 1
|  | TOTAL |  |  | 16
xii | Dismantling of existing RCC 6 "/ 9" thk wall.
| For Plumbing | 2 | 1 | 1 | 2
|  | TOTAL |  |  | 2
2 | Construction of Masonry Walls
d | Do-do as 2(a) above but 150mm thk siporex / AAC / Aerocon / light weight block wall
| Hub Room Window | 1 | 7 | 3 | 21 | Photos
| Hub Room Entry | 1 | 6.97 | 9 | 62.73
| Deduction - Door | -1 | 3.2 | 7.15 | -22.88
| Hub Room | 1 | 10.52 | 10.25 | 107.83
| Electric Room | 1 | 6.94 | 10.25 | 71.135
| Utility Entry | 1 | 18.94 | 9 | 170.46
| Deduction - Door | -1 | 2.75 | 6.82 | -18.755
| Store Room Wall | 1 | 10.53 | 10.25 | 107.9325
| Deduction - Door | -1 | 2.75 | 6.82 | -18.755
| Gents Wall | 1 | 10.42 | 10.25 | 106.805
| Deduction - Door | -1 | 2.75 | 6.82 | -18.755
| Ladies Entry Wall | 1 | 7.94 | 10.25 | 81.385
| Deduction - Door | -1 | 2.75 | 6.82 | -18.755
| Store Room Window | 1 | 4 | 3 | 12
| Ladies Wall Near Column | 1 | 1.5 | 10.25 | 15.375
| Ladies Window | 1 | 5.5 | 4 | 22 | Photo
| Gents Window | 1 | 4 | 2 | 8 | Photo
| Pantry Wall | 1 | 11.77 | 10.25 | 120.6425
| Pantry Window | 1 | 3 | 2 | 6 | Photos
| Conf Window | 4 | 3 | 2 | 24 | Photos
| CH Windpw | 1 | 3 | 2 | 6 | Photos
| RM Window | 1 | 3 | 2 | 6 | Photos
| Misc |  |  |  | 0
|  | TOTAL |  |  | 851.395
4 | Plaster
a | P/A 1:4 cement plaster
| Wall Construction | 2 | 1 | 851.395 | 1702.79 | Need to check
| Ladies Column | 1 | 2 | 10.25 | 20.5
| Existing Wall in Ladies Column | 1 | 5.36 | 9 | 48.24
| Deduction - Window | -1 | 5.5 | 4 | -22
|  | -1 | 2 | 3 | -6
| Existing Wall in Gents | 1 | 17 | 9 | 153
| Deduction - Window | -1 | 1.5 | 2.2 | -3.3
|  | -1 | 1.5 | 1.5 | -2.25
| Pantry Wall | 1 | 20.02 | 9 | 180.18
| Deduction - Windows | -1 | 3.71 | 3.69 | -13.6899
| Deduction - Windows | -1 | 3.76 | 3.54 | -13.3104
| Conference Room | 1 | 18.33 | 9 | 164.97
| Deduction - Windows | -4 | 2 | 3 | -24
| CH Cabin | 1 | 6.5 | 9 | 58.5 | Photo
| RM Area | 1 | 6.5 | 9 | 58.5 | Photo
| RM Arear near Window | 1 | 5 | 3 | 15 | Photo
| Misc |  |  |  | 0
|  | TOTAL |  |  | 2317.1297
5 | Waterproofing treatment
a | P/A waterproofing treatment for toilets , pantry counter
| Ladies - Floor | 1 | 7.93 | 5.45 | 43.2185
| Ladies - Wall | 1 | 26.76 | 3 | 80.28 | Photo
| Deduction - Column | -1 | 1.54 | 2.5 | -3.85
| Deduction - Ladies Door | -1 | 2.75 | 3 | -8.25
| Gents - Floor | 1 | 10.42 | 5.75 | 59.915
| Gents - Wall | 1 | 32.34 | 3 | 97.02
| Deduction - Gents Door | -1 | 2.75 | 3 | -8.25
| Basin Counter | 1 | 5 | 2 | 10
| Basin Counter Wall | 1 | 5 | 3 | 15
| Misc |  |  |  | 0
|  | TOTAL |  |  | 285.0835
6 | Brick Bat Coba
a | Proving and Laying brick bat coba up to 150mm thk
| Ladies - Floor | 1 | 7.93 | 5.45 | 43.2185
| Deduction - Column | -1 | 1.54 | 2.5 | -3.85
| Gents - Floor | 1 | 10.42 | 5.75 | 59.915
| Basin Counter | 1 | 5 | 2 | 10
| Misc |  |  |  | 0
|  | TOTAL |  |  | 109.2835
7 | Plain Cement Concrete
a | P/E Plain cement concrete
| Hub Room | 1 | 12 | 2 | 24
| Conf Room | 1 | 18 | 9.25 | 166.5
|  | 1 | 2 | 10 | 20
| CH Cabin | 1 | 5 | 7 | 35 | Photos required
| RM Area | 1 | 5 | 7 | 35
| RM Window Area | 1 | 19.5 | 8 | 156
| Lift Area | 1 | 7 | 14 | 98
|  | TOTAL |  |  | 534.5
9 | Flooring
a | Vitrified Tile Flooring
i | Proving and Laying 1000mm x 1000mm / 800mm X 800 mm Vitrified floor tiles
| Branch / ATM Area | 1 | 1 | 2280 | 2280
| Staircase Area | 1 | 14.2 | 8.14 | 115.588
Deductions
| Staircase Area | -1 | 1.54 | 0.9 | -1.386
| Server room | -1 | 10.52 | 6.97 | -73.3244
| Store room | -1 | 10.53 | 8.95 | -94.2435
| Ladies - Floor | -1 | 7.93 | 5.45 | -43.2185
| Gents - Floor | -1 | 10.42 | 5.75 | -59.915
| Antilobby | -1 | 7.94 | 4.42 | -35.0948
| Less Balcony | -1 | 1 | 78.625 | -78.625
|  | TOTAL |  |  | 2009.7808
ii | Similar to above but for providing and fixing 75mm high skirting/border.
| Pantry | 1 | 32 | 1 | 32
| RM Area | 1 | 31.45 | 1 | 31.45
| Lift Lobby | 1 | 23 | 1 | 23
|  | TOTAL |  |  | 86.45
b | Anti-skid and anti-dust vitrified tile Flooring
iii | Proving and Laying 600mm x 600mm anti-skid and Anti-dust Vitrified floor tiles
Ground Floor
| Ladies - Floor | 1 | 7.93 | 5.45 | 43.2185
| Ladies - Wall | 1 | 26.76 | 8 | 214.08
| Deduction - Ladies Door | -1 | 2.75 | 6.82 | -18.755
| Deduction - Window | -1 | 1.5 | 2 | -3
| Gents - Floor | 1 | 10.42 | 5.75 | 59.915
| Gents - Wall | 1 | 32.34 | 8 | 258.72
| Deduction - Gents Door | -1 | 2.75 | 6.82 | -18.755
| Deduction - Window | -1 | 1.5 | 2.2 | -3.3
|  | -1 | 1.5 | 1.5 | -2.25
| Server room | 1 | 10.52 | 6.97 | 73.3244
| Store room | 1 | 10.53 | 8.95 | 94.2435
| Antilobby floor | 1 | 7.94 | 4.42 | 35.0948
| Antilobby wall | 1 | 24.72 | 8 | 197.76
| Deduction - Door | -4 | 2.75 | 6.82 | -75.02
| Cafeteria Wall | 1 | 74.19 | 8 | 593.52
| Deduction - Windows | -1 | 3.71 | 3.69 | -13.6899
| Deduction - Windows | -1 | 3.76 | 3.54 | -13.3104
| Deduction - Door | -1 | 3.2 | 7.15 | -22.88
| Deduction - Electric Panel | -1 | 4 | 7 | -28
| Deduction - Graphic Wall | -1 | 7.54 | 6.92 | -52.1768
| Deduction - Door | -1 | 2.75 | 6.82 | -18.755
| Deduction - Window | -1 | 5.78 | 3.77 | -21.7906
| Balcony Area | 1 | 31.45 | 2.5 | 78.625 | Need to check for dedication in 800 x 800
|  | 1 | 2.5 | 1 | 2.5
| Misc |  |  |  | 0
|  | TOTAL |  |  | 1359.3185
iv | Similar as 9_b_i but for providing and fixing 75mm high skirting/border.
| Balcony Area | 2 | 31.45 | 1 | 62.9
| Less door | -1 | 3 | 1 | -3
|  | 2 | 2.5 | 1 | 5
| Hub Room | 1 | 31.78 | 1 | 31.78
| Store Room | 1 | 33.21 | 1 | 33.21
|  | TOTAL |  |  | 129.89
f | Vinyl Flooring
i | Providing fixing Vinyl Anti-Static flooring 2mm thick (flexible roll) -Armstrong/LG/Tusker -
| Conference room | 1 | 32.67 | 13.33 | 435.4911
| Deduction | -1 | 5.85 | 1.84 | -10.764
|  | -1 | 1.15 | 2.33 | -2.6795
|  | -1 | 1.35 | 1.4 | -1.89
|  | -1 | 0.88 | 1.24 | -1.0912
|  | -1 | 0.25 | 2.2 | -0.55
|  | TOTAL |  |  | 418.5164
g | False Flooring
i | P/F Raised access floor (false floor app. 150 mm to 230 mm high) .
| Server | 1 | 10.52 | 6.97 | 73.3244
| Misc |  |  |  | 0
|  | TOTAL |  |  | 73.3244
h | POP covering on Flooring
ii | Providing and applying covering on flooring for floor protection
| Branch | 1 | 1 | 2280 | 2280 | Photos required
| Deduction - Washroom & Server | -1 | 31.5 | 11 | -346.5
| Staircase Area | 1 | 14.2 | 8.14 | 115.588
| Misc |  |  |  | 0
|  | TOTAL |  |  | 2049.088
10 | Pantry / Dining / Toilet Counter & Thresholds
a | Providing & fixing 600mm deep pantry counter
| Pantry counter | 1 | 1 | 20 | 20
d | Providing & Fixing of size 450mm X 900mm both sides polished divider
Gents
|  | TOTAL |  |  | 1
e | Providing & Laying 150mm wide Jet black Granite Threshold at ATM and Main Entrance
| Hub Room | 1 | 3 | 1 | 3
| Ladies | 1 | 2.75 | 1 | 2.75
| Gents | 1 | 2.75 | 1 | 2.75
| Antilobby | 1 | 2.75 | 1 | 2.75
| Store | 1 | 2.75 | 1 | 2.75
|  | 1 | 3 | 1 | 3
| Pantry | 1 | 4.16 | 1 | 4.16
| Office Entry | 1 | 4 | 1 | 4
| Staircase | 1 | 4.25 | 1 | 4.25
|  | TOTAL |  |  | 29.41
f | Providing & Laying 75 mm wide Black granite Threshold for Toilets & Pantry. (Basic Cost of Jet black granite upto Rs. 180/- sq.ft)
Ground Floor
| Gents | 2 | 1 | 5.75 | 11.5 | Double Patti 3"
| Misc |  |  |  | 0
|  | TOTAL |  |  | 11.5
11 | External Paving/Flooring/Window sill
e | Sill & jambs to windows / Doors. Providing and laying in required positions granite, slab 12 mm thk (Single piece)
| Gents | 1 | 6 | 1 | 6
|  | 1 | 6 | 1 | 6
| Ladies | 1 | 6.78 | 1 | 6.78
| Pantry | 1 | 14.8 | 1 | 14.8
|  | 1 | 14.61 | 1 | 14.61
| Pantry Door | 1 | 19.13 | 1 | 19.13
|  | 1 | 17.72 | 1 | 17.72
|  | TOTAL |  |  | 85.04
f | Sill & jambs to windows / Doors.Providing and laying in required positions black granite of 18mm thk. Upto 2100mm in length (double piece),
| Gents Washroom | 1 | 1 | 16.75 | 16.75
| Ladies Washrooom | 1 | 1 | 16.75 | 16.75
| Antilobby | 1 | 1 | 16.75 | 16.75
| Store | 1 | 1 | 16.75 | 16.75
|  | 1 | 1 | 17 | 17
|  | TOTAL |  |  | 84
15 | Plumbing
a | Internal concealed plumbing . Gents Toilet (2 no Urinal + 1 nos. wash basin + 1 no EWC) |  |  |  | 1.25
b | Internal concealed plumbing Ladies Toilet (1 Wash Basin + 1 EWC) |  |  |  | 1
c | Supply fixing and installation of Concealed stop cocks |  |  |  | 1 | Jacquard
d | Internal Plumbing work for Pantry. Water supply and drainage points for sink. |  |  |  | 1
e | Supply & fixing of Nahani trap |  |  |  | 4
f | Providing and fixing machanical driven industrial grade water meter |  |  |  | 1 | Kranti
16 | Sanitary wares (Pure white colour)
a | Providing and fixing first quality European Water closet with attached cisten of Dual Flush Cistern |  |  |  | 2 | Cera
d | Providing and fixing of single Urinal pressmatic Flushing system |  |  |  | 2 | Cera
e | Providing and fixing under/ Over counter Wash Basin |  |  |  | 4 | Cera
h | Providing and fixing Pantry staintless steel sink |  |  |  | 0
17 | Plumbing Fittings
a | Providing and fixing heavy duty pillar cock for pantry |  |  |  | 0
b | Providing and fixing angular stopcock |  |  |  | 6 | Jacquard
c | Providing and fixing heavy duty C.P. brass short body bibcock (two in one) |  |  |  | 2 | Cera
d | providing and fixing of heavy duty bottle trap. |  |  |  | 4 | Jacquard
e | Providing and fixing heavy duty pillar cock for washbasins |  |  |  | 4 | Cera
g | Providing and fixing aerators Shower Flow Aerator (Spray)
h | Providing and fixing hand type Jet Spray with adjustable nozzle |  |  |  | 2 | Cera
18 | Toilet Accessories
a | Supplying of disposable Soap Dispenser |  |  |  | 4 | Jaugar
b | Supply & fixing of Toilet paper holder |  |  |  | 2
c | Supply & fixing of SS finish Robe Hooks |  |  |  | 2
d | CP brass towel ring manufactured by Jaugar or as approved by bank or CPC team |  |  |  | 4
19 | External plumbing works.
a | Providing & laying CPVC pipes with screwed sockets, joints, and necessary pvc fittings such as socket, elbows, bends, tees etc., including making/ drilling holes in walls/ slabs and remaking good the damages in original conditions. The rate is inclusive of necessary scaffolding ( Make : Astral / Precision / Prince )
iii | 25mmdia |  |  |  | 5
b | Supplying and fixing of PVC Pipe of SWR Grade of approved company including all necessary fitting fixed with GI Clamp making necessary holes in valets, refilling the same with concrete making good the damaged portions with matching plaster complete in all respects. The rate is inclusive of scaffolding. ( Make : Astral / Precision / Prince )
ii | 4" dia |  |  |  | 30
20 | Anti Termite Treatment
a | Carrying out Ecofriendly Pest control and ant-termite
| Branch | 1 | 1 | 2280 | 2280 | Certificate | 115
|  | TOTAL |  |  | 2280
21 | Miscellaneous civil work
a | Chasing work in the existing brick/siporex up to 200mm wide and max to 75mm deep,
Pantry - 6' x 6nos + 4' x 1nos / Server -6' x 1nos / Antilobby - 6' x 1nos / Store - 6' x 1nos
b | Trenching work as per width and depth required. |  |  |  | 190 | Photos required
c | Making punctures in existing brick/siporex block up to 200mm diameter, |  |  |  | 1 | Photos required
e | Filling charges of Diesel in installed D.G. set by Bank (Vendor should submit diesel bill during final billing)
f | Civil & interior vendor will be responsible for securing the premises till the site is ready for IT hand-over with proper locking mechanism or till project is handed over to Project manager. (Daily 12 hour shift )
g | TOILET CUBICLES - Provide and fix Toilet cubicles bottom
| Gents | 1 | 5.75 | 6 | 34.5
|  | TOTAL |  |  | 34.5
h | Providing and making Core cut of in RCC slab / Beam of thickness up to 300mm,
i | Upto 75mm dia |  |  |  | 0
ii | Upto 100mm dia
iii | Upto 150mm dia |  |  |  | 1
i | Providing, fixing and Removing MS H type frame scaffolding for branch interior and exterior work. Scafolding should have flat working platform.
| Plumbing Work - 10 x 35 | 1 | 10 | 35 | 350 | Photos required
k | Prepare and maintain document list, Technical cut sheet, All type of layout, Electrical based calculations, Invoice, Purchase order of purchased goods and Materials for enrollment of the Green building certification.Cost is included with charges towards professional video recording & photo shoot of entire facility available in the premises. |  |  |  | 1
l | Charges towards the preparation of multiple options of proposed or dropped location/s recommended by regional project team (Jobs can not be more than 3 ) |  |  |  | 1
m | Providing and fixing a desktop model of CO2 Monitoring Unit having CO2 |  |  |  | 3 | Pending
n | Providing and placing medium size self watering ceramic planters (12 Inch) |  |  |  | 30
i | Providing & fixing Vinly Graphic Film of approved make
Cafeteria
| EP wall | 1 | 7.54 | 6.6 | 49.764
| L wall | 1 | 28.7 | 8.1 | 232.47
|  | -1 | 6.79 | 4.16 | -28.2464
| Conference Room | 1 | 13.5 | 8 | 108
| RM Area | 1 | 12 | 8.3 | 99.6
|  | TOTAL |  |  | 461.5876
II | POP & FALSE CEILING WORKS
1 | POP Punning
a | Providing and applying Plaster of Paris punning to wall
| Hub Room | 1 | 31.78 | 9 | 286.02
| Electric Panel | 1 | 8.64 | 7 | 60.48
| Graphic Wall | 1 | 7.54 | 6.6 | 49.764 | Photo required
| L wall | 1 | 28.7 | 8.1 | 232.47
| Less door | -1 | 6.79 | 4.16 | -28.2464
| Store | 1 | 38.97 | 10.25 | 399.4425
| Deduction - Door | -1 | 2.87 | 6.82 | -19.5734
|  | -1 | 2.67 | 6.82 | -18.2094
| RM | 1 | 15.79 | 5 | 78.95
| Deduction - Window | -1 | 6.3 | 3.16 | -19.908
| CH Cabin | 1 | 5.2 | 5 | 26
| Misc |  |  |  | 0
|  | TOTAL |  |  | 1047.1893
2 | False Ceiling
a | Gypsum board Ceiling - 12.5mm thk. single layer gypsum board
| Branch | 1 | 1 | 2280 | 2280
| Lift Lobby Area | 1 | 8 | 14.19 | 113.52
Vertical
| Pantry | 1 | 12 | 0.25 | 3
|  | 1 | 20 | 0.25 | 5
| Lift Lobby | 2 | 1.5 | 4.25 | 12.75
| Lift Lobby | 1 | 26.25 | 0.25 | 6.5625
| CH | 1 | 18 | 0.25 | 4.5
| CH Outside | 1 | 4 | 0.25 | 1
| Balcony Area | 1 | 10 | 0.25 | 2.5
| Conference Room | 1 | 72 | 0.25 | 18
| Deduction - Grid | -1 | 1 | 1917.9425 | -1917.9425
|  | TOTAL |  |  | 528.89
b | 600mm x 600mm Modular Grid Ceiling :
| Pantry | 1 | 32 | 10 | 320
|  | 1 | 12 | 10 | 120 | Pending around cassette
| Hub Room | 1 | 10.52 | 7 | 73.64
| Store | 1 | 8.5 | 8.96 | 76.16
|  | 1 | 2 | 3.46 | 6.92
| Antilobby | 1 | 8 | 4.43 | 35.44
| Ladies | 1 | 5.37 | 5.45 | 29.2665
|  | 1 | 2.55 | 3.92 | 9.996
| Gents | 1 | 10.42 | 6 | 62.52
| Lift Lobby | 1 | 10 | 8 | 80
| Office Area | 1 | 42 | 18 | 756
| Near CH | 1 | 4 | 12 | 48
|  | 1 | 2 | 10 | 20
| CH | 1 | 10 | 8 | 80
| Conference Room | 1 | 28 | 8 | 224 | Armstrong
| Column | -6 | 2 | 2 | -24
|  | TOTAL |  |  | 1917.9425
c | Providing rectangular Coves made up of Gypsum board | 1 | 72 | 1 | 72
III | CARPENTRY AND INTERIOR WORKS
1 | Partition
a | Solid Partitions
i | Providing and fixing of full height solid partition
| Conference Room | 1 | 11.39 | 8.82 | 100.4598
| Deduction - Glazing | -1 | 11.39 | 7 | -79.73
|  | 1 | 13.11 | 8.82 | 115.6302
|  | -1 | 13.11 | 7 | -91.77
|  | 1 | 13.45 | 8.82 | 118.629
| Storage | 1 | 2.07 | 8.82 | 18.2574
|  | 1 | 3.96 | 8.82 | 34.9272
| Deduction - Storage Area | -1 | 3.55 | 7 | -24.85
| CH | 1 | 16.71 | 8.82 | 147.3822
| Deduction - Glazing | -1 | 14.92 | 7 | -104.44
|  | 1 | 3.27 | 8.52 | 27.8604
| Deduction - Glazing | -1 | 3 | 7 | -21
| Façade | 1 | 31.25 | 2 | 62.5
|  | 2 | 2.5 | 2 | 10
| RM Side Façade | 1 | 23 | 0.5 | 11.5
|  | TOTAL |  |  | 325.3562
b | Glazed Partitions
i | DORMA WC profile single glazed fixed partition for 12 mm toughened glass
| Conference Room | 1 | 11.39 | 7 | 79.73
| Deduction - Door | -1 | 3 | 7 | -21
|  | 1 | 13.11 | 7 | 91.77 | Invoice
| CH Cabin | 1 | 14.92 | 7 | 104.44
| Deduction - Door | -1 | 3 | 7 | -21
|  | 1 | 3 | 7 | 21
| Pantry Entry | 1 | 0.65 | 6.78 | 4.407
| Façade Road Side | 1 | 36.04 | 4.42 | 159.2968
| Façade Near RM | 1 | 22.76 | 4.34 | 98.7784
|  | TOTAL |  |  | 517.4222
2 | Paneling Work
a | Column / Wall Paneling
ii | P/F paneling with Aluminium frame work of 18 gauge of size 50mm x 38mm
| Electric Panel | 1 | 5 | 9 | 45
| Deduction - Door | -1 | 4.5 | 7 | -31.5
| Office Entry | 2 | 4.44 | 8.86 | 78.6768
| Deduction - Door | -2 | 3.5 | 7 | -49
| Portal | 1 | 10.5 | 1 | 10.5
| Portal Side | 1 | 2.21 | 8.86 | 19.5806
| Deduction - Beam | -1 | 1.5 | 1 | -1.5
| Graphic Wall | 1 | 13.32 | 8.86 | 118.0152
|  | 1 | 0.25 | 8.86 | 2.215
| Conference Room | 1 | 32.3 | 8.86 | 286.178
|  | 1 | 10 | 8.86 | 88.6
| Deduction - Window | -1 | 5.65 | 3.59 | -20.2835
| Portal | 1 | 18.47 | 0.3 | 5.541
|  | 1 | 3.19 | 8.86 | 28.2634
| Deduction - Window | -1 | 3.14 | 3.62 | -11.3668
| Portal | 1 | 13.51 | 0.3 | 4.053
| CH | 1 | 5.15 | 8.86 | 45.629
|  | 1 | 5.36 | 4 | 21.44
| Balcony till RM | 1 | 75.4 | 4 | 301.6
| Top | 1 | 74.75 | 0.45 | 33.6375
| Portal | 1 | 11.3 | 0.3 | 3.39
| Window Sides | 1 | 12 | 0.5 | 6
| Façade | 1 | 4.36 | 1 | 4.36
|  | TOTAL |  |  | 989.0292
viii | Providing and fixing 6mm thk back painted glass (extra clear glass)
| Entry | 1 | 1.3 | 8.4 | 10.92
| RM Lobby | 1 | 7.08 | 8.4 | 59.472
|  | 1 | 7.08 | 8.4 | 59.472
|  | 1 | 5.9 | 8.4 | 49.56
|  | 1 | 5.5 | 8.4 | 46.2
|  | 1 | 7.25 | 8.4 | 60.9
| CH | 1 | 5.4 | 8.4 | 45.36
|  | 1 | 3.25 | 8.4 | 27.3
| Outside Conf | 1 | 2.3 | 8.4 | 19.32
|  | 1 | 0.4 | 8.4 | 3.36
| Conference Room | 1 | 1.9 | 8 | 15.2
|  | 1 | 2.7 | 8 | 21.6
|  | 1 | 3 | 8 | 24
|  | 1 | 4 | 8 | 32
|  | 1 | 4.8 | 8 | 38.4
|  | TOTAL |  |  | 513.064
4 | Doors
a | Main Entrance and ATM door
ii | Same as above but of size 1050 mm x 2400 mm , Floor Spring BTS 65 EN 1 - 4 | [5 empty] | 1070*2115
| Office & Pantry |  |  |  | 2 | Invoice | 1070*2060
|  | TOTAL |  |  | 2
b | Cabin and Meeting Room Doors
i | Same as above but size of the door shall be 900mm x 2100mm
| Conference room |  |  |  | 1
| CH cabin |  |  |  | 1
|  | TOTAL |  |  | 2
c | Doors for Server Room, Store Room, Pantry and Toilet.
e | iii. Pantry door : 825mm x 2100mm
| Store / Washroom Antilobby |  |  |  | 3 | One glass pending
ii | same as item 4.c-(i) but with out vision panel for toilets and wash rooms. |  |  |  | 2 |  | 740*2080
Gents / Ladies
d | Door Frames
i | Providing and fixing architraves made out of rubber wood sections over door frames and finished with approved shade of duco paint finished. (Approved Low VOC/No VOC Paints as suggested by Bank or CPC team as exception / Refer Make and Model sheet, paints) |  |  |  | 1
e | Server Room Door
i | approx size upto 1050 mm x 2100 mm (server room) |  |  |  | 1 | Certificate | 960*2180
5 | Tables
a | Branch Manager's Table
i | CH cabin |  |  |  | 1 | Without pedstel | 1500*750
|  | TOTAL |  |  | 1
d | Running Counter, Linear Desks (WBO and back office) and Pantry Counter
i | RM Tables - 1200 mm width x 600 mm deep |  |  |  | 21 |  | 1050 x 600
h | Meeting table
iii | Same as above item no. 5.h.ii Conference room table having approximate size of table 2700mm x 1050mm.
| Conference Room Table [24rft] - Additional Item |  |  |  | 0
|  | TOTAL |  |  | 0
i | Reprography Counter (Requirement to be rechecked with Project Manager at site before providing)
i | Reprography Unit of Size :-725(H) x 750mm D
| Office area | 1 | 4 | 2.5 | 10
| Misc |  |  |  | 0
|  | TOTAL |  |  | 10
6 | Storages
a | Full height storage units (use of BIFMA/Green Guard/ GPSC certified Storage Units)
i | Providing and fixing 450mm deep full height storage unit ( 2100mm high)
| HKC | 1 | 2 | 7 | 14
| Near CH | 1 | 3.5 | 7 | 24.5
Misc
|  | TOTAL |  |  | 38.5
b | Low height storage units (BIFMA/Green Guard/ GPSC certified Storage Units)
i | Storage top made of 25mm thk prelaminated particle board frosty white color
| Cluster head | 1 | 9.4 | 2.5 | 23.5
| Conference area | 1 | 8.76 | 1.5 | 13.14
| Open Office | 3 | 5.6 | 4 | 67.2
Misc
|  | TOTAL |  |  | 103.84
iii | Same as item 6.b-(i) above but overhead storage of approx. height 750mm.
| Pantry |  | 0 | 0 | 0
| Misc |  |  |  | 0
|  | TOTAL |  |  | 0
c | Slotted Angle Racks
i | Steel Slotted Angle Racks
| Store | 6 | 3 | 6.5 | 117
| Misc |  |  |  | 0
|  | TOTAL |  |  | 117
7 | Shutters
a | Providing and fixing shutters below pantry counter
| Pantry | 1 | 15.39 | 2.66 | 40.9374
| Basin | 1 | 4.6 | 2.3 | 10.58
| Misc |  |  |  | 0
|  | TOTAL |  |  | 51.5174
c | Providing and fixing DB shutters
| Electrical Panel | 1 | 4.5 | 7 | 31.5
| Misc |  |  |  | 0
|  | TOTAL |  |  | 31.5
8 | Façade Treatment
a | Aluminium Composite Panel
i | Providing and fixing tricolour (Silver - Red - Grey) Aluminium Composite Panels (ACP)
| Shutter 1 | 1 | 3 | 7.9 | 23.7
|  | 2 | 0.8 | 7.25 | 11.6
| Shutter 2 | 1 | 5.8 | 3 | 17.4
|  | 1 | 0.3 | 7 | 2.1
| Elect Panel | 1 | 2 | 4.5 | 9
| External Façade | 1 | 24 | 2 | 48
|  | TOTAL |  |  | 111.8
9 | Railing
a | SS Railing
ii | Same as item 9.a-(i) above but providing only ss pipe of dia 50 mm on one side of the wall with necessary brackets at required intervals.
| Staircase periphery | 0 | 0 | 0 | 0
| Misc |  |  |  | 0
|  | TOTAL |  |  | 0
11 | Windows
a | Supplying & fixing in position Aluminium extruder two track sliding windows
| Lift Lobby | 1 | 14 | 6 | 84
| Pantry | 2 | 3.75 | 3.75 | 28.125
|  | 1 | 3.75 | 5.79 | 21.7125
|  | TOTAL |  |  | 133.8375
d | Louvered windows for toilet and pantry windows
| Ladies | 1 | 1.5 | 2 | 3
| Gents | 1 | 1.5 | 1.5 | 2.25
|  | 1 | 1.5 | 2.25 | 3.375
|  | TOTAL |  |  | 8.625
12 | Miscellaneous
a | Soft / Pinup Board
i | Providing and fixing 12thk. Soft board
| Office area | 1 | 30 | 1.5 | 45
| CH cabin | 1 | 18 | 1.5 | 27
| Misc |  |  |  | 0
|  | TOTAL |  |  | 72
b | White Board
iii | Providing and fixing 6mm thk back painted glass
Conference room
CH cabin
|  | TOTAL |  |  | 0
c | Window Blinds
ii | Supplying and fixing roller fabric blinds
| RM Façade | 1 | 22.77 | 4.35 | 99.0495
| Window | 1 | 5.6 | 2.85 | 15.96
| Conference room | 1 | 3.13 | 3.62 | 11.3306
|  | 1 | 3.59 | 5.65 | 20.2835
| Pantry | 1 | 5.78 | 3.75 | 21.675
|  | 1 | 3.71 | 3.69 | 13.6899
|  | 1 | 3.76 | 5.3 | 19.928
|  | TOTAL |  |  | 201.9165
d | Frosted Film
ii | Providing and fixing of frosted film on glass as per design - make 3M # 7725324
| Conference Room | 1 | 11.39 | 5 | 56.95
|  | 1 | 13.11 | 5 | 65.55 | Invoice
| CH Cabin | 1 | 14.92 | 5 | 74.6
|  | 1 | 3 | 5 | 15
| Pantry Entry | 1 | 0.5 | 5 | 2.5
| Façade Road Side | 1 | 36.04 | 4.08 | 147.0432
| Façade Near RM | 1 | 22.76 | 4.08 | 92.8608
| Pantry & Office Door | 2 | 3.5 | 5 | 35
|  | TOTAL |  |  | 489.504
e | Mirror for Toilets & Strong Room
i | Providing and fixing flawless 6 mm thk. mirror of approved quality .
| Gents | 1 | 2 | 3 | 6 | Without plywood
| Ladies | 1 | 2 | 3 | 6
Misc
|  | TOTAL |  |  | 12
h | Glass Shelves
i | Providing and fixing 300 mm wide and 10 mm thick glass (use Green Pro certified Glass and make approved by Bank or CPC team as exception / Refer Make and Model sheet, Glass) shelves for momentos in Br. manager's cabin fixed with ss brackets. Size of each shelve. |  |  |  | 0
j | Plastic Board Signages
i | Providing & fixing Steel signage SS 304 in Brush finish
| IGBC / pantry/Store/Ladies/Gents/Elect/ Server |  |  |  | 12
|  | TOTAL |  |  | 12
n | Key Hanging Box
i | Providing and fixing in place key hanging box of size 600mm x 675mm |  |  |  | 1
o | Aluminium Folding Step Ladder (A` type Self-supporting plate form ladder
i | Ladder of height 8 feet (C section and steps on both sides) |  |  |  | 1
p | Miscellaneous work
i | Fixing of internal marketing poster frames supplied by the bank.
ii | Fixing of modular ATM drop box cum writing ledge supplied by the bank |  |  |  | 0
v | Supply of carpenter on monthly basis |  |  |  | 1
viii | Providing and fixing 12 mm Chair / Corner Guard
| Pantry |  |  |  | 10.6
| Gents |  |  |  | 15.74
| Ladies |  |  |  | 8
| Conference room - column |  |  |  | 72
| Conference room - glazed |  |  |  | 24.5
| Conference room - window |  |  |  | 32.14
| CH cabin |  |  |  | 61.4
| Lobby |  |  |  | 392.8
|  | TOTAL |  |  | 617.18
ix | Providing Heavy Traffic Entrance Mattin 3M Nomad Terra 8150 Floor Mat |  |  |  | 2
x | Providing and placing foot operated Dry and Wet Dust made up of 100 % food grade and BPA Free plastice having 19 Liters capacity . Bin should have individual bin slot with removable buckets and covered with outer frame. ( Make : Nayasa or RAGA) (For Desk) |  |  |  | 18 | Nayasa
xi | Providing and placing foot operated Dry and Wet Dust made up of 100 % food grade and BPA Free plastice having 33 Liters capacity . Bin should have individual bin slot with removable buckets and covered with outer frame. ( Make : Nayasa or RAGA) ( For Pantry ) |  |  |  | 3 | Nayasa
xiii | Providing and placing 6 mm transparant acrylic glass for table top to avoid lnk / stamp marking on white laminated tops. (Basis rate of acrylic is 300 Rs./ Sq.ft)
| Work stations | 0 | 0 | 0 | 0
| CH cabin | 0 | 0 | 0 | 0
| Misc |  |  |  | 0
|  | TOTAL |  |  | 0
IV | PAINTING WORKS
a | Paint on Walls
i | Providing and applying desired paint luster finish to walls, of approved shade
| Punning Qnty | 1 | 1 | 1047.1893 | 1047.1893
| Misc |  |  |  | 0
|  | TOTAL |  |  | 1047.1893
b | Acrylic Emulsion Paint on Ceiling
i | Same as item (a) but applying acrylic emulsion paint on the ceiling
| Gypsum Ceiling | 1 | 1 | 528.89 | 528.89
| Less Patta | -1 | 1 | 50.3125 | -50.3125
|  | TOTAL |  |  | 478.5775
c | Synthetic Enamel Paint (over existing MS grilles, gates, shutters etc.)
i | Same as item (a) above but applying synthetic enamel paint to MS grilles, collapsible gates, rolling shutters etc.
| RM Area | 1.5 | 22.77 | 5 | 170.775
|  | 1.5 | 6 | 5 | 45
| Conference room | 1.5 | 3.5 | 4 | 21
|  | 1.5 | 3.5 | 6 | 31.5
| Lift Lobby | 1.5 | 14 | 6 | 126
| Pantry | 1.5 | 5.78 | 3.77 | 32.6859
| Pantry | 1.5 | 3.71 | 3.69 | 20.5348
| Pantry | 1.5 | 3.76 | 5.3 | 29.892
| Balcony | 1.5 | 36.5 | 4.25 | 232.6875
| Washroom | 1.5 | 1.5 | 2 | 4.5
|  | 1.5 | 1.5 | 1.5 | 3.375
|  | 1.5 | 1.5 | 2 | 4.5
| Shutter | 2 | 4.25 | 8 | 68
|  | 2 | 4.25 | 8 | 68
|  | TOTAL |  |  | 858.4502
d | Apex Paint
i | The surface of wall or ceiling to be painted
| Lobby | 1 | 13.59 | 3 | 40.77
| Column | 1 | 3.7 | 8.9 | 32.93
| Wall | 1 | 3 | 8.9 | 26.7
| Wall Around Lift Opp Side | 1 | 39.16 | 9.5 | 372.02
| Wall Around Lift | 1 | 20.95 | 9.5 | 199.025
| Wall Around Lift Opp Side near Office entry | 1 | 15 | 9.5 | 142.5
| Wall Around Lift | 1 | 7 | 9.5 | 66.5
| Ceiling Near Pantry | 1 | 40 | 4.26 | 170.4
| Ceiling Near Office | 1 | 14 | 4.26 | 59.64
| Balcony | 1 | 2.36 | 36.28 | 85.6208
|  | 1 | 31.76 | 10.3 | 327.128
|  | -1 | 2.76 | 6.82 | -18.8232
| Ceiling | 1 | 2.78 | 31.76 | 88.2928
|  | TOTAL |  |  | 1592.7034
VI | ELECTRIFICATION AND ALLIED WORKS
PART- | 1 : POWER DISTRIBUTION PANEL
1.1.2 | TYPE I PANEL - Main LT Panel (For 1500-2500 sq. ft) |  |  |  | 1
1.1.4 | Supply & Installation of Master Switch with Key comprising of Start and Stop Push Button with key control for Start and Stop complete in powder coated MS box near the entrance of the bank. By Switching off this master switch the entire electrical equipment (Except Critical Bus) in the branch will get switched off. This switch can be operated while closing the branch. We have excluded following load from Master switch : entire UPS Load, Signage, Server room and ATM room AC's, CCTV, emergency lights and any other critical loads if any as per the seperate critical bus mentioned in panels specification as above. |  |  |  | 2
PART ‘1’ TOTAL CARRIED TO SUMMARY
PART- | 4 : DISTRIBUTION BOARDS
4.1 | Providing Lighting / UPS / Power Distribution Boards (Double Door) suitable for 415V, 50 Hz system. Dust and vermin proof having floor / wall mounting cubicle pattern with removable gland plates, with 1 set of 100 amps Copper Bus Bar, Earth and Neutral Link etc as required.
ALL MCBS SHALL BE "C" TYPE AND RATED AT 10kA
4.1.1 | UPS DB : |  |  |  |  | 40 Amps MCB to Change to 63
4.1.1.a | For 3 Phase UPS |  |  |  | 1 | 40 Amps MCB to Change to 63
4.1.3.b | TPN, 8 Way (above 2500 Sq. ft area) |  |  |  | 1 | Legrand
4.1.4 | Lighting DB :
4.1.4.b | TPN, 8 Way (above 2500 Sq. ft area) |  |  |  | 1 | 40 Amps MCB to Change to 63
PART- | 5 : CABLES & TERMINATIONS
5.1 | Supply , Installation of 1100V Grade PVC insulated , PVC sheathed GI wire armored Aluminium/ copper standard conductor , Cable of following sizes to be laid in on wall complete with dressing saddling clamping etc. Including civil work and required accessories.
5.1.3 | 3½ Core 70 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  |  |  | 28
| Panel to Near Meter Room |  | 1 | 28 | 28
5.1.11 | 4 Core 4 sq.mm 1.1 KV Grade Copper Ar. Cable |  |  |  | 90
| Cassatte AC 1 |  | 1 | 14 | 14
| Cassatte AC 2 |  | 1 | 16 | 16
| Cassatte AC 3 |  | 1 | 19 | 19
| Cassatte AC 4 |  | 1 | 20 | 20
| Cassatte AC 5 |  | 1 | 21 | 21
5.1.15 | 1 Core 16 sq.mm. copper flexible cable |  |  |  | 50
| UPS IN/ UPS DB/ UPS |  | 4 | 12.5 | 50
5.1.16 | 1 Core 10 sq.mm. copper flexible cable |  |  |  | 48
| UPS DB To UPS |  | 2 | 5 | 10
| UPS DB To 1st Floor UPS DB |  | 2 | 5 | 10
| LD To Panel |  | 4 | 3 | 12
| PD To Panel |  | 4 | 4 | 16
5.2. | End termination of the following sizes of 1100V, Aluminium/copper (as per conductor), PVC insulated and sheathed armoured cables with single compression brass cable glands & crimping type Aluminum / Copper lugs, complete with all hardware etc. One end connection of a cable (with 3/4 core) to be consider as 1 end termination.
5.2.3 | 3½ Core 70 sq.mm 1.1 KV Grade Aluminium Ar. Cable |  |  |  | 2
5.2.11 | 4 Core 4 sq.mm 1.1 KV Grade Copper Ar. Cable |  |  |  | 5
5.2.15 | 1 Core 16 sq.mm. copper flexible cable |  |  |  | 8
5.2.16 | 1 Core 10 sq.mm. copper flexible cable |  |  |  | 10
PART ‘5’ TOTAL CARRIED TO SUMMARY
PART- | 6 : CABLING FOR CCTV, PAS AND FAS
6.1.6 | Providing and laying armoured Category 6 (CAT 6) cable for video transmission and to be fixed on ceilling & wall with MS clamps & clips at every 1 mtr distance. (Cost of clamps and clips included with the rates) Make : D-Link |  |  |  | 160
| Serevr To RM 1 |  | 1 | 35 | 35
| Serevr To RM 2 |  | 1 | 31 | 31
| Serevr To RM 3 |  | 1 | 29 | 29
| Serevr To RM 4 |  | 1 | 20 | 20
| Serevr To Main Entrance |  | 1 | 27 | 27
| Serevr To Pantry |  | 1 | 13 | 13
| Serevr To Server |  | 1 | 5 | 5
6.2.1 | 4 Core 1 sq.mm. shielded copper cable in 20 mm rigid PVC Conduit with its accessories such as PVC spacers, saddles, screws, bends, couplings etc. |  |  |  | 75
| CH Cabin Panic |  | 1 | 25 | 25
| Main Entrance MC |  | 1 | 21 | 21 | Measurement are till 2nd floor core cut only
| Patry Entrance MC |  | 1 | 11 | 11
| Hotter |  | 1 | 13 | 13
| Serevr Room Door Keypad |  | 1 | 5 | 5
6.4 | FAS - Fire Alarm System
6.4.1 | 2 Core X 1.5 Sqmm solid bare copper conductor, PVC insulated, Laid up, PVC sheathed, GI round wire armoured and overall FRLS RED colour PVS sheathed cable to IS 1554 Part I latest, Cable shall be cleated on ceiling, walls; laid on trays; concealed in timber partitions etc complete as directed and required to complete the installation. (For FAS) |  |  |  | 122
| SD 1 To SD 2 |  | 1 | 3 | 3
| SD 2 To SD 3 |  | 1 | 3 | 3
| RI |  | 1 | 3 | 3
| SD 3 To SD 4 |  | 1 | 4 | 4
| SD 4 To SD 5 |  | 1 | 5 | 5
| SD 5 To SD 6 |  | 1 | 5 | 5
| SD 6 To SD 7 |  | 1 | 4 | 4
| SD 7 To SD 8 |  | 1 | 4 | 4
| SD 8 To SD 9 |  | 1 | 5 | 5
| SD 9 To SD 10 |  | 1 | 7 | 7
| RI |  | 1 | 3 | 3
| SD 10 To SD 11 |  | 1 | 8 | 8
| SD 11 To SD 12 |  | 1 | 6 | 6
| SD 12 To SD 13 |  | 1 | 3 | 3
| RI |  | 1 | 2 | 2
| SD 13 To SD 14 |  | 1 | 4 | 4
| RI |  | 1 | 3 | 3
| HD |  | 1 | 5 | 5
| RI |  | 1 | 3 | 3
| SD 14 To SD 15 |  | 1 | 5 | 5
| SD 15 To SD 16 |  | 1 | 4 | 4
| Hotter 1 |  | 1 | 7 | 7 | Measurement are till 2nd floor core cut only Pannel
| Hotter 2 |  | 1 | 21 | 21 | Measurement are till 2nd floor core cut only Pannel
| Panel to 1 SD |  | 1 | 5 | 5 | Measurement are till 2nd floor core cut only Pannel
PART ‘6’ TOTAL CARRIED TO SUMMARY
PART- | 7 : EARTHING WORK
7.1.2 | 1 core 10 sq.mm copper flexible cable for UPS earthing laid through the conduit.
7.1.3 | 25 mm x 3 mm copper strip
7.4 | Chemical Earthing: - Maintenance free Electrical Grounding system comprising of low carbon high tensile solid electrode of sufficient length (Not less than 2.5 Mtrs) with carbon based, combination of highly conductive material to achieve earth resistance less than 2 ohm. as confirming to IS : 3043-1987, Clause 9.2.8 and 9.3 : The material, selected for Earthing Electrode, and material used should be such that it resists the corrosion complete with CI cover (suitable for vehicular movement) and required masonry work.
PART- | 9 : LIGHTING & POWER POINT WIRING
9.1.1 | Primary Point : One Light Pt. controlled by one 6 Amps Switch (Point wiring including switches approx. 10 meters. Length) |  |  |  | 44 | Legrand
9.1.2 | Secondary light point: looped from primary light point. ( comprising of 3 nos. 1.5 sq.mm PVC ins. Copper cond. Wire in 20mm. Rigid PVC conduit pipe without switches) |  |  |  | 46 | Legrand
9.2 | Power Point Wiring :
9.2.1 | 6 amps Light Plug Outlets :- |  |  |  | 20 | 4 Pending
9.2.2 | Exhaust Fan Outlet points :- Providing of 6 amps 3Pin socket near the exhaust Fan and switch with the light switch board, G.I / M.S Box for housing the above, complete with earthing with 1.5 sq.mm. PVC insulated copper conductor/wire.
9.2.3 | 6/16 amps Power Plug Outlets :- Providing of 16 amps Modular type Socket and switch(multicountry type), Box for housing the above, Modular sheet, earthing the third pin with 2.5 sq.mm mm PVC Insulated Copper Conductor Wire, complete in all respects as required (Cost of wire /pipe/raceways is NOT to be included in this cost) |  |  |  | 9 | Legrand
PART- | 10 : POWER SOCKET & SWITCHES
10.1.3 | 3 nos. of 5/15 A power sockets controlled by 1 no. of 15 A switch(multicountry sockets) |  |  |  | 25 | Legrand
10.1.4 | 1 nos. of 5/15A power socket controlled by 1 no. of 15 A switch(multicountry sockets) |  |  |  | 21 | Legrand
10.1.5 | 3 nos. of 5/15 A power sockets without switch for CCTV power Supply unit(multicountry sockets). |  |  |  | 1.33 | Legrand
10.1.7 | 2 nos. of 5/15 A power sockets controlled by 1 no. of 15 A switch (multicountry sockets for Display TV) Separate circuit for 3 nos of front side TV's to be provided.
PART- | 11 : SUBMAINS CIRCUIT WIRING
11.1 | Circuit Wiring (Light & Raw power points): Supply and laying of following sets of wires of PVC insulated , PVC sheathed copper flexible wires in laid PVC conduits Including civil work and required accessories spacers, clamps and hardware etc.(Cost of pipe/raceways is NOT to be included)
11.1.1 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 8 meter wires) |  |  |  | 6
11.1.2 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 12 meter wires) |  |  |  | 4
11.1.3 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 18 meter wires) |  |  |  | 2
11.1.4 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 24 meter wires) |  |  |  | 4
11.2 | AC Wiring: Supply and laying of following cables with fixed length mentioned cable should be PVC insulated , PVC sheathed copper flexible wires in laid PVC conduits Including civil work and required accessories spacers, clamps and hardware etc.(Cost of pipe/raceways is NOT to be included)
11.2.1 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 12 meter wires) |  |  |  | 7
11.2.3 | 2 X 2.5 sqmm and 1 X 1.5 sqmm (set of 24 meter wires) |  |  |  | 6
11.3 | Computer / RAW Power Point Wiring: Supply & Installation of 3 core 2.5 sq.mm copper flexible PVC insulated sheathed wire 650V grade with ISI mark for connecting power points on work station in laid PVC conduits/raceways. One circuit wire should contains 2-3 UPS / Raw power points as least. (white colour- UPS and black colour:- RAW). (Cost of pipe/raceway is NOT to be included)
11.3.1 | 3 core 2.5 sq.mm copper flexible cable ( set of 8 meter Length) |  |  |  | 3
11.3.2 | 3 core 2.5 sq.mm copper flexible cable ( set of 12 meter Length) |  |  |  | 2
11.3.3 | 3 core 2.5 sq.mm copper flexible cable ( set of 18 meter Length) |  |  |  | 4
11.3.4 | 3 core 2.5 sq.mm copper flexible cable ( set of 24 meter Length) |  |  |  | 6
PART- | 12 : LIGHT FITTINGS,EXHAUST FANS ETC.
12.1 | LED Light fittings
LED light design should be such that LPD (lighting Power Density) should be below 0.6 W per Sq.ft. at 400 lux level on table top.
12.1.1 | 600 x 600mm Recess mounting LED panel CRCA powder coated white housing, Slim, aesthetic CRCA powder coated bottom frame, out frame (If requires) Special translucent high transmissivity, non yellowing polycarbonate diffuser, High power, high efficiency LEDs ,Specially designed constant current driver. Lumen output should be 3000 to 4000. Wattage should be inclusive of LED and Driver losses. (cost is including outer frame if lights need to be placed in gypsum celing)
Color Temperature 5000-6000K
i | 35W - 40W |  |  |  | 34
12.1.2 | Circular recess mounted LED Down lighter High power, high efficiency Chip-On-Board LED module, High transitivity, non-yellowing PMMA diffuser, Pressure die cast aluminum housing and special, wave shaped radial heat sink, black powder coated, for superior thermal performance, Aesthetic white rim molded in engineering plastic, Specially designed, easy to install mounting clips. Lumen output should be 1000 to 1300 for 16 -18W, 700 - 1000 for 10 - 12W and 600 to 700 for 6 - 8W. Wattage should be inclusive of LED and Driver losses
Color Temperature 5000-6000K
i | 16W - 18W |  |  |  | 50
ii | 20W |  |  |  | 0
12.1.8 | Supply & Installation of 225 mm single phase exhaust fans ( BEE Star rated Fans as suggested by Bank or CPC team as exception / Refer Make and Model sheet,fans) with mounting frame and safety grill etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan. |  |  |  | 3 | V Guard
12.1.10 | Supply & Installation of bracket fan 400 mm sweep, oscillating type with all fixing accessories, blades etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan. |  |  |  | 4 | Crompton
12.1.11 | Supply & Installation of pedestal fan 400 mm sweep, oscillating type with all fixing accessories, blades etc. complete. Make:- Usha, Crompton, Bajaj, Khaitan |  |  |  | 2 | Crompton
PART- | 13 : RACEWAYS ,CONDUITS, CASSING-CAPPING
13.2 | Supply & Installation of Floor Junction Boxes fabricated out of GI / M.S Sheet (Powder Coated) of the following sizes as required complete with 3mm Thick SS Sheet Cover as required.
13.2.2 | 150 x 150 mm |  |  |  | 3
13.2.3 | 200 x 200 mm |  |  |  | 2
13.2.4 | 300 x 300 mm |  |  |  | 9
13.3 | Supply & Installation of totally concealed underfloor rigid PVC pipes of MMS gauge of following sizes.
13.3.2 | 25 mm |  |  |  | 38
13.3.3 | 32 mm |  |  |  | 210
13.4 | Supply & Installation of the PVC casing capping over the wall, partition from junction box to power point
13.4.1 | 25 mm |  |  |  | 10
13.4.2 | 50 mm |  |  |  | 20
PART- | 15 : MISCELLANEOUS WORK
15.1 | Retaining one electrician at site till completion of IT installation and Branch launch activities. |  |  |  | 1
VII | ADDITIONAL WORK (As per site requirement and prior to PM confirmation )
1 | Chess Board |  |  |  | 0 | On Site
2 | Dart Board |  |  |  | 0 | On Site
3 | Conference Room Table | 1 | 23.6 | 4 | 94.4
4 | Pantry Table | 3 | 6 | 3 | 54
5 | Back Painted Glass Divider | 7 | 3 | 1 | 21
6 | HDMI Cable 1 |  |  |  | 15
7 | HDMI Cable 2 |  |  |  | 25
8 | LED Profile |  |  |  | 25
9 | Photo Frame |  |  |  | 5 | (Size 1 x 1.5 Ft)
10 | UPS DB (100 Amp 4P -1 Nos 63 AMP 2P x 3 nos) - Legrand |  |  |  | 1
11 | LED Tube 40 W - Philips |  |  |  | 3

## Debit
U.Code | Sr.No | Particulars | Unit | Rate | Earlier Qty | Eariler Amount | Revised Qty as per CWI | Final Amount | Remarks
Civil & related works
i | i | Providing and fixing in place, branch manager's table of size 1575mm x 675mm(worktop size)comprising of 25mm thick table top made of medium density particle board with side credenza of size 400mm deep and 900mm long having sliding shutters with locks ( Make : Ebco ) and a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high Density particle board. The table top to have post form edge. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware .( Make : Ebco) all the external surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with 0.8 mm thick laminate of approved shade. all complete as directed.( All furniture hardware should be Ebco Make ) | Nos | 28249 | 2 | 56498 | 1.75 | 49435.75 | A 25% debit has been imposed due to the non-provision of the keyboard tray and 3-drawer pedestal as per the approved specifications and the quantity has been rounded off accordingly
III_5.b.iii | iii | same as item 5(a) above but size of the worktable to be 1200mm x 675mm with drawer pedestal and without side credenza. |  | 20488 | 8 | 163904 | 7.65 | 156733.2 | A debit of ₹900 has been imposed due to the non-provision of the keyboard tray as per the approved specifications, and the quantity has been rounded off accordingly
III_5.d.i | i | Providing and fixing in place 600mm deep running counter made of medium density particle board with post form edge profile for 25mm thick table top, Consisting of a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board. All complete including key board drawer, M.S. Powder coated Cable tray to place electrical sockets on it, CPU trolley and necessary hardware.All the exposed surfaces to be finished with 1.0mm thick laminate.( All furniture hardware should be Ebco Make ) |  | 16568 | 2 | 33136 | 1.89 | 31313.52 | A debit of ₹900 has been imposed due to the non-provision of the keyboard tray as per the approved specifications, and the quantity has been rounded off accordingly
III_5.e.i | i | Providing and fixing welcome desk consisting of two worktops (laminate and glass/granite) with a cabinet to house FRFC made of 19mm thick BWR plywood top, sides finished in 1.0mm thick laminate of approved shade. The table shall have a 3 drawer pedestal of size 400mm x 500 mm x700mm consisting of 2nos. drawer of 150mm deep and 300mm deep filing drawer having common lock ( Make : Ebco ) including modesty apron to be made out of 19mm thick BWR plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) /high particle board. with key boards and CPU stand complete with all hardware etc. all the exposed edges to have wooden lipping stained to match the laminate and Melaminee finished. all the internal surfaces to be hand Melamine Polished. ( All furniture hardware should be Ebco Make ) |  | 24336 | 1 | 24336 | 0.96 | 23362.56 | A debit of ₹900 has been imposed due to the non-provision of the keyboard tray as per the approved specifications, and the quantity has been rounded off accordingly
III_5.f.i | i | P/f Double level teller counter made out of 19mm thick plywood (use Plywood which are "Free of Added Urea Formaldehyde" (required) and Green Pro certified (Mandatory) and make approved by Bank or CPC team as exception / Refer Make and Model sheet, BWR Plywood) and finished in laminate one at 750mm and other at 1200mm level. Top level counter to be finished in jet black granite with double molding. The upper most worktop to have vertical barriers in form of 8 mm thick toughen glass mounted on ss finish fabricated brackets for cash transactions. Teller to be provided with 4 nos. equal sized drawers, one key board at every 1200mm length. There should be a vertical barrier separating the adjacent counter at every 1200mm length. All the exposed surfaces to be finished with 1.0mm thick laminate and internal surfaces to be finished with hand Melamine Polish. all 5 S compliances as per bank's requirements to be followed. ( All furniture hardware should be Ebco Make ) | R.ft | 3813 | 4.44 | 16929.72 | 4.2 | 16014.6 | A debit of ₹900 has been imposed due to the non-provision of the keyboard tray as per the approved specifications, and the quantity has been rounded off accordingly
ELECTRIFICATION AND ALLIED WORKS
VI_1.1.2 | 1.1.2 | TYPE I PANEL - Main LT Panel (For 1500-2500 sq. ft) | Nos | 155313 | 1 | 155313 | 0.935 | 145217.655 | A 6% debit has been imposed due to the non-provision of 1 No. 32A TPN MCB and 1 No. 80A TP MCCB (Incomer) as per the approved specification.

## Documnets
Sr. No | Description | Unit | Qty Claimed | Photos and Documents Requird
Demolition / Clearing Works
1 | Dismantling of existing dado tiles without plaster | Sq.ft | 932.39 | Photos required & Existing Layout with Marking and CAD File
2 | Dismantling of existing plaster | Sq.ft | 459.73 | Photos required & Existing Layout with Marking and CAD File
3 | Existing flooring including bedding material & PCC/IPS. | Sq.ft | 540.83 | Photos required
4 | Windows and Door | Nos | 16 | Photos required & Existing Layout
5 | Dismantling of existing RCC 6 "/ 9" thk wall. | Sq.ft | 2 | Photos required
6 | Construction of Masonry Walls
| Hub Room Window | Sq.ft | 21 | Photos required
| Ladies Window | Sq.ft | 22
| Gents Window | Sq.ft | 8
| Pantry Window | Sq.ft | 6
| Conf Window | Sq.ft | 24
| CH Windpw | Sq.ft | 6
| RM Window | Sq.ft | 6
7 | Plaster
| CH Cabin | Sq.ft | 58.5
| RM Area | Sq.ft | 58.5
| RM Arear near Window | Sq.ft | 15
8 | Waterproofing Photos | Sq.ft | 285.08 | Photos required
9 | Brickbat work | Sq.ft | 109.28 | Photos required
10 | PCC Work | Sq.ft | 534.5 | Photos required
11 | POP covering on Flooring | Sq.ft | 2191.5 | Photos required Staircase Area As well
12 | Trenching work as per width and depth required. | R.ft | 190 | Photos required
13 | Making punctures in existing brick/siporex block up to 200mm diameter, | Nos | 1 | Photos required
14 | MS H Type Frame | Sq.ft | 350 | Photos required
15 | C02 Monitoring | Nos | 3 | Pending
16 | POP Punning - Graphic Wall | Sq.ft | 49.76 | Photos required
17 | 600mm x 600mm Modular Grid Ceiling : Around AC in Pantry |  |  | Photos required
18 | Washroom Antilobby Door Glass fixed Photos | Nos | 1 | Photos required
19 | For 3 Phase UPS 40 Amp MCB to 63 AMP MCB Change | Nos | 1 | Geo Tag Photos required
20 | TPN, 8 Way (above 2500 Sq. ft area) 40 Amp MCB to 63 AMP MCB Change | Nos | 1 | Geo Tag Photos required
21 | TPN, 8 Way (above 2500 Sq. ft area) -40 Amp MCB to 63 AMP MCB Change | Nos | 1 | Geo Tag Photos required
22 | 6 amps Light Plug Outlets :- Conference Room | Nos | 4 | Geo Tag Photos required
23 | Wooden Fire Rated Door |  |  | Certficate Required
24 | All Inovices (Including Painting Plumbing, Eletrical,Carpentry, Waterproofing, Cement, Blockwork, Tuffen glass, Modular) |  |  | As mentioned, all required invoices
25 | Glazed Glass Invoice
26 | Frosted Film
27 | IGBC |  |  | Required Product Certficate that has been used in the branch
28 | CAR and WC |  |  | Policies

## Make and Models
LIST OF MATERIALS & APPROVED BRANDS FOR HDFC Bank
| Material | IMP Criteria | Approved brands
Civil Items
1 | Cement | Green Pro Certification | ACC 1. ACC Suraksha Power 2. ACC Gold Water Shield 3. ACC F2R Superfast 4. ACC HPC Long Life 5. ACC Concrete+ Xtra Strong JK Lakshmi Cement Ltd 1. COC 2. PPC 3. Sixer 4. HDP 5. PHDP 6. Platinum 7. PSC 8. PRO Plus UltraTech Cement Limited 1. UltraTech Premium, Composite Cement 2. UltraTech Weather Plus, Composite Cement 3. UltraTech Weather Plus, Portland Pozzolana Cement 4. UltraTech, Composite Cement 5. UltraTech, Portland Pozzolana Cement Dalmia Cement 1. Vajram Cement - Portland Pozzolana Cement (PPC) JSW Cement Ltd 1. portland Slag Cement 2. Composite Cement
2 | Ready Mixed Concrete | Green Pro Certification | ACC : ACC ECOPACT ACC Feathercrete ACC Fillcrete ACC Flowcrete ACC Permicrete ULTRATECH : Ultratech Duracon Ultratech Flowfill Ultratech Free flow Ultratech Hypercon
3 | Aerocon Block | Green Pro Certification | Ultra Tech 1. Extralite- AAC Blocks JK Lakshmi Cement Ltd 1.JK Smartblox Godrej 1. Tuff Blocks JVS Comatsco Industries Pvt. Ltd 1. Ecolite AAC Blocks KD Infra 1.Brikolite AAC Block UAL Industries Ltd 1.KON_CRETE AAC blocks UltraTech Cement Limited 1. Xtralite - AAC Blocks Zuari Cement Limited 1. Super lite- AACblocks
4 | Waterproofing | NA | Pedilite /Roff
5 | False Flooring | NA | United insulation /Flexi floor (aet) / Kebao / Innerspace
6 | Bubble sheet | NA | Cello
7 | SS Sink | NA | Nirali
8 | Sanitarywares & Faucets
8.01 | Pillar cock | Water Flow Rate at 3 Bar pressure | Jaguar Use Jaquar Make with model no. 021KNG with flow rate of 2.5 LPM @ pressure of 3 Bar. Pl note Suffix G in model no. is critical to get desired flow rate. Cera F2013101- FOUNTAIN - Pillar cock with aerator F1001101- PLATINUM - Pillar cock with aerator F1015101-VICTOR - Pillar cock with aerator Hindware : F730002CP : Contessa Neo Pillar Cock Long Neck F740001CP : Dove Pillar cock
8.02 | Sink cock | Water Flow Rate at 3 Bar pressure | Jaguar Use Jaquar Make and same model with Suffix GD (like 349 KNGD) with flow rate of 3.8 LPM @ pressure of 3 Bar. Pl note Suffix GD in model no. is critical to get desired flow rate. Cera F1016251-CHELSEA - Sink cock (wall mounted) with 200 mm (8″) long swivel spout and wall flange F1002251 - CARBON - Sink cock (wall mounted) with 150 mm (6″) long swivel spout and aerator F2013251 - FOUNTAIN - Sink cock (wall mounted) with 150 mm (6″) long swivel spout and aerator Hindware F200024CP :Classik Sink Cock With Swivel Casted Spout (Wall Mounted) F120021CP :Axxis Sink Cock With Normal Swinging Spout (Wall Mounted)
8.03 | Two way bib cock | Water Flow Rate at 3 Bar pressure | Jaguar Use Jaquar Make with model no. 043NG with flow rate of 2.5 LPM @ pressure of 3 Bar. Pl note Suffix G in model no. is critical to get desired flow rate. Cera F2013163-FOUNTAIN - 2-way Bib cock with single handle and wall flange F1003161- TITANUM - 2-Way bib cock with wall flange and aerator Hindware : F200004CP :Classik Bib Cock 2 In 1 F120003CP :Axxis Bib Cock 2 In 1
8.04 | Angle cock | NA | Jaguar : CON-CHR-059KN Hindware : F200005CP :Classik Angular Stop Cock
8.05 | Concealed stop cock | NA | Jaguar : CON-CHR-083FTK Hindware : F200007CP : Classik Concealed Stop Cock- 15 / 20 mm
8.06 | Urinal - Flush Valve | Water Flow Rate | Jaguar Use Jaquar Make with model no. 077G with flow rate of 1.5 LPF. Pl note Suffix G in model no. is critical to get desired flow rate. Cera - F9020203 : Self closing angle cock pressmatic for urinal with wall flange and 200 mm connecting pipe
8.07 | Tower rail (450 mm) | NA | ACN-1111BNM
8.08 | Towel ring | NA | ACN-CHR-1121N
8.09 | Soap dispenser | NA | ACN-CHR-1135N
8.1 | Toilet roll holder | NA | ACN-CHR-1153S
8.11 | Hook | NA | ANC-1161N
8.12 | Jet spray | Water Flow Rate at 3 Bar pressure | Jaguar Use Jaquar Make with model no. 565GA with flow rate of 6 LPM @ pressure of 3 Bar. Pl note Suffix GA in model no. is critical to get desired flow rate. Cera F8030101 / F8030102 / F8030103 / F8030104AB /F8030105AB / F8030109AB - Health Faucet ABS body with 1 meter SS braided connection pipe
8.13 | Waste coupling | NA | ACD-709
8.14 | Bottle trap | NA | ACD-769L300x190
8.15 | Connector pipe | NA | ACD-805B
8.16 | SS Sink | NA | Nirali - Grace plain - Small (485mm x 410mm) glossy
8.17a | Wall hung Water closet (Ceramic Fitting) | Green Pro Certification | Hindware - ATHENS One Piece Closet 92511/ Mario Extended Wall Mounted Closet 20084 / Element 92082 /Florence Coupled Closet 92058 / Constellation Extended Wall Mounted Closet 20028. Cera - CAMPBELL S1021109 S Trap 120 mm S1021110 P Trap/ CURTIS S1031111 P Trap /
8.17b | Water Closet With Flush Valve | Water Flow rate | Jaguar Suggesting use of jaguar make with model number 1085G, 1085SQG, 1085DFPG, 1089G, 1089SQG, 1089DFPG (for flush valves) with flow rates of 4/2 LPF. Pl note Suffix G in model no is critical to get desired flow rate. Cera: F8010106 : Flush valve concealed push type (Double flow) 25 mm (1”) 4/2 LPF
8.17c | Water Closet With Cistern | Water Flow rate | Cera S1021103 + S1060101 - Calibre deluxe ewc-S + Calibre cistern S1021104 + S1060104 -Callaghan two pc ewc-S + Callaghan cistern S1013110 - Campbell one pc ewc-S 110 mm S1021120 + B1020105 - Curtis two pc ewc-S S1021113 + S1060106 - Cruse two pc ewc-S S1041105 - Compact wall hung S1031111 + B1020105 - Curtis wall hung with Curtis PVC Cistern S1021132 + S1060122 - Cimberly two piece Water closet-S trap with Cimberly cistern Hindware Cleo - S-190/220 ESSENCE - 92051 ENIGMA SLIM 92502 ELEMENT 92081
8.19 | Wall mounted / Table top Wash basin | Green Pro Certification | Hindware - Compac 10004 / Cleo 10012 WHITE CERA Wash basins - CHIME S2040139 / CAMMY : S2090127 / CORBA : S2020104
8.2 | Urinal | Green Pro Certification | CERA Sanitaryware - URINAL Urinal Flat Back with integrated EFS 360 x 330 x 740 mm (S4010101) Hindware : 60020 : FB- Eureka Standard Urinal
8.21 | Under counter wash basin | NA | Hindware Round 10065 / Zen 10049 WHITE / Cera
10 | PVC/ CPVC/UPVC pipe | NA | Astral / Prince / Precision
11 | Anti Termite | NA | PCI / Hicare
Flooring
1 | Tiles | Green Pro Certification | Somany : Ultra Charge -Vitro - Milky White (800 x 800) Ultra charge - Vitro - Berlineta White ( 800 x 800 ) Delmon Beige - (600 x 600) Prism Johnson JOHNSON MARBONITE - DOUBLE CHARGE JOHNSON REFLECTO Nitco Duracottura Tiles Wall Tiles
3 | Vinyl Flooring | NA | Armstrong/Tusker
Carpentry Items
1 | BWR Plywood | Green Pro Certification | Vidya Ply and Board Pvt Ltd , Samrat,
1.1 | Commercial Plywood Plywood with "Free of Urea Formaldehyde" | Free of Urea Formaldehyde , FSC Certified, IGBC Registered | Century,V-CAN,Green Ply
2 | Marine Plywood Plywood with "Free of Urea Formaldehyde" | Free of Urea Formaldehyde , FSC Certified, IGBC Registered | Century, Samrat, V-CAN,Green Ply,
4 | Partition Framework | NA | Aluminium sections / India Gypsum : GI METAL FRAME PARTITION SYSTEM
5 | Block Board | Free of Urea Formaldehyde , FSC Certified, IGBC Registered | Century,Samrat, V-CAN, Vidya Ply and Board Pvt Ltd,Green Ply,
6 | Gypsum Board | Green Pro Certification | Gyproc Saint Gobin : Gypboard Plain Gypboard Fireline Board India Gypsum : Regular Gypsum Board Fire Resistance Gypsum Board USG Boral :
7 | Bison Board | NA | Bison
8 | Flush Door | Free of Urea Formaldehyde , FSC Certified, IGBC Registered | Century,Green Ply, Samrat,
9 | Laminate |  | Century,Green lam, Samrat, Royal Touch,
9a | Laminate Shade | Green Certification & IGBC Registered | Century Lam : # 525 - Fusion Maple Samrat : 485SF #Light Bavarian Beech and 816SF #Mangfall Beech
10 | Adhesive For Wood | Low VOC or No VOC as per IGBC Norms | Fevicol SH / Marine/ Hiper
11 | Rubberized Adhesive | Low VOC or No VOC as per IGBC Norms | Fevicol SR / Fevicol Heatx / Ezee Spray / SR-998
12 | Clear Float Glass, Toughened glass | Green Pro Certification | Saint Globain
13 | Back Painted Glass | Green Pro Certification | Saint Globain - Titanium Gray Asahi : Stone Grey and Sparling Snow White
14 | Full glazed toughened glass partition | Green Pro Certification | Saint Globain/Asahi / Modiguard
15 | Frame toughened glass door fitting | Green Pro Certification | Saint Globain/Asahi / Modiguard
16 | Acrylic Solid surface | NA | LG/Samsung/Dupont/Infini/ Granium
|  | NA | LG - Artic White # S006
17 | Roller Blinds | NA
18 | Fire Rated Door | NA | Kenwood / Promat
19 | Aluminium Composite Panel | NA | Eurobond # Bright Silver - ER 101 Red -ER 107 Silver - ER102
20 | Fabric | NA | Response - HDFC Blue
21 | Aluminium skirting / chair guard / hat section | NA | Bottomline/ Orno
23 | Modular Furniture | BIFMA / Green Guard / Green Pro Certification- (Interior products must produce BIFMA M 7.1, E3 / Green Guard Certificate (Sustainability) | AFC Furnitures , PSL and other brands approved by CPC team
Ceiling
1 | Gypsum Ceiling | Green Pro Certification | Gyproc Saint Gobin : Gypboard Plain Gypboard Fireline Board India Gypsum : Regular Gypsum Board Fire Resistance Gypsum Board USG Boral : Sheetrock Gypsum Board Firebloc Board
2 | Axiom Trim Channel | Green Pro Certification | Armstrong / USG Boral / India Gypsum
3 | Metal Ceiling | Green Pro Certification | Armstrong : 5488P1 / Indian Gypsum : Aluminium Ceiling Tiles
4 | Modular Grid Ceiling | Green Pro Certification | Armstrong -USG Boral : 0.7 NRC
Loose Furniture
| Center table , Coffee table. | BIFMA / Green Guard / Green Pro Certification- (Interior products must produce BIFMA M 7.1, E3 / Green Guard Certificate (Sustainability) | As approved by CPC Team
| Lounge seating / Sofas / Waiting Area Chair | BIFMA / Green Guard / Green Pro Certification- (Interior products must produce BIFMA M 7.1, E3 / Green Guard Certificate (Sustainability) | As approved by CPC Team
Hardware Items
1 | Aluminum Section | NA | Jindal / Hindalco / Nalco
2 | Floor Springs | Environmental Product Declaration is mandetor | Dorma/ Hafele / Ozone / Enox
3 | Door Closer | Environmental Product Declaration is mandetor | Dorma - Sap code: 66400101 Description: TS 68 Door Closer with Std Arm EN 2/3/4 Silver / Ozone / Enox
4 | Door Stopper | NA | Dorma - Sap Code: 9113304: Description Door Stop half dome 45mm dia / Ozone / Enox
5 | Magnetic Door Holder | NA | Dorma - Sap Code: 9112181 : Description: Magnetic Door Holder,satin chrome finish / Ozone / Enox
6 | Glass Handles | NA | Dorma - Sap code: 9125510 Description: TGD D 350 X 25 S, Satin SS 304 / Ozone / Enox
7 | Dead Lock (for Flush Door) | NA | Dorma - Sap code: 9120855 Description: 706 Dead Lock, 55mm Backset , SSS, Escutcheons - 01 Pair, EPC TTK Key -60mm Qty / Ozone / Enox
8 | Dead Lock (for Toilet Door) | NA | Dorma - Sap code: 9120855 Description: 706 Dead Lock, 55mm Backset , SSS, Escutcheons - 01 Pair,, One Side Tumb Turn Other side Coin Privacy Key -60mm / Ozone / Enox
9 | Door Hinges - Brass | NA | Dorma - sap code 9117214 / Description : BB4330, 5 Kn uckle, 2 Ball bearing butt hinges.Size: 4" x 3" x 3mm Grade SS 304 - Fin ish SSS / Ozone / Enox
10 | Cabinet Handles | NA | Kitch / Ozone / Enox
11 | Shutter Hinges | NA | Magnum / Palladium / Haffele / Ozone / Enox
12 | Latch | NA | Godrej / Tag / Hafele/ Ozone / Enox
13 | Tower Bolt | NA | Magnum / Palladium / Ozone / Enox
14 | Cylindrical Lock | NA | Dorma / Ozone / Enox
15 | Door Lock | NA | Dorma / Ozone / Enox
16 | Drawer Lock | NA | Hafele / Ozone / Vijayan / Godrej/ Enox
17 | Pedestal Lock | NA | Hafele / Ozone / Vijayan / Godrej / Enox
18 | Storage Lock | Environmental Product Declaration is mandetor | Hafele / Ozone / Vijayan / Godrej/ Enox
19 | Magnetic Ball Catch | NA | Magnum / Palladium/ Enox
20 | Aluminum Louvers | NA | Jindal / Hindalco / Nalco/ Geeta / Enox
21 | Screws | NA | GKW / Enox
Paint , Ceiling & Flooring Items
1 | Acrylic Emulsion Paint | Low VOC or No VOC as per IGBC Norms | Berger / Dulux/Nippon Paints/ Surfa Coats India Limited / AkzoNobel India Ltd
2 | Plastic Paint | Low VOC or No VOC as per IGBC Norms | Berger / Dulux/Nippon Paints/ Surfa Coats India Limited / AkzoNobel India Ltd
1 | Digital VAF meter | NA | L&T / Yokins
2 | RYB Indicators | NA | L&T / Tecknics / Vashno
3 | Panel tagging | NA | Anodised aluminum / Trafolite black on white with etched capital lettering
4 | APFC Panel ( Capacitor ) | NA | L&T / Vishay / Malde / Epcos
5 | AC outdoor power supply box enclosure should be IP66 / IP65 | NA | Devi Polymers / Hensel should be IP66
6 | HRC Fuses | NA | L&T / Schnieder / Siemens
7 | Fuse Switch Unit | NA | L&T / Schnieder / Siemens
8 | Glands | NA | ECG / EMI /Comet
9 | Lugs | NA | Dowells / Lotus
10 | Terminals | NA | Essen / Elmex
11 | Distribution Board With MCBs | NA | Legrand / Siemens /Schnieder/L&T
12 | MCCBs | NA | Legrand / Siemens /Schnieder/L&T
13 | ELCB / ELMCBs | NA | Legrand / Siemens /Schnieder/L&T
14 | Industrial Socket Outlet | NA | Legrand / Siemens /Schnieder/L&T
15 | Wires | NA | Finolex/ Polycab / KEI
16 | Cables | NA | Finolex/ Polycab / KEI
17 | PVC Conduit | NA | Precision / VIP
18 | Flexible Conduit | NA | Tubflex / Precision
19 | Switch / Socket | NA | Anchor - Roma /Legrand / North West /Gold metal
20 | Light Fixtures | Lighting Design with Low LPD | Wipro/Philips/havells/Bajaj /CG/Panasonic/Halonix/Polycab / Orient / Jaguar / Quadralumen
21 | Wall / Pedestal & Ceiling Fans | BEE 5 Star rating | Usha, Cromptom, Bajaj.
22 | Exhaust Fan | BEE 5 Star rating | Bajaj / Usha.
23 | Air Curtain | BEE 5 Star rating | Russell / Euronics
24 | LED fittings | BEE 5 Star rating | Wipro/Philips/havells/Bajaj /CG/Panasonic/Halonix/Polycab / Orient / Jaguar / Quadralumen
25 | ELCB - Sensitivity | NA | Sensitivity of the ELCB shall be 30mA for lighting and small power circuits (6A) and 100mA for AC and boiler circuits. Computer power circuits shall be provided with Hi-sense type ELCBs at 30mA or if not available then 100mA ELCBs
26 | Raceway thickness (AL / GI) | NA | Underfloor raceways shall be 1.60mm up to 38mm depth and 2.0 mm above 40mm depth
27 | Panel / Cables / DB Tagging | NA | Panel / all DB's / Main power cables should be tagged properly with Anodised aluminum / Trafolite black on white plate / phenolic tagging only will be permitted.